|  | ESRC Research Group for the Study of Care, Values and the Future of Welfare End of Award Report July 2005 |
| --- | --- |

Contents

1. Research Objectives 										2

1.1.	Background to ‘Care, Values and the Future of Welfare’ (CAVA) 			2

1.2. 	Outline of the Scientific Programme  							2

1.3.	Progress towards research objectives 							4

1.4.	Research Achievements, Results and Impact on the Research Field 		5

1.5.	Changes to or developments of the scientific programme 				9

1.6.	Unexpected outcomes									10

1.7.	Difficulties encountered 									11

1.8.	Potential future research priorities 							11

2. 	Dissemination 										13

2.1. 	Dissemination Timetable 									13

2.2.	Difficulties and unexpected outcomes 							17

3. 	Specific Impact on Policy and Practice 						17

4. 	Management 										18

References not included in Annexes 								20

Annex A - Outputs 										21

Annex B – Resources 										74

Annex C - Advisory Committee 									86

Annex D - Other Activities 									87

Annex E - Research Group Staff’s CVs 							112

1. Research Objectives

1.1.	 Background to ‘Care, Values and the Future of Welfare’ (CAVA)

The original research proposal was submitted to the ESRC Research Centres and Groups competition on ‘The Future of Social Policy’. Its starting point was that the social, economic, political and cultural conditions which sustained the Beveridge welfare settlement had changed. Changing patterns of women's and men’s paid employment, increases in divorce, lone parenting and long-term relationships outside marriage, an ageing population, women's claims for autonomy, and greater ethnic and cultural diversity, all challenged the normative structures of family life upon which post-war social policies were built. Within this broad context we focused on changes in parenting and partnering, and the implications of these for future social policies. However, our conceptual and methodological perspective on these changes took an innovative turn for we were interested in the moral texture of people’s lives as they lived with these social changes. This focus on values reflected a concern to understand people as creative moral agents which informed much of the core team’s existing areas of research (Finch and Mason, 1993; Smart and Neale, 1998, Williams et al 1999; Duncan and Edwards, 1999; Deacon and Mann, 1999). In addition, values and moral regeneration were central to the then newly elected New Labour government’s welfare reforms and family policy. Further, in using predominantly qualitative methods, we intended to carry out research on a wider, more holistic scale than is usually possible for qualitative work, and to capture an in-depth understanding of process to inform social policies.

We harnessed the investigation around the concept of ‘care’ and this enabled us to explore practices of relationality in and beyond families or households (e.g. friends, support networks). It also provided a possible frame for our empirical findings drawn from the debate in political theory around the ethics of care and its relationship to citizenship (Tronto, 1993; Sevenhuijsen, 1999).

  - Outline of the Scientific Programme

CAVA’s main objectives:

- To develop interdisciplinary, theoretical, conceptual and methodological parameters for research into care, values and the future of welfare.

- To undertake empirical research in the area of diversity and change in parenting and partnering practices.

- To develop cross-national perspectives with researchers in other western welfare societies.

- To develop the research findings into recommendations to inform policies and practice in the areas of care, intimacy and family life.

Researchers: periods and percentages of employment are shown in Annex B.

| # Director: Williams Deputy Director: Smart |  |  |  |  |
| --- | --- | --- | --- | --- |
| # Strand Leaders and Management Team |  |  |  |  |
| # Strands 1 and 2 ## Williams and Deacon | # Strand 3 # Smart | # Strand 4 ### Duncan | # Strand 5 Roseneil | # Strand 6 ### Williams |
| # Researchers |  |  |  |  |
| # Smart | # Neale | # Williams | # Williams | # Groves |
| # Duncan | # Duncan | # Smart | # Martin | # Roseneil |
| # Roseneil | # Ackers | # Roseneil |  | # Irwin |
| # Neale | # Mason |  |  | # Duncan |
| # Hollway | # Roseneil |  |  | # Smart |
| # Mason | # Budgeon |  |  | # Neale |
| # Martin | # Saugeres |  |  | # Deacon |
| # Irwin | # Hussain |  |  | # Churchill* |
| # Ackers | # Shipman |  |  | Gabb* |
| # May* | Shipman |  |  | Gavanas* |
|  | Katariya |  |  |  |
|  | Flowerdew |  |  |  |
| #### Support staff: Waite, Mosby, Jackman, Groves, Harvey |  |  |  |  |

* employed through other funding or additional ESRC funding

COMPONENTS OF CAVA’S RESEARCH

| CO-FUNDED PROJECTS |  | MAIN CAVA PROJECTS |  |  |  |  |  |  |  | CO-FUNDED PROJECTS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Funding for the 3 ESRC Seminar series: ‘Changing social norms, changing family law’ ;‘Knowing Families’; and ‘Non-familial Relationships across the Lifecourse’ |  | Strand 1 October 1999-May 2000 RETHINKING THE CONCEPTS Develops theoretical, conceptual and methodological frameworks for the whole research |  |  |  | Strand 2 October 1999-May 2000 EXAMINING THE EVIDENCE Reviews of existing and relevant empirical research on: *kinship, obligation and care *changes in households, work and welfare *user movements and grass-roots organisations *existing welfare strategies *citizenship, democracy and welfare |  |  |  | Leverhulme Professorial Fellowship Professor Selma Sevenhuijsen of Utrecht University to work with CAVA 2003-4 |
| Family restructuring, the common law marriage: myth and legal realism (Nuffield) (Duncan, University of Bradford (2000-02). |  |  |  |  |  |  |  |  |  | ‘Rethinking Families’ (Calouste Gulbenkian Foundation) (book project: Williams and Churchill) 2003-5 |
|  |  | Empirical projects |  |  |  |  |  |  |  |  |
| CAVA PhD Studentships: Sally Hines: Care and Intimacy in Transgender Communities. Oct 00 – Oct 04. Jackie Terry-Schuhmann: Volunteer-service User Relationships in Services for Disabled Older People. Oct 2001 - |  | Strand 3 October 1999-December 2003 CARE, DIVERSITY & FAMILY LIFE 1. Mothers, Care & Employment; 2. Families after Divorce; 3. Transnational Kinship; 4.Care, Friendship & Non-conventional Partnerships |  | Strand 4 September 2000-September 2003 CROSS-NATIONAL RESEARCH ON CARE, DIVERSITY & FAMILY LIFE International seminars to draw on research to mirror the research concerns of Strands 3 & 5 |  |  |  | Strand 5 March 2000-October 2003 COLLECTIVE VOICES ON CARE, DIVERSITY & FAMILY LIFE Investigates the claims of grass-roots groups, voluntary organisations and trade unions on parenting and partnering, and the challenges these make to social policy |  | Gay and Lesbian ‘Marriage’: An Exploration of the Meanings and Significance of Legitimating Same Sex Relationships (ESRC) (Smart, Mason, Shipman) 2003-6. _________________ Dr Emma Head 2004-5 ESRC Postdoctoral Fellowship on lone parents (with Williams) |
| Enduring Families Project (ESRC) (Neale, Flowerdew, Smart and Wade): 2001-3; Family Dynamics project (ESRC) 2004-5 |  |  |  |  |  |  |  |  |  | Marie Curie Post-Doctoral Fellowship: Migrant Domestic Workers in Three European Care Regimes (Gavanas and Williams) EU funded, 2003-2005 |
| Continuity and Change in Parent-Child Relations over three Generations (ESRC) (Wade and Smart). 2002-4 |  | Strand 6 March 2003 - September 2004 NEW VALUES FOR WELFARE Development of feedback into integrated findings for dissemination and to provide basis for various reports and recommendations for a new framework of values for social policy. |  |  |  |  |  |  |  | Parental Empowerment in Sure Start Programmes (NESS – Birkbeck College) (Williams and Churchill) 2004-5 |
| Residence and Contact Disputes in Court (Department for Constitutional Affairs) Smart, May, Wade & Furniss). 2002-4 |  | Additional ESRC Funding for Pilot Projects 2003-2005: - International Care Chains - Marrying in/Marrying out - Friendships and Non-Conventional Partnerships Revisited - Values, Care and Commitments amongst Parents of Primary School Children - CAVA National Survey 2005 |  |  |  |  |  |  |  | Leeds University Centre for the Study of Families, Kinship and Childhood and Centre for Interdisciplinary Gender Studies Seminars, Workshops and Conferences 1999-2005 |

1.3.	Progress towards research objectives

Here we report on two aspects of the objectives: the development of interdisciplinary working and cross-national perspectives, as the remaining objectives are covered in the subsequent sections

1.3.1.	Interdisciplinary working

The Research Group was composed of members from different disciplinary backgrounds: sociology, social policy, socio-legal studies, psychology and geography. The main opportunities for interdisciplinary work came from 6 workshops in Strands 1 and 2 which discussed a total of 29 new papers from CAVA members (See Annex A.6.2 for details) and this framed our future work. These included:

- geography expertise to develop a locality based methodology for our sampling (Duncan, see 1.4.1)

- sociological research on relationality and the negotiation of family change to inform our methods for investigating values (Mason, Smart and Neale)

- social policy and socio-legal understandings of challenges to the post-war settlement (Smart, Deacon, Williams)

- a synthesis of ideas drawn from social movement theory, the politics of recognition and social policy (Martin, Roseneil, Williams)

- a synthetic overview of our conceptual framework (Williams)

- psychoanalytic-informed research methods for understanding moral intersubjectivity which became incorporated into two of our projects (Hollway, Roseneil).

The development of an empirical basis for ideas on ‘the ethic of care’ drawn from political philosophy involved an International Conference in July 2000 organized by Roseneil for the Centre for Interdisciplinary Gender Studies on Gendering Ethics / The Ethics of Gender; the visit of Professor Selma Sevenhuijsen, a world leading expert in feminist political philosophy, from Utrecht University as Leverhulme Visiting Fellow; two workshops on ‘Care’ with a dialogue between care ethicists and disability researchers, and on ‘Ethics’ to which we invited theologians and moral philosophers.  In addition, some 20 day workshops and some 50 seminars on multidisciplinary themes relevant to our work were organized by CAVA members under the auspices of the Centre for Interdisciplinary Gender Studies and the Centre for Research on Family, Kinship and Childhood (listed in Annex D1.1-1.4).

All papers from the CAVA events were posted on the website and most incorporated into subsequent publications. What emerged from our workshops in Strands 1 and 2 was a research programme which sought to explore the empirical basis for sociological theories of individualization, the moral ordering of contemporary family policy, and theories of rationality and preference in household decision-making. This was informed by an engagement with philosophical theories of relational autonomy and the ethic of care, psychoanalytic theories of moral intersubjectivity, queer theory, and sociological and political theories of social relations, especially with reference to class, gender, ethnicity, sexuality, childhood and migration, as well as social movement theory of the ‘politics of recognition’. These shaped our methodologies which focused centrally on how, through in-depth interviews, to understand the basis on which people ground those relationships that matter to them.

1.3.2.	To develop cross-national perspectives with researchers in other western welfare societies

The main vehicle for this was our international seminar series in Strand 4 and the publications that followed. They allowed us to understand how family changes in the UK were context-specific, whist at the same time displaying general international trends. They also afforded opportunities to explore how policies could be different. ‘New Divisions of Labour?, January 2001; speakers from Netherlands, Sweden, UK, USA and Australia. Papers published in Special Issue of Critical Social Policy, 22 (1) 2002

- ‘Divorce, Separation and Changing Family Practices’, September 2001.Speakers from UK, Hungary, Australia, Norway, Netherlands, Ireland and New Zealand). Published in Special Issue of Childhood, 10 (2) 2003

- ‘Friends and Non-Conventional Partnerships’, January 2002. Speakers from USA, Canada, UK, Norway, Belgium. Published in Special Issue of Current Sociology, 52 (2), 2004.

- Collective Interventions on the Terrain of Care and Intimacy’, November 2002. Speakers from Finland, UK, Canada, and Sweden. Published in Special Issue of Social Politics: International Studies in Gender, State and Society, 11 (2) 2004

- ‘Moving and Caring: The Impact of Migration on Kinship and Care’, September 2003. Different country specialists from UK and Australia.

Professor Selma Sevenhuijsen from University of Utrecht, Netherlands was Leverhulme Visiting Fellow with CAVA, 2003-4. This resulted in a joint paper by Williams and Sevenhuijsen presented at the Institute of Education’s ‘Employment and Care’ seminar at Cumberland Lodge in October, 2003, and influenced subsequent publication (Williams 2004a,e).

Migrant Workers in European Care regimes: With the support of additional funds awarded to the Group in 2003, Williams worked with Dr Anna Gavanas, who was subsequently awarded a two year EU-funded Marie Curie fellowship. The joint project is an empirical investigation of migrant domestic/child care workers in three cities – Stockholm, London and Madrid. In addition to various conference papers and publications, the project has led to further important collaborations with the International Network Gender, Welfare and Citizenship in Europe and with the University of Cork, Ireland (see 1.8.2 below).

WELLCHI: EU 6th Framework, Coordination Action, ‘The Well Being of Children: The impact of changing family forms, working conditions of parents, social policy and legislative measures’ was a direct result of EU collaborations led by Smart.  It is a series of seminars and conference held across the EU, and will become a depository of information and statistics concerning the well being of children throughout the EU region.  The first seminar was held in Leeds in November 2004 and this was the launch event.  This cross-national work and our project on Transnational Families benefited from the input of Professor Louise Ackers, Director of the Centre for the Study of Law and Policy in Europe at Leeds University (see Annex D1.2)

The CAVA International Symposium Rethinking Care Relations, Family Lives and Policies in December 2004 brought together leading scholars from Finland, USA, Germany, Sweden, The Netherlands and Hungary for presentations and discussions of our work (an edited book from the symposium is under negotiation).

International Visits: Included among 60 visitors from 16 countries were Professor Anneli Antonnen, from Tampere University, for a month in November 2002, and Dr Pauline Stolz from the University of Målmo, Sweden for 2 months in Spring 2005, and Dr. John Murphy, Associate Professor, Politics and History, RMIT University, Melbourne in October 2003. Dr Vanessa May from Abo Akademi University in Finland worked on the LCD-funded project on Contacts and Resident Disputes in Court. We have also given papers on CAVA’s research to the Nordic Council of Ministers Research Programme on Active Citizenship, Marginality and Welfare and the STAKES research institute in Helsinki.  Links with our work on divorce have been established with the International Institute for Socio-Legal Studies and the Institut d’Infancia I Mon Urba, both in Spain, and both the National Family Law Association and the Children’s Issues Centre in New Zealand and the Australian Institute for Family Studies. The Leverhulme Interchange enabled links with the Centre for Feminist Legal Research in New Delhi.  In addition, members of the Group have over the period taken up Visiting Fellowships at the universities of New South Wales, Adelaide, La Trobe, Melbourne, Roskilde , UCLA and Auckland. Hines, CAVA PhD Student, was awarded Worldwide Universities Network funding to study for a term in 2003 at the University of San Diego.

1.4.	Research Achievements, Results and Impact on the Research Field

1.4.1. 	New methodologies for studying care, values and diversity

- Our sampling and subsequent analysis was framed by an innovative methodology of the ‘geography of family formations’ based on analysis of large scale quantitative data sets (Duncan and Smith, 2002). This mapping of variations in family type by locality enabled us to find a basis for the selection of case study areas that reflected the programme’s concern with partnering and parenting, rather than simply relying on traditional area classifications by class and local economy. The 6 ‘CAVA localities’ were Craven, Barnsley, Burnley, ‘transnational’ Bradford, Hebden Bridge, and ‘alternative’ Leeds (see Rethinking Families p.95 for description). Each of the Strand 3 projects and the locality element of Strand 5 was carried out in 3 or 4 of the CAVA localities.  This meant that there was an overlap which gave the work as a whole a broad geographical reach notwithstanding the qualitative nature of the individual studies. Ethnographic work in the localities provided each qualitative study with the best opportunity of sampling from diverse communities. Although each study could not address every important dimension of social diversity, together they ensured that we included people from a range of minority ethnic communities, class backgrounds, religious backgrounds, and generations, as appropriate. So, for example, the Families after Divorce Project was carried out in 3 of the CAVA locations and sampled from the dominant White ethnic community (where religious affiliation was predominantly Church of England or agnostic depending on age group), the Jewish community, and the Muslim community. In this way the projects produced data beyond the scope of most small scale qualitative studies while retaining the ability to work intensively and in-depth with our interviewees.

- Our research into people’s values was based on a theoretical understanding of moralities as situated and contextual, so our interviews focused not on abstract moral principles or questions about 'what is right or moral' but on 'what matters' in people's everyday lived experiences of parenting and partnering (Mason, 2002b). Thus, the Strand 3 projects all took as a core focus the issue of how to understand the basis on which people ground their relationships, and on what basis they act to preserve, nurture, sever, or pursue relationships with others. In our analyses we refer to this ‘what matters’ element variously as ‘operational moralities’, ‘gendered moral rationalities’ and ‘practical ethics of care’. This, of course, posed methodological challenges which were resolved in different ways in different projects.  For example the Care, Friendship and Non-Conventional Partnership project developed the use of the psycho-social free association narrative interview method, which was used longitudinally. Families after Divorce and Transnational Kinship projects interviewed different generations of the same family to capture how values are negotiated across generations. Each project focused on a significant aspect of change in family lives and personal relationships. In Strand 5 (Collective Voices) the question of what matters was extended to the practices of self-help groups and to the political value-discourses of trade unions and voluntary organizations campaigning around parenting and partnering issues.  We thus examined values around parenting and partnering at individual and collective levels and within and beyond families. A triangulation opportunity was provided in 2005 through a National Survey.

1.4.2.	New knowledge about care, values and social change

How relationality and commitments to significant others shape and are shaped by normative ideas about care:

- The Mothers, Care and Employment study explored how mothers combine mothering with paid work, how they allocate time and tasks with partners, and choose appropriate childcare. It found that while there are differences in whether mothers work full-time or part-time or not at all, what they share is that their decisions are based primarily on doing the right thing for their children. Central to this is the mother/worker identity they hold. Money does matter, but normative views of what constitutes a ‘good mother’ matters more (Duncan et al, 2003,2004; Duncan, 2005a,b). (Social variations in identity are detailed below).

- Similarly, in the Families after Divorce project, we found that divorced parents did not necessarily rush to remarry because they were increasingly attentive to the difficulties that could arise, especially for their relationships with their children from introducing a new person into the household. They were also aware of the wider options available to them, for example living apart together, rather than co-habiting.  We found that a new ‘moral code’ was available to these parents, namely, staying apart for the sake of the children. This illustrates how new forms of commitment and a refinement of values can arise in response to changing conditions (Neale, 2005 forthcoming). Grandparents interviewed in this study often had had to face difficult situations where they morally disapproved of divorce, and yet, faced with this as a reality in their own children’s lives, they found it difficult to condemn their children in these blanket terms The value which guided them through the dilemma was that of commitment and support: of standing by their children in times of trouble (Smart and Neale, 2003; Smart, 2005a,b).

- The Transnational Kinship study of caring commitments of second and third generation Irish, Pakistani and Indian family members produced insights into the normative journeys that people take; having perhaps arrived in England with a specific set of values which ebbed and flowed over the life course, being retained and not retained to different degrees at different moments. It is oversimplifying to depict this change as ‘assimilation’ or the adoption of ‘Western values’.  Instead what emerged was often a new form altogether which combined and subtly modified different elements of different value systems. Such complex ideas as the ‘arranged love marriage’ for example, captures succinctly how parental responsibilities may be retained by the older generation in a changing cultural context, while at the same time allowing the younger generation still to adhere to ‘traditional’ values (see  Smart and Shipman, 2004; Mason, 2004b).

- The Care, Friendship and Non-conventional Partnership project which focused on those who do not live with partners found a strong value in the importance of having friends and a high degree of reliance on friends, as opposed to biological kin and sexual partners. This was particularly important for the provision of care and support in everyday life, and especially in relation to psychological distress and mental illness. In this way, the sexual/ love relationship was not the exclusive, and often not the primary, space of intimacy and was becoming de-centred in people’s ‘relationship landscapes’. In addition, there was sexual/love experimentation with non-cohabitation a clear choice for many (Roseneil and Budgeon, 2004).

- An overall message emerging from this body of publications is that investigating the processes and practices of embeddedness and connectedness yields an important picture of contemporary family lives and personal relationships. The shape of people’s commitments may be different in so far as they are less dependent on blood or marriage ties, and may extend across to different households linked by dissolved marriages, reconstituted families, non-resident partners and transnational kin. There may be more blurring between kin, ex-kin, sexual partners, and friends in people’s networks, but little of this indicates a loss of commitment itself. When faced with dilemmas they generally negotiate what they think is best in and through their commitments to others, especially with reference to the well-being of their children (Smart, 2004b; Roseneil and Budgeon, 2004; Williams, 2004a ).

- Drawing together ‘what matters’ to people from our different projects, including our co-funded projects which interviewed children, we identified the following as some of the practical ethics which facilitate resilience: attentiveness to others’ situation, accommodating one’s own needs to those of others, adaptability to others’ changing identities, and being non-judgemental enabled people to find ways of coping with their family lives and personal relationships, even though they might have found those transitions hard. Children valued fairness, respect, care, communication and trust in coping with changes in their family lives (Neale and Smart, 2001; Neale, 2004, Smart, 2005, forthcoming). These values indicate the moral texture of people’s commitments and constitute ‘a compassionate realism of good-enough care’ (Williams, 2004a).  Interestingly, these ethics resonated with the findings of the Strand 5 interviews with local self-help groups where we found practices of care and support based on principles of trust, reciprocity, non-judgementalism and mutual respect were felt to provide an important alternative to professional support (Williams, 2004f).

These last two bullet points pose important challenges to theories about family lives, to public debate, professional practice and current policy, discussed later.

The Significance of Context for Diversity and Change

- In the Motherhood, Care and Employment study ethnicity and variations in family conventionality (Duncan and Smith, 2002a,b) were associated with major differences in mothers’ gendered moral rationalities concerning employment, partnering and childcare. For example, Black mothers were most likely to see full-time work as part of being a good mother, while ‘alternative’ White mothers were particularly likely to value child development in childcare.  Class differences, although less important, were also found. These were not, however, simply co-incident with major working/middle class cleavages.  Rather, class differences related more to nuanced patterns of social identity. Furthermore, decisions were influenced by social networks and the customs of local neighbourhoods, which themselves could be historically produced (for example, traditions of female employment in the ex-cotton town of Burnley) (Duncan, 2005b). This finding was supported in two further ways. The mapping of the geography of family formations in Britain through national statistical datasets demonstrated the significance of local economic and cultural context in the constitution of family ‘types’ (Duncan and Smith, 2001a, 2002a,b).  Second, a small survey of the work/ care behaviour of parents with children at primary school  where local neighbourhoods and school networks act as reference groups in shaping the repertoire of norms available to parents in working out how to combine work and care (Duncan and Irwin, 2004). Along with findings from our other projects, we propose that choices people make around parenting and partnering are not simply ‘free’ preferences, nor simply determined by social positioning, but emerge in complex patterns from moral considerations of what is right for their children, and are shaped by bonds of love, affection, association and place.

- The claims of the local self-help groups we studied were influenced by local cultural contexts, and were both enabled and constrained by dominant local and national political discourses, and the funding opportunities that these make available. Priorities around crime and community safety, health and social exclusion, skewed claims around parenting and partnering. For instance, the national priority given to the needs of children and to education leaves some groups of children and their parents out of the frame, especially older children and children with behavioural or learning difficulties.

- The imbrication of cultural and policy contexts of care at local, national and international levels is the focus of the co-funded study of Migrant Domestic Workers in European Care Regimes where data from interviews with migrant women who care for children in private homes and employers reveal different ‘moral’ meanings of such employment in Sweden, UK and Spain. In all countries it marks the re-emergence of traditional forms of domestic work under the new conditions of increased female employment and of female migration. However, whilst such domestic/care work is normalized in Spain, which has no tradition of public child care, in Sweden it is emerging, facilitated by local networks, in spite of extensive public provision and a culture of egalitarianism which views such employment as morally repugnant (Gavanas, Tobio and Williams, forthcoming).

1.4.3.	Theoretical challenges and new theorizations

Critiques of Individualization

- The above findings challenge the individualization thesis -the idea that we now live in a highly individualized society, where commitment to others is less significant than a commitment to individual self-fulfillment and self-actualization (Giddens, 1992; Beck and Beck-Gernsheim, 1995; 2002). This sociological conceptualization of modern life frames contemporary understanding of social and family relationships. However, our research shows how people value connectedness, how they remain committed to others - even if the commitment does not take a traditional form as in marriage - and how it is vital to go beyond analyses based on couple relationships in order to understand how contemporary, diverse families actually work. Our findings reveal the complexity of family and intimate lives and the extent to which people are attentive to one another, even though what matters within families and across generations may be changing (Duncan, 2005a,b;  Irwin,2005;  Neale, Smart, 2005a; Williams, 2004a). At the same time, the bleak, dystopian vision found in contemporary theoretical accounts of relationships and family life (e.g. Bauman, 2003) or assertions in public moral debate of the way selfish individualism, acquisitive consumerism or a parenting deficit are thwarting family lives (e.g. Etzioni, 1993) finds little support in our findings. Even amongst those who might seem to be most “individualized” (those who live without a co-resident partner), their lives are enmeshed in complex relationships with friends, partners, biological kin and, sometimes, ex-partners and their kin (Roseneil, 2004b). In addition, these processes of individualization may be context-specific and modernized forms of ‘traditional’ social processes, like suburbanization (Duncan and Smith, 2006).  Other theories that posit instrumental financial rationality as the basis to family decision-making, such as the ‘new household economics’ (Becker, 1991) are also discounted.  At the same time, whilst the idea of negotiation between partners is helpful, it can underestimate the extent to which some groups accept traditional gendered roles and discourses as non-negotiable or given (Duncan et al, 2003, 2004).

New analyses and theorizations

- Our empirical work has led us to engage with middle-range concepts of ‘relationality’, ‘contextualization’, ‘embeddedness’  and ‘care’ which capture a different lived reality with more texture and mutual responsiveness than the individualization thesis, Thus, Smart and Shipman (2004) and Mason (2005) analyze how people negotiate their way through competing demands and claims made by family members, by religious ideals, by ‘ideas’ of community and so on, in order to arrive at ways of balancing commitments with personal ideas of how to live their ‘own’ lives. The Families after Divorce study demonstrates the way in which the decline of horizontal commitment (e.g. between spouses) was met by an increase in vertical commitment (e.g. between grandparents, adult children and grandchildren) (Smart, 2005b). Roseneil‘s forthcoming book Sociability, Sexuality, Self: Relationality and Individualization proposes a queer theorizing of individualization which examines counter-heteronormative care and relationship practices, yet still holds relationality as central to the contemporary social condition.

- Duncan (Duncan et al, 2003, 2004; Duncan 2005a,b) has developed the concept of ‘gendered moral rationalities’ to understand the relationship between identity and moral agency, which finds support at the quantitative level in the ’geography of family formations’. Neale (forthcoming) refers to the ‘repertoire of moral values’ that people draw on as appropriate to the context and relationships they are in.

- The cross-generational data from the Families after Divorce project was able to demonstrate how people carry two sets of (often incongruent) accounts about their families - their actual married lives (or the lives of those around them or in their wider families) and how families ‘should be’ or how couples should relate to one another. This has potentially important policy implications (Smart, 2005b) because while people may subscribe to the idealised model, their actually family life may take a very different shape.  The question this raises is whether policies should meet the needs of the idealised family or the actual family.

- Smart (2005b) has produced a theoretical account of how different values interact and how people can ‘carry’ values which derive from their origins and early kin relationships, yet also take on board different values introduced by social change and their need to accommodate to changing circumstances and experiences. Irwin’s forthcoming book (2005) Reshaping Social Life draws on CAVA interviews and other empirical data to develop new analyses of change in family organisation, divisions of gender, and work and care. It analyses perceptions of ethnicity and belonging, social inequalities and fairness, as these relate to diverse contexts and social positions. As such it elaborates in new ways the link between norms, values and social inter-connections and their relationship to social structure (Irwin, 2004, CAVA symposium).

- Our research findings have provided the basis for rethinking ‘care’ as an analytical, political and ethical concept in social policy, and for developing a new framework for policies around child care, children’s citizenship, partnering and parenting after divorce, parenting support, education, work/life balance (inter alia, Neale and Smart, 2001, Duncan et al, 2003, 2004, Neale, 2004a, Williams, 2004a). Williams argues that care provides an important analytical lens on changing welfare regimes, on globalization, and on social movements (Williams, 2001, 2004d)  It also provides a vision for thinking about the future – for developing a ‘political ethic of care’ (2004a, 2005d). Drawing on our analysis of the value discourses of voluntary organizations which centre upon care, well-being, respect for children and social justice (Williams and Roseneil, 2004), she argues that current social policies tend to underestimate the importance of the practical ethics of relationality in people’s lives. Developing the arguments of Sevenhuisjen and Tronto, Williams proposes in Rethinking Families and elsewhere that the giving and receiving of care needs to be understood as universal, and as activities which are central to citizenship. More generally Williams argues for a ‘social environment of care’ that would encompass, amongst other things, the environment, transport, local democracy, a refocusing of education, a restructuring of social security and of the care workforce, and respect for old age and childhood (Williams, 2005a,d, and SPA address 2005)

- Influenced by CAVA’s work, Hollway’s forthcoming book about gender, parenting and care, Capacities to Care (2006), develops these themes through a psycho-social perspective and offers a ‘radically relational’ account of subjectivity that goes beyond individualism and social constructionist accounts, informed by the work  of Klein, Benjamin, Winnicott, Mitchell and others.

- Deacon has drawn upon CAVA’s findings in his debtes about welfare conditionality (2004b, 2004c, 2005), arguing that conditionality need not be incompatible with an ethic of care but should be grounded in everyday moralities.

Our work has impacted in different ways: in sociology it brings a critical mass of qualitative evidence to scrutinize theories of social change which focus upon families and personal relationships, and to provide alternative more nuanced theoretical accounts of the relationship between values, practices of care and intimacy and social change. Our research has successfully test-driven sociological and psycho-social methodologies for investigating everyday moralities and provided a basis for the reintroduction of values and everyday moralities into sociological analysis. In social policy we have provided a way of linking empirical data on cultural practices at the micro/ local level to an analysis of current family policy nationally and cross-nationally, and used this to explain the dissonance between the normative family of government policy and lived family practices.

1.5.	Changes to or developments of the scientific programme

Minor changes to the programme are reported in the 4 Annual Reports; here we account for the major changes.

- Strand 4: before the programme started we concluded that it would not be possible to conduct our own ‘in house’ cross-national research, given the time, linguistic skills and substantive knowledge required.  We therefore decided to mount a series of international seminars. These were not only effective in providing a cross-national perspective, but were successful in terms of international dissemination and impact (see 1.3.3).

- Transnational Kinship Project: This was originally conceived as the ‘Diversity Study’ and was to study caring networks across the generations in a selected number of families of different ethnic origins. After discussion and expert consultation, this changed focus to become the ‘Transnational Kinship Study’.

- The ‘geography of family formations’ generated two key developments: use of the methodology developed to analyse and describe the geography of family formations in Britain as a whole; use of this material as an additional stance in assessing theories of family individualisation

- Two developments in the ‘Mothers, Care and Employment’ project: 1. Integration of the interview data from CAVA with complementary data from two earlier projects which enlarged the interview base and extended coverage of a wider range of social groups and geographical areas (Duncan et al, 2003, 2004). 2. Class differences emerged as more important than originally envisaged, although this related to nuanced intra-class / context located groups rather than broad class divisions. This led to both an empirical investigation of the nature of these differences; with the help of Hollway an adoption of psycho-social techniques not used before in this project; and the development of theoretical frameworks around preference, rationality, biography and habitus (Duncan 2005b).

- Additional funding for four additional projects (see diagram in 1.2), all of which provided excellent resources for our developing analyses. For example, it generated a successful application to the EU for a Marie Curie Fellowship, and in the Care, Friendship and Non-conventional Partnerships project it facilitated the re-interviewing of 25 of the 53 interviewees and introduced a longitudinal element into the research design. Our co-funded projects have been very important sources of further data, particularly in the interviews with children.

- Strand 6: Our original intention had been to create an iterative process of, on the one hand, an integrative analysis across our research findings, and, on the other, dialogue about these findings with the people we had interviewed through the ‘Citizens’ Dialogues’, and with policy makers and other research user groups through local and national ‘Feedback Forums’. However, two important opportunities emerged in 2003 which made us shift our strategy and schedule for the last 18 months. The first was an offer from the Calouste Gulbenkian Foundation to fund a book for policy makers and the other was ESRC funding for a media fellow to work with us on our dissemination strategy. We decided to change our schedule and use our energies to focus on the dissemination strategy, using this as a source for Rethinking Families, and using the book as a resource for user dissemination. In retrospect this was a good decision.  We held two ‘Citizens’ Dialogues’, drawn from some of our interviewees and practitioner contacts. Discussion was based on a number of ‘care dilemma’ scenarios drawn from our data. (The groups were filmed by broadcasting students in the University as part of their final year project and edited into a short video film). With additional funding from the ESRC, we approached Leeds Citizens’ Panel with a view to using their 1,000 representative sample for a survey on our key findings. However, early in 2005 the Leeds City Council decided they were going to reconstitute their Panel and we would have to wait another 9 months. At that point we decided an alternative strategy of data triangulation through commissioning a National Survey through QA Research, using this as a form of pilot for a module in the 2006 British Social Attitudes Survey. This was completed and the first report is due at the end of June 2005.

- We were granted a ‘no cost extension’ initially from September 2004 to end December 2004 in order to allow us time to hold our International Symposium at a point when it would not clash with competing events, and then a further 3 months’ extension to end March 2005 in order to complete the Survey.

1.6.	Unexpected outcomes

- The description of the geography of family formations in Britain showed this was only contextually linked to geographies of class, prosperity and urbanisation, and should in many ways be treated as socially autonomous.

- The analysis of the key indicators of family change in Britain shows that theoretical accounts of family change emphasizing individualization are not only over-stressed but that different changes take place in different areas, with different social and geographical rationales

- The emergence of contextual class differences as a major division in mothering, care and employment.

- The Care, Friendship and Non-conventional Partnership study revealed the extent of psychic distress and mental illness amongst the interviewees.

- The Transnational Kinship, the Families After Divorce and the Marrying in/ Marrying Out projects identified the ways in which religious faith, often reconfigured as a cultural heritage, remains central to how some minority ethnic groups ‘do’ their family life.

- The media fellow was an excellent source of contacts with policy-makers.

- Significant proportion of those telephone-interviewed in the National Survey indicated enthusiasm for further face-to-face interviews.

1.7.	Difficulties encountered

  - The initial Research Officer on the Transnational Kinship Project left at the conclusion of the interviews with Pakistani respondents.  This meant that we employed 2 casual interviewers for the Indian and Irish communities as well as deploying some of Neale’s time to assist with these.  The main disadvantage was a loss of continuity. But one main advantage was that we were able to interview some people in their first language because the interviewer for the Pakistani sample was Pakistani and the interviewer for the Indian sample was Indian.   We felt that this was important, especially for older members of the groups.

  - Our aim in the Families after Divorce project was to interview a divorced parent and one relative (typically a grandparent) from the same family group.  We were only partially successful because the project encountered problems of reaching as many family members as originally planned. Interviewing family members raises ethical issues regardless of the substance of the interviews and we found that the sensitivities surrounding divorce and the problem of potentially sharing intimate knowledge about wider kin, was a major obstacle.  Even where parents were happy to pass us on to relatives, the relatives were not always comfortable with the prospect of being interviewed. These difficulties made us reflect on some of the methodological challenges of researching relationality.   Increasingly research on families and relationships seeks to capture how people relate, how lives are lived and linked with each other, in order to present a more realistic understanding of the social space of families.  Yet, often research can only access one individual and so has to speculate about interconnections.  We were successful in accessing some of the interconnections in this study and we regard this as a methodological advance, yet there is still a long way to go to work through the ethical problems and the bias that may be introduced because of high rates of refusal.  Methodological challenges such as these are the focus of a major ESRC project led by Mason which focuses explicitly on ‘Multi-dimensional Methods for Real Lives Research’.

  - Delays caused by personnel changes, moves and long-term illness; poor quality of a large number of transcriptions (which in the end we rectified ourselves because of the cost and time in having them re-transcribed), corruption of coded data, and delay of 2001 census data meant that the CAVA case study areas had to rely on 1991 census data. All this cut into our time, some of which we regained, mainly through extra effort and reassessment of priorities, but it left us with less time than we would have liked to do analysis of the data across the projects as well as within them (although see Irwin, 2005 and Williams, 2004a)

1.8.	Potential future research priorities

CAVA now exists as a University of Leeds Research Centre for the study of Practices, Policies and Ethics of Care. The CAVA research has provided a springboard for the further development of new areas as well as a solid basis for consolidating new contributions to theory and policy.

1.8.1.	Development of methodology and application to the interdisciplinary study of dynamics of intimacy and personal and social relationships:

- Developing longitudinal qualitative research: Neale was awarded an ESRC grant in 2004 to study Family Dynamics After Divorce: A Meta-Analysis of Longitudinal Qualitative Data  followed by an ESRC  Research Fellowship on Time, Texture and Young Lives: Developing Qualitative Longitudinal Research. Since then she has  developed a consortium bid under the ESRC Changing Lives and Times Qualitative Longitudinal Initiative to explore personal relationships and identities across the life course, using QL methodology to capture the timescapes of real lives and how they unfold under the conditions of late modernity.

- Developing mixed methods: successful bid to become a ‘Node’ for the ESRC National Centre for Research Methods on ‘Multidimensional methods for real lives research’ involved Mason (Director) Irwin, Neale, Smart, and Ackers (2005-2008).

- Developing research on those living outside the conventional family, particularly on those living alone and on those in non-cohabiting relationships, on friendship, and on the psycho-social dimensions of individualization: Roseneil and Hollway are developing a participatory approach to the free association narrative interview method, and are using the Care, Friendship and Non-conventional Partnership project data as a basis to a pilot project with a view to seek future funding. Hines, one of CAVA’s PhD students received an ESRC post-doctoral fellowship (2005-6) to consolidate her thesis on transgender identities.

- Complementing CAVA’s ‘intensive’ research, we have begun ‘extensive’ research on patterns and distributions in family and ‘non-family’ lives and personal relationships, using a National Representative Survey of 555 telephone interviews and a Black and Ethnic Minority booster sample of 99. Following on from this, Duncan in association with the National Centre for Social Research is seeking funds to lead a CAVA-based team to place a module in the British Social Attitudes survey in 2006 which will generate a more robust analysis of the nature of contemporary care and commitments. In addition, Duncan and Smith are refining their work on the geography of family formations.

- Further secondary analysis of the data: both the CAVA and the Sure Start research suggest there is a need, especially with respect to policy interventions, for a much more nuanced understanding of the meanings of class, ethnicity and gender in parenting practices. Williams, Duncan, Churchill and Head aim to seek funding to develop such analysis.

- Smart, Mason and Shipman will take up new posts at Manchester University in September 2005 where Smart and Mason will set up and lead the Morgan Centre for the Study of Relationships and Personal Life.

1.8.2.	Cross-national perspectives on Care, Intimacy, Citizenship and Collective Action

- Following their collaboration with Professor Constanza Tobio of Spain and an international team to provide a comparison of migrant domestic work in Spain, Sweden and UK (Gendering citizenship in Western Europe: new challenges for citizenship research in a cross-national context, Policy Press 2007), Gavanas and Williams have submitted a proposal Migration and Networks of Care in Europe, to EUROCORES  in collaboration with Dr Linda Connelly of the University of Cork, with partners in Netherlands, Germany, Sweden and Italy. In this Williams proposes to advance cross-national analysis of European regimes of welfare, care and migration, and Gavanas to investigate further domestic work in Sweden.

- Developing the ‘Collective Voices’ project, Roseneil will be collaborating with Professor Nickie Charles of Warwick University on an ESRC project Gender and political processes in the context of devolution providing a study of the new discursive and political opportunity structures created for social movements and NGOs given women’s increased representation through devolution. Roseneil is also a partner in a €4 million EU Priority FP-7 integrated bid on The Construction of Female Citizenship developing research on the Transformation of Intimate Citizenship in Europe.

1.8.3.	Consolidating Theoretical Advances

- The CAVA research has provided the opportunity to re-examine theories around care, intimacy and family change. Williams has applied for funding (Leverhulme Major Research Grant) for a book project on Reinterpreting Care: New Ethical, Social and Political Dimensions of Care in a Welfare Society which brings together theoretical research on care, a new cross-national analysis of changing care regimes in Europe with new policy agendas for thinking about care provision in the 21st century.  Smart is writing a monograph on family and personal life based on ten years of empirical research. Together with Irwin’s, Roseneil’s and Hollway’s books identified in 1.4.3 and Neale and Flowerdew’s forthcoming Moving On: The Changing Lives of Young People after Parental Divorce , these will make substantial contributions to the fields of family and social change, childhood and youth research, the practice and policy of care, cross-national social policy, queer theory and psychoanalytic theory.

2.	Dissemination

Between October 1999 and March 2005 we published 28 books and reports, 88 articles in journals representing 12 different disciplinary areas, and a further 56 book chapters. We have produced 5 special issues of journals based on CAVA's research and seminars. Of the 332 seminar and conference papers we have given, 118 have been international, 72 were to practitioner/policy audiences, and 70 were keynotes or plenaries. We have organised 22 public seminars/lectures/conferences through CAVA and a further 110 under the auspices of the Centre for Research on Families, Kinship and Childhood and the Centre for Interdisciplinary Gender Studies at the University of Leeds.  Our work has received mention in 84 media pieces (mainly practitioner and national broadsheets) and we have appeared on 35 radio and TV programmes talking about our work.

Our earlier dissemination is detailed in our Annual Reports; however, from the end of 2002 we developed a concentrated strategy which linked our dissemination to academic and non-academic audiences. This was greatly helped by the appointment of a Media Fellow (Angela Phillips) to work with us from July 2003 for a year, and by our decision to convert a secretarial post into a communications co-coordinator post (Dr Keleigh Groves) as well as by Mosby’s web-site skills. The focus for some of this work became the Rethinking Families book. Much of the detail of our dissemination is given in Annex B 3,5 and 7, and we have also described the reasoning behind our strategy in Annual Report 2003: 27, so here, in order to give a sense of the effectiveness of the strategy, we show how our dissemination events rolled out over 2003-5.

Dissemination Timetable Jan 2003 – March 2005

| Jan 2003 |  | - 2-day ESRC Media Training in London for Williams, Smart, Deacon, Duncan, Roseneil, Groves and Shipman. - Williams’ public lecture to the Centre for Policy Studies in Education at the University of Leeds. Practitioner and academic audience. |
| --- | --- | --- |
| Feb 2003 |  | - Neale gives keynote address on ‘Parenting Arrangements for Children after Divorce: Children’s long term perspectives’ to UK College of Family Mediators Annual Conference, Swindon. - Appointment of Keleigh Groves as Communications Co-ordinator through H.I.C., existing staff costs and £15,000 supplement from ESRC for March 2003 to September 2004. - Appointment by ESRC of Media Fellow, Angela Phillips, and first meeting to develop strategy for June 2003 - June 2004. - Meeting with Gulbenkian Foundation regarding the funding offer to publish a book aimed at policymakers for publication in 2004. Initial contact based on Gulbenkian Director reading Williams’ piece in Times Higher Education Supplement in September 2002. - Seminar by Williams and Duncan at ODPM. Contacts established. |
| Mar 2003 |  | - Establish daily e-briefing service for the Group on parliamentary developments, government reports and breaking news stories that may provide an opportunity for the Group to publicise their research. - Smart on BBC Radio 4’s Analysis on ‘marriage’ and later on BBC Radio 4’s Thinking Allowed on ‘changing commitments’. - Roseneil on BBC’s World Service on ‘changing patterns of relationship formation and individualisation’. |
| Apr 2003 |  | - Neale’s keynote address to the Gingerbread Regional Bi-Annual Conference. Practitioner audience. - Roseneil on BBC Radio 4’s Woman’s Hour on ‘the company of women’. - 29th April: Smart gives an interview on ‘Changing Commitments’ on BBC Radio 4’s Thinking Allowed. |
| May 2003 |  | - Initial Findings Seminar to Advisory Group and invited audience. - Meeting with Phillips to organise the Citizens’ Dialogues for the autumn and possible themes for dissemination. |
| Jun 2003 |  | - 4th June: Smart gives an interview on ‘’Changing Nature of Family’ on BBC Radio 4’s Thinking Allowed. - Day Workshop for Research Group organised by Phillips at Leeds University to pull together key themes for different media outputs. This is combined with a discussion of integrative analysis. - Parliamentary and Public Affairs training, organised by the ESRC, for Groves and Roseneil. - Mary MacLeod - NFPI’s Chief Executive and Advisory Group member - article ‘Drawing the Boundaries between State and Family’ appears in the June edition of the ESRC’s The Edge. |
| Jul 2003 |  | - Contract with Gulbenkian agreed. - Research Group workshop to finalise themes for integrative analysis for the Gulbenkian book, the Media Fellow and for joint academic publications. - Meeting with Phillips to finalise dispersal approach. - Roseneil on BBC Radio 4’s Woman’s Hour on ‘do lesbians really want to marry?’ - First media hit: ‘Children before Money’, Guardian, 30 July, by Phillips. - Requests for information from: Department for Work and Pensions (DWP); House of Commons’ Statistics Resource Unit; Equal Opportunities Commission; Social Care Institute for Excellence (SCIE); New Opportunities Fund; Commission for Health Inequality; London Advice Services Alliances; Parents at Work; Leicester City Council; Lewisham Council; South East England Development Agency (SEEDA); Somerset Learning and Skills Council; European Work and Employment Research Centre; Bright Horizons; and Nursery Market News. - Williams interviewed for BBC 1’s Six O’clock News (30 July); research featured on BBC Interactive; Duncan on BBC Radio 4’s Woman’s Hour (6 August). |
| Aug 2003 |  | - 6th August 2003: Duncan talks about ‘Women and Rationality’ on BBC Radio 4’s Woman’s Hour. |
| Sep 2003 |  | - Smart interviewed on BBC’s World Service’s Language in Focus, on ‘the language of the family’. |
| Oct 2003 |  | - 17th October: CAVA Press Release: Shared Residence Not a ‘Magic Solution’. - 2nd media hit: ‘A Child is not a House’, Guardian, 17 October, by Phillips. - Followed up in The Independent (20 October) and Yorkshire Post (20 October). - Requests for information from the BBC’s The Politics Show; BBC and Channel 4 documentary makers; Children and Family Court Advisory and Support Service (CAFCASS); - Phillips interviewed on BBC Radio 4’s Woman’s Hour on ‘fathers campaigning for equal access’. - Smart subsequently invited to Ministerial Seminar on divorce, contact and residence, attended by Margaret Hodge, Harriet Harman, Baroness Hollis, Baroness Scotland, and Lord Filkin. - Contact made with Deborah Lincoln, Special Adviser to Patricia Hewitt, Secretary of State for Trade and Industry and Minister for Women and Equality. - Williams’ talk to Catalyst public meeting in Leeds. Established contact with trade unionists and Alan Simpson MP, Chairman of the All-Party Parliamentary Group for Social Science and Policy. - Launch of the new-look CAVA website. New features included: experts page, news and events section with press release series and a search facility. - Williams gives ‘Rethinking Care in Social Policy’ Keynote presentation to the Conference of the Finnish Social Policy Association, University of Joensuu, Finland, October 24th 2003 - Williams and Selma Sevenhuijsen joint paper at ‘Employment and Care’ seminar. Contacts made with Liz Kendall, Maternity Alliance, and Madeline Bunting, Guardian journalist. - Research assistant to work on Gulbenkian book appointed. - Williams interviewed in Leeds Review (circulated to 90,000 graduates from Leeds University). |
| Nov 2003 |  | - 2 Citizens’ Dialogues held in Leeds with Media Fellow. - Discussions with Media Fellow and Vanessa Bridge (Head of University Press Office) about next media ‘strike’. - Smart’s research featured in Sydney Morning Herald. - Williams’ submission to DfES ‘Every Child Matters’ Green Paper consultation process. - Williams invited to be a member of the Commission on the Future of Family and the Well-Being of Children, organised by the NFPI with the National Children’s Home (NCH) and supported by the Joseph Rowntree Foundation (JRF). - Duncan talks at the first annual Promoting Women’s Enterprise Support (Prowess) Conference in Brighton. - Smart addresses the National Council for One Parent Families Annual Conference in London. - 17th November: CAVA Press Release: Talking Home Truths in Leeds. |
| Dec 2003 |  | - 3rd media hit: ‘Friends are the new Family’, Guardian, 12 December, by Phillips, to coincide with ‘We’d rather be with Friends’, New Statesman, 15 December, by Roseneil. |
| Jan 2004 |  | - 1st January: Williams receives OBE in the New Years Honours. - 3rd January: Deacon in the Guardian reflecting on the originality of Michael Howard’s core principles. - 6th January: CAVA Press Release: CAVA Director Receives New Year Honour.. - 20th January: Enduring Families findings on shared residence is featured in the Aberdeen Press and Journal. |
| Feb 2004 |  | - 8th February: ESRC issue press release on CAVA’s sister-project, Enduring Families, directed by Neale - ‘Life after Divorce’. Research is reported on in The Times. - 20th February: ESRC Seminar Series: ‘Non-familial Relationships across the Lifecourse’. First seminar, ‘Unconventional Couples’, organised by CRFR and Roseneil, at University of Leeds. Presentation from Roseneil on CAVA research. - 26th February: Smart speaks at DAWN Project Annual Conference on children’s experiences of long-term shared residence in Sheffield. |
| Mar 2004 |  | - Roseneil’s article ‘Towards a More Friendly Society’ appears in The Edge, Issue 15. - Williams’s article ‘How mother juggle care and work’ appears in Family Today. - 3rd March: ‘Greenham Common Changed my Life’ on Timeshift BBC2, featuring Roseneil. - 20th March: Smart’s Australian seminars - as part of her visiting fellowships at La Trobe University and Melbourne University - are covered in 3 newspapers stories over the week::The Age (20/3/04), The Sydney Morning Herald (20/3/04), The Sydney Morning Herald (27/3/04) - 23rd March: Smart is interviewed for ABC Radio (Australia) about ‘Changing Commitments’. - 26th March: Neale features in Edinburgh Evening News. - 27th March: Roseneil and Duncan feature separately in a Guardian article on the gay geography of Britain. |
| Apr 2004 |  | - 1st April: Smart on ABC Radio’s ‘Life Matters’ programme (Australia) discussing children’s narratives of divorce. - 1-2 April 2004: Smart gives a keynote speech on ‘Changing Families: Parents, Children & Divorce’ at the Families Australia ‘Globalisation, Families and Work’ Conference, Brisbane. - 5th April: CAVA Press Release: CAVA Welcomes Family Policy Debate. - 23rd April: Smart gives a keynote speech on ‘Children Creating Narratives’ at the University of Sydney Law Faculty Family Law Seminar, Australia. |
| May 2004 |  | - Invitations sent out for Rethinking Families book launch. Interest from: Employment Market and Analysis Research team at DTI; Childline; over 50 MPs; |
| Jun 2004 |  | - 13th June: Williams’ keynote at the NFPI is reported on in the Guardian ahead of the ParentChild2004 conference. - 15th June: CAVA Press Release: Contact in Context – Post Divorce Family Lives. Enduring Families findings on shared residence is press released ahead of a Fathers4Justice demonstration. - 16th June: CAVA Press Release: Social Policy Must Adapt to New ‘Family Values’. - 16th June: Duncan’s research on working mothers features in London’s Evening Standard. The story is also covered by PA News and there are a number of subsequent media hits: Daily Mail (17/6/04), Guardian (17/6/04), The Newcastle Journal (17/6/04), Brighton Evening Argus (18/6/04), The Evening Chronicle (24/6/04), PA Features (24/6/04), Manchester Online (25/6/04), Bolton Evening News (26/6/04), Blackpool Gazette (26/6/04), Huddersfield Examiner (26/6/04), York Evening Press (26/6/04), Burton Daily Mail (29/6/04), Portsmouth News (29/6/04) - 17th June: Williams gives keynote at NFPI’s ParentChild2004 international conference: ‘Changing Values, Changing Families?’ - 18th June: Williams’ keynote is covered on the front page of the Daily Mail, a full page spread in the Times, and in the Guardian. also gives a radio interview to the Independent Radio Network. - 19th June: The Daily Mail runs an article on ‘The Gay Myth’, mentioning CAVA’s research. - 21st June: Coleman Getty PR issue press release on Rethinking Families ahead of the book launch later in the week. Patricia Hewitt MP - Secretary of State for Trade and Industry and Minister for Women - personally endorses the report. - 21st June: ESRC launch of ‘Seven Ages of Man and Woman’ at the beginning of Social Science Week. Report features research by Duncan which is also press released by the ESRC. Subsequent media hits from: Daily Mail (21/604), The Independent (21/6/04), Financial Times (21/6/04), Bradford Telegraph and Argus (26/6/04) - 22nd June: Smart gives keynote at CAFCASS conference on insights into long-term contact. - 23rd June: Book launch for ‘Rethinking Families’, RICS, Parliament Square. Speakers included Simpson MP, Kay Carberry (EOC) and Williams. - 23rd June: Williams and Duncan present at the All-Party Parliamentary Group for Social Science and Policy at the House of Commons. - 24th June: Williams’ keynote at the NFPI, and the Rethinking Families book, feature in Community Care magazine. - 26th June: Duncan’s ‘gay map’ is covered in the Bradford Telegraph and Argus. - 30th June: CAVA’s research programme features in Phillips’ piece in the Guardian. |
| Jul 2004 |  | - 1st July: Duncan’s research on working mothers continues to feature in the local press. A story in the Mansfield and Ashfield Recorder is followed by: Kettering Evening Telegraph (6/7/04) Northampton Chronicle and Echo (6/7/04), Southern Daily News (6/7/04), The Gloucestershire Echo (6/7/04), Oldham Evening Chronicle (13/7/04), Telford Journal (15/7/04), Nottingham Recorder (15/7/04), Aberdeen Press and Journal (16/7/04), Derby Express (23/7/04). - 4th July: Rethinking Families is covered in The Observer and The Observer’s Review. - 5th July: Double page-spread on Rethinking Families in University of Leeds’ Reporter. - 11th July: Smart’s research features in the Observer. - 16th July: Neale is interviewed in a two-page spread in the Yorkshire Post. about Enduring Families project on shared residence. - 21st July: Smart on Radio Four’s ‘You and Yours’ programme discussing marriage and weddings. - 23rd July: Duncan research features in the Derby Express. |
| Aug 2004 |  | - 3rd August: Newcastle-Under-Tyne Journal runs article on ‘Research into Working Mums Doesn’t Help’. - 18th August: Duncan’s research features in the House of Fraser’s seasonal newsletter. |
| Sep 2004 |  | - 3rd September: Rethinking Families features in Yorkshire Post article - ‘Society needs to find a different way of living, concludes research report’ - 10th September: Joseph Rowntree Foundation publish Neale and colleagues’ report on young children’s citizenship. - 16th September: Williams gives keynote ‘Rethinking Care’.at the Irish Social Policy Association’s Annual Conference - 20th September: Neale and Flowerdew’s book ‘Parent Problems Two’ is published by Young Voice. The book is featured in the Times, the London Evening Standard (21/9/04) and the Times Saturday Supplement (25/9/04). - 21st September: Roseneil’s CAVA research is featured in the Times. The Richard and Judy show on Channel 4 ask to go on the show to talk about her research but unfortunately the item does not go ahead. - 25th September: Williams features in the Guardian’s special report on The World in 2020. - 27th September: Williams on News Talk 106 radio show (Dublin) discussing ‘Rethinking Families’. - 27th September: Smart, Margaret Hodge MP and David Aaronovich speak at ‘Stuck in the Middle: Are we doing enough to help children when their parents split up?’ at the Labour Party Fringe Meeting hosted by NCH Action for Children. - 30th September: Williams’ ‘Rethinking Families’ book is highlighted in the ESRC’s publication Social Sciences. |
| Oct 2004 |  | - October 2005: Project findings on Enduring Families are featured in the Times, Evening Standard and Glasgow Herald. Invited presentations on the findings given at Making Contact Safe (family law) conference, London, CAFCASS Yorkshire and Humberside Regional Training Day and the Hear me Out conference, Cheshire County Council/ CAFCASS north west region. - 1st October: Smart gives invited paper on ‘Long term conflict in contact and residence cases’ to the NE Judicial Training Seminar at York County Court. - 4th October: Smart and Theresa May MP speak at ‘Stuck in the Middle: Are we doing enough to help children when their parents split up?’ at the Conservative Party Fringe Meeting hosted by NCH Action for Children. - 7TH October: Rethinking Families is favourably reviewed in Community Care magazine. - 13th October: Enduring Families research is featured in Phillips’ Guardian article on fathers’ rights. - 13th October: Smart presents paper on ‘Dealing with Long-Term Conflict: the perspective of children’ to the Aire Valley Contact Centres Annual General Meeting, Keighley. - 13th October: Phillips’s article ‘Most Fathers Get Justice’ appears in The Guardian. - 15th October: CAVA’s special themed section of Social Policy and Society is published, edited by Deacon and Williams. Contributions from: Smart, Mason, Roseneil, Duncan and Irwin, Williams, Deacon, Phillips and Groves. - 27th October: Williams presents 'Concept' public lecture to social workers, trainers, educators and community workers at the University of Edinburgh. |
| Nov 2004 |  | - 3rd November: Roseneil presents CAVA work on `Beyond the Conventional Family: new ways of thinking about personal relationships’at Intel Research Seminar, Portland, Oregon, US. - 10th November 2004: Smart gives paper on ‘Why can’t they agree’ to the Lancashire Family Mediation AGM at the University of Central Lancashire, Preston. - 10th November 2004: Williams gives a plenary paper on ‘Work, Family and Care and the Future of Social Policy in Europe’ to the Conference of STAKES Work and Family Project, Helsinki. - 18th November: Duncan’s research features in an article piece in The Economist on ‘Urban Family Values’. - 25th November: Smart on Radio 4’s Woman’s Hour discussing cohabitation and marriage in later life. |
| Dec 2004 |  | - 3rd - 4th December: CAVA International Symposium ‘Rethinking Care Relations, Family Lives and Public Policies’ at Weetwood Conference Centre, Leeds. Presentations from Williams, Sarah Irwin, Duncan, Smart and Roseneil. - 10th December: ESRC Seminar Series: 'Changing Social Norms, Changing Family Law? Rights and Responsibilities for Partners, Friends and Carers’. First seminar, ‘Individualisation, Families and Legal Regulation’, organised by Duncan, at Nuffield Foundation, London. Presentations from Williams and Smart. - 12th December: Roseneil featured in a piece in the Boston Globe - ‘Violence toward gays and lesbians escalates in the UK’. - 20th December: ESRC issues two press releases on CAVA’s sister-project ‘Enduring Families’, directed by Neale. Research is reported on in the Daily Mail, the Western Mail, Scunthorpe Evening News and Daily Mirror. |
| Jan 2005 |  | - 7th January: Smart presents at the first international conference of the WELLCHI network - ‘Challenges and Opportunities faced by European Welfare States: The Changing Context for Child Welfare’ - at the University of Oxford. - 24th January: Williams gives a public lecture on ‘Changes in families and personal relationships: the implications for a political ethic of care’ to University College Cork, Ireland. - 27th January: Williams gives a staff seminar on ‘The Practical and Political Ethics of Care and the Implications for Child Welfare’ to social work staff at Huddersfield University. - 31st January: Rethinking Families sales are recorded at 640 copies. |
| Feb 2005 |  | - 25th February 2005: ESRC Seminar Series: 'Changing Social Norms, Changing Family Law? Rights and Responsibilities for Partners, Friends and Carers’. Second seminar ‘The New Family – Unmarried Cohabitation, Temporary Marriage and Legal Rights’ organised by Duncan at The Nuffield Foundation, London. Duncan gives the paper ‘Why don’t they marry? Cohabitation and commitment’.. |
| Mar 2005 |  | - 3rd March 2005: Mason organises the first seminar at the Leeds Social Sciences Institute: ‘What can qualitative and quantitative methods offer each other?’. - 18th March 2005: Williams gives a keynote lecture on ‘Making sense of changing family lives and personal relationships’ to the ESRC LARCI Seminar ‘Delivering Services for Children and Young People: Evidence from Research and Best Practice’. - 18th March 2005: Smart presents on ‘Unmanageable Conflict: Parents, Children and Separation’ to the Judicial Studies Board at the Annual Seminar for District Judges. - 30th March 2005: Smart presents on ‘Same-Sex Partnership: What’s love got to do with it?’ and Duncan presents the paper ‘Why don’t they marry? Cohabitation and commitment’ at the Socio-Legal Studies Annual Conference at the University of Liverpool in a special stream organised by the Department for Constitutional Affairs. |
| Apr 2005 onward |  | - May and June 2005: Williams features in a Times and Sunday TImes articles, Italian newswire ANSA Notiziario Generale, and on Radios Ireland, Scotland and Berkshire, on Radio 4’s Woman’s Hour, talking about LATs. - Duncan and Williams are consulted for making of BBC documentary on ‘Love Maps of Britain’ |

2.2.	Difficulties and unexpected outcomes

Lessons learned:

- Media dissemination of qualitative research works well riding on the back of topical issues.

- Need to build up trust between researchers and key journalists – works best if there are shared personal/political/intellectual identities. This prevents distorted messages going out.

- Our dissemination work helped integrate our research findings from different projects by thinking through overall messages; it helped Group morale and identity, as well as clarity of thinking.

- Our media fellow was an excellent contact for policy-makers.

- If different PR companies are involved in events, negotiation is needed beforehand as to who takes priority.

- Need to balance ‘high profile’ national broadsheet coverage with work with grass roots NGOs.

- Journalists, politicians, trade unionists and policy makers are interested in ideas – invite them to academic events. Good to break down the distinction between academic and non-academic at times.

- Ensure media fellow meets with university press office and each knows what the other is doing.

- Both academic and non-academic dissemination take time and resources. Need to ensure energies go into a few well-planned collective events and balance that with high profile members doing keynotes, alongside normal conference work.

- Need to manage conflict between academic pressure to publish in academic journals and dissemination and work with users for which there is little formal recognition.

- Conflict between academic insistence on correct attribution of work done and a newspaper editor’s pen needs to be handled carefully and explained to all involved beforehand.

3. 	Specific Impact on Policy and Practice

As detailed above, and in Annex B, we have engaged with the policy and practitioner world over the life course of the Group in various ways – information seminars for practitioners, seminars to government departments, to Party Conferences, to trade unionists, involvement in local and national NGOs, and policy advice committees, keynotes to practitioner/policy conferences; consultation to professional  organizations. We have, in all of this, managed to get across some key messages with authority:

- That, in spite of the diversity of family lives, there has been no loss in commitment; people are devising new ways of maintaining their commitments and retaining the values that are important to them

- That there is no standard family, that non-familial relationships matter and that policy and law need to respect and protect these diversities.

- That the ‘care’ side of work/life balance is a central issue in people’s lives and just as if not more important than the ‘work’ side.

- That we need new political vision for thinking about care and social justice in a holistic way – a ‘political ethic of care’ which gives value to the giving and receiving of care.

- That family law and policy has to take children’s perspectives into account and listen to what they have to say especially with respect to residence after divorce.

Examples of impact:

- Patricia Hewitt, Secretary of State for Trade and Industry and Minister for Women provided the following endorsement for Rethinking Families:

"I welcome this report, and in particular the research results which underline the deep commitment that people demonstrate towards their friends and loved ones, irrespective of the form their family takes. Government policy should always work with the grain of people's lives. That's why we have put in place a range of policies which help to provide a climate that supports people in different kinds of families in carrying out their caring commitments while, at the same time, working to support themselves. I particularly welcome the proposal for promoting and valuing an 'ethic of care' alongside an ethic of work."

The book was launched with Kay Carberry, Assistant General Secretary of the TUC; Alan Simpson MP, Chair of the All-Party Parliamentary Group for Social Science as speakers.  A review in Community Care Magazine called it ‘a little gem’.

- Significant impact on divorce policy debates in the UK and Australia: Smart was cited in evidence given to the Senate Inquiry into Child Custody in Australia and her work with Neale and Wade is regarded as having influenced policy in both Australia and the UK away from an automatic presumption of shared residence for children on divorce.  Research by Smart and V. May has also been cited in Hansard and is currently informing the policy debates on how to reform family law in relation to conflict over children.

- Duncan’s work on cohabitation in a co-funded project led to the initiation of a Department of Constitutional Affairs information campaign about common law marriage, and policy debate concerning the legal recognition of heterosexual cohabiting couples.

- In a speech to 60 representatives of Leeds Diocese, Rt. Hon. John Battle on 13th June 2004 said the findings in Rethinking Families were part of a ‘vision for a changing society and the world’ (www.catholic-ew.org.uk/listneing 2004).

- Williams was interviewed by Christina Hardyment as a ‘significant opinion-former’ for a commissioned think piece for the Joseph Rowntree Foundation on the ‘Social Construction of Parenting’ in August 2004, and was a member of the Commission on Families and the Wellbeing of Children established by the National Family and Parenting Institute, Joseph Rowntree Foundation and NCH and reporting in November 2005.

- Roseneil’s talk `Beyond the Conventional Family: new ways of thinking about personal relationships’, to Intel, in Portland, Oregon in October 2004 was described by Intel as ‘a real wake-up call for us as a company since our product and market strategies are based on faulty understandings of family, home and relationships.’

- Presentations by Smart and Williams have been videoed for training purposes for judges and social workers. Neale’s work on children’s citizenship has fed directly into professional practice through collaboration with CAFCASS, the development of practice guidelines for CAFCASS staff, a commissioned book for Joseph Rowntree Foundation, and work with children’s charity Young Voice to produce writings tailored to different audiences. Neale is consultant to a DfES project secured by Young Voice to develop, in collaboration with young people, a multi media training package for parents and professionals involved in divorce, drawing on  ‘Enduring Families’ research and to be rolled out nationally through a series of training events.

- In March 2005 37 local and national professional/policy/advice organisations mentioned our work on their websites.

- In January 2004 CAVA Director was awarded an O.B.E. for services to social policy.

4. 	Management

- Critical Mass: The benefits of Group funding were that it provided critical mass, broader intellectual context and aims, a wider pool of complementary specialist knowledge, an enhanced division of labour, and a range of skills and knowledge to draw on. This also facilitated the development of a ‘brand’ and research whose sum is greater than its parts. Most of the team was based at Leeds University; we came from 3 departments and were ‘bought out’ for parts of our teaching. This was important in allowing us to focus on research. We enhanced the critical mass by devolving 10% of our overheads to the Centre for Research on Family Kinships and Childhood and Centre for Interdisciplinary Gender Studies who organized workshops, seminars and conferences along themes in our research and developed some of the co-funded activities.

- Matrix management: The organization of the research and the management of the Group as a matrix (see diagrams in 1.2 above) attempted to facilitate this critical mass. The research strand leaders made up the Management Team who met about 8 times a year and the Group as a whole met about 6 times a year while the projects teams met much more frequently. We used the first 9 months in year 1 for a series of intensive workshops where members presented intellectual position-papers and reviews, and this served as a crucible for cross-fertilization of disciplines. This was followed by the empirical work in years 2 and 3, and in Years 4 and 5 we focused on analysis and dissemination.

- Individual vs. Collective: This chronology of the programme attempted to deal with one of the difficulties of academic team-building - the tension between expectations of autonomy and individual achievement and the commitment to collective endeavour.  It created possibilities for group cohesion at the beginning and brought the Group back together with external recognition in the last two years. However, in retrospect, this process did not work so well for those research fellows who we recruited at the end of Year 1 and whose contracts finished, in the main, around the end of year 3 because most were not part of the intellectual discussion in year 1 or the stimulating aspects of dissemination in years 4 and 5.  We also found that there were differences between those who had worked closely with us beforehand and identified with the intellectual thrust of the programme and those who were recruited later, in that the latter found the overall programme less intellectually compelling. On the other hand, for those who became attached to us through stand-alone co-funded projects this was less of an issue: they have expressed benefits of being associated with CAVA and having access to expertise. We have reflected since that there is a difficult balance to be made between linking the different parts to meet overall objectives, on the one hand, and leaving those parts to develop in their own time and manner, on the other. We have also reflected that a mix of researchers – pre-and postdoctoral – would be better from the outset. (All but one of our research fellows found secure and upgraded job destinations).

- Administrative support: our funding allowed for a full time and part time secretary and the University paid for a half time lecturer to develop Knowledge Transfer with the Group. However, this was difficult to do in the first two years of the projects and the post holder left in 2002. Eventually we used this allocation towards the funding of a Communications Coordinator post to work with the Media Fellow, and this was a good strategic decision. However, given that we did not have sufficient administrative support (as well as changes in secretarial staff over the first 2 years due to illness), we should, in retrospect, have had a full time project manager from the beginning. Not having this created a drain on the Management Team’s, and especially the Director’s, resources in the first three years.

- Time: as mentioned in the section on dissemination, we have reflected that we needed more time for analysis of the data, especially to devise new methods for reading across data from different qualitative projects. (We fed this into the ESRC’s review of qualitative research). We were allowed a no-cost extension until March 2005, and the methodology for this more sophisticated analysis is the subject of new awards (see 1.8.1). One important way of dealing with time and priority issues was by the University allowing us to have access to 20% of the overheads which meant we had leeway to employ temporary staff when we needed to.

- Advisory Group: we were fortunate in having a very supportive Advisory Group. However, all of them were very busy people who were mainly London-based and a meeting for them meant a whole day away from their own work. The role of such Groups, especially for researchers based outside London, needs some rethinking with possibly a local group for twice yearly meetings and a virtual Group which could include international advisors who would attend preset meetings in London at the beginning and end of the programme.

- Guinea pig effect:  we were one of the ESRC’s first two Research Groups (as opposed to Research Centres) and in a number of respects have had to define for ourselves what might differentiate us from a Research Centre, apart from being time limited to 5 years and having less funding. For the first two and a half years we had either a temporary or no ESRC case officer attached to us and also, after year 1, no representative on the then Research Priorities Board. This meant we often had to deal with difficulties on our own and were out of the loop when it came to opportunities for additional funding. Added to this, the goalposts of ESRC evaluation through Annual Reports often changed and for three years we had no more than a two-line response to our Reports. Furthermore, a formal procedure to allow Research Groups to re-apply for up to 5 years’ re-funding was put into action at a time when it was too late for us to apply. In some respects benign neglect allowed us to flourish in our own way, and, when communication procedures improved and we got into the loop, we gained some important additional resources such as the additional funding for four pump-priming projects, a Media Fellow, contribution to the Communication Coordinator post and funding for a National Survey, which were all vital to our success.

References not included in Annexes

Bauman, Z. (2003) ‘Liquid Love: on the Frailty of Human Bonds’.Cambridge: Polity Press,

Deacon, A.  and Mann, K. (1999) ‘Agency, modernity and social policy’, Journal of Social Policy, 28 (3): 413-435

Duncan, S. and Edwards, R. (1999) Lone Mothers, Paid Work and Gendered Moral Rationalities. Basingstoke: Macmillan.

Finch, J. and Mason, J (1993) Negotiating Family Responsibilities London: Routledge.

Smart, C and Neale, B (1998) Family Fragments? Cambridge: Polity.

Giddens, A. (1992) The Transformation of Intimacy: Sexuality, Love and Eroticism in Modern Societies. Cambridge:Polity.

Beck, U. and. Beck-Gernsheim, E (2002) Individualization: Institutionalized Individualism and its Social and Political Consequences. London: Sage.

Tronto, J.C. (1993) Moral Boundaries: A Political Argument for an Ethic of Care. New York:Routledge.

Sevenhuijsen, S. (1998) Citizenship and the Ethic of Care: Feminist Considerations on Justice, Morality and Politics. London: Routledge.

Annex A - Outputs

Nominated Publications

Williams, F. (2004a) Rethinking Families. London: Calouste Gulbenkian Foundation. ISBN 1 903080 02 9. 96pp.

Smart, C. and Shipman, R. (2004) ‘Visions in Monochrome: Families, Marriage and the Individualization Thesis’. British Journal of Sociology. 55(4), pp 491-509.

http://www.blackwell-synergy.com/toc/bjos/55/4

Deacon, A. and Williams F. (eds.) (2004) Care, Values and the Future of Welfare. Themed Section Social Policy and Society, 4(3). Cambridge: Cambridge University Press, October 2004, pp. 385-463.

http://journals.cambridge.org/bin/bladerunner?REQUNIQ=1121183660&REQSESS=1657901&117000REQEVENT=&REQINT1=250988&REQAUTH=0

Duncan, S. and Smith, D. (2002b) ‘Geographies of Family Formations: Spatial Differences and Gender Cultures in Britain’. Transactions of the Institute of British Geographers. 27(4), pp 471-493.

http://www.ingentaconnect.com/content/bpl/tran/2002/00000027/00000004;jsessionid=7og9pmq1kglhk.victoria

Williams, F. and Roseneil, S. (eds.) (2004a) ‘New Contexts for Collective Action: The Politics of Parenting, Partnering and Participation’. Special Issue of Social Politics: International Studies in Gender, State and Society,11(2). Oxford: Oxford University Press.

http://sp.oxfordjournals.org/content/vol11/issue2/index.dtl

We would like to recommend in addition the following Special Issue, which has defined a new field and is already influencing agendas:

Roseneil, S. and Budgeon, S. (eds.) (2004) ‘Beyond the Conventional Family: Intimacy, Care and Community in the 21st Century’. Special Issue of Current Sociology , 52(2). London: Sage. 180pp.

(http://csi.sagepub.com/content/vol52/issue2/).

1. Single Published Item

Ackers, H. L. (2001) The Participation of Women Researchers in the TMR Programme of the European Commission: An Evaluation. European Commission (DG12). Reprinted in 2003.

Ackers, H. L. (ed.) (2005a) ‘Special Issue: Scientific Migration within the European Union’, Innovation: The European Journal of Social Science Research, 18(3).

Ackers, H. L. and Dwyer, P. (2002) Senior Citizenship? Retirement, Migration and Welfare in the European Union. Policy Press: Bristol. ISBN 1 861 342640 (pb).

Ackers, H. L. and Stalford, H. E. (2004) A Community for Children? Children, Citizenship and Internal Migration in the EU. London: Ashgate.

Deacon, A. (2002a) Perspectives on Welfare: Ideas, Ideologies and Policy Debates. Buckingham: Open University Press.ISBN 0 335 20320 (pb), 0 335 20321 (hb).

Deacon, A. (ed.) (2002b) Debating Pensions: Self-interest, Citizenship and the Common Good. London: Civitas, the Institute for the Study of Civil Society. ISBN 1 903 38621.

Deacon, A. and Williams F. (eds.) (2004) Care, Values and the Future of Welfare. Themed Section Social Policy and Society, 4(3). Cambridge: Cambridge University Press, October 2004, pp. 385-463.

Available at: http://journals.cambridge.org/bin/bladerunner?REQUNIQ=1121183660&REQSESS=1657901&117000REQEVENT=&REQINT1=250988&REQAUTH=0

Duncan, S. and Pfau-Effinger, B. (eds.) (2001) Gender, Economy and Culture in the EU. London: Routledge. ISBN 0 415 23911 7.

Duncan, S., Carling, A. and Edwards, R. (eds.) (2002) Analysing Families: Morality and Rationality in Policy and Practice. Routledge: London. ISBN 0 415 250404 (pb), 0 415 250390 (hb).

Duncan, S., Barlow, A., James, G. and Park, A. (2005) Cohabitation, Marriage and the Law: Social Change and Legal Reform in 21st Century Britain. Oxford: Hart.

Duncan, S. and Williams, F. (eds.) (2002a) ‘New Divisions for Labour: Alternatives for Caring and Working’.  Special Issue of Critical Social Policy, 22(1). London: Sage.

Finch, J. and Mason, J. (2000a) Passing on Kinship and Inheritance in England. London: Routledge. ISBN 1 857 28276 0 (hb), 1 857 28277 9 (pb).

Gavanas, A. (2004a) Fatherhood Politics in the United States: Masculinity, Sexuality, Race and Marriage. Illinois: University of Illinois Press.

Hollway, W (ed.) (2004a) ‘Psychosocial Research’. Special issue of International Journal of Critical Psychology, 10, 2004. London: Lawrence & Wishart. ISBN 0 85315 995 5.

Hollway, W. and Jefferson, T. (2000a) Doing Qualitative Research Differently: Free Association, Narrative and the Interview Method. London: Sage.

Mason, J. (2002a) Qualitative Researching (Second edition). London: Sage. ISBN 0 761 97428 (pb), 0 761 97427 (hb).

Neale, B. (2004) (ed.) Young Children’s Citizenship: Ideas into Practice. Editor and contributor, with C. Willow, R. Marchant and P.Kirby. York: Joseph Rowntree Foundation. ISBN 1 85935 223 5 (pb), 1 85935 224 3 (pdf www.jrf.org.uk).

Neale, B. and Flowerdew, J. (2004) Parent Problems 2!  Looking Back at our Parents’ Divorce. East Molesey, Surrey: Young Voice.

Neale, B. and Smart, C. (2001) Good to Talk? Conversations with Children after Divorce. East Molesey, Surrey: Young Voice. 35pp. ISBN: 1 903456 02 9.

Neale, B. and Wade, A.  (2000) Parent Problems!  Children’s Views on Life when Parents Split Up. East Molesey, Surrey: Young Voice. ISBN: 1 903456 00 2.

Neale, B., Willow, C., Marchant, R. and Kirby, P. (2004) (eds.) Young Children’s Citizenship: Ideas into Practice. York: Joseph Rowntree Foundation. ISBN 1 85935 223 5 (pb) / 1 85935 224 3 (pdf www.jrf.org.uk).

Roseneil, S. (2000a) Common Women, Uncommon Practices: The Queer Feminisms of Greenham. London: Cassell Academic Press.

Roseneil, S. (2001a) ‘Rethinking Citizenship: Gender and Sexuality’. Special Issue of Citizenship Studies, 5(3), 101pp..

Roseneil, S. and Budgeon, S. (eds.) (2004) ‘Beyond the Conventional Family: Intimacy, Care and Community in the 21st Century’. Special Issue of Current Sociology , 52(2). London: Sage. 180pp. Available at: http://csi.sagepub.com/content/vol52/issue2/

Roseneil, S., Hamel, P., Lustiger-Thaler, H. and Nederveen Pieterse, J. (eds.) (2001a) Globalisation and Social Movements. Basingstoke: Palgrave. 258pp.

Roseneil, S. and Hogan, L. (eds.) (2001a) ‘Gendering Ethics, The Ethics of Gender’. Special Issue of Feminist Theory, 2(2). London: Sage. 109pp.

Roseneil, S. and Hogan, L. (eds.) (2003a) ‘Ethical Relationality: Agency, Autonomy, Care’, Special Issue of Feminist Theory, 4(2). London: Sage. 115pp.

Smart, C. (ed.) (2003a) ‘New Perspectives on Childhood and Divorce’. Special issue of Childhood: A global journal of child research, 10(2). London: Sage.

Smart, C. and May, V. (2005) Residence and Contact Disputes in Court, Volume 2. London: Department for Constitutional Affairs, Research Series.

Smart, C. and Stevens, P. (2000) ‘Cohabitation Breakdown’. Final Report to the Joseph Rowntree Foundation. London: The Family Policy Studies Centre. 53pp.

Smart, C., Neale, B. and Wade, A. (2001) The Changing Experience of Childhood: Families and Divorce. Cambridge: Polity Press. ISBN 0 7456 2400 6

Smart, C., May, V., Wade, A. and Furniss, C. (2003) Residence and Contact Disputes in Court, Volume 1. London: Department for Constitutional Affairs, Research Series No 6/03, 138pp.

Wade, A. and Smart, C. (2002) Facing Family Change: Children’s Circumstances, Strategies and Resources. York: York Publishing Services for the Joseph Rowntree Foundation. pp.50. ISBN 1 842 630776.

Williams, F. (2004a) Rethinking Families. London: Calouste Gulbenkian Foundation. ISBN 1 903080 02 9.

Williams, F. and Roseneil, S. (eds.) (2004a) ‘New Contexts for Collective Action: The Politics of Parenting, Partnering and Participation’. Special Issue of Social Politics: International Studies in Gender, State and Society,11(2). Oxford: Oxford University Press.

Available at:http://sp.oxfordjournals.org/content/vol11/issue2/index.dtl

Williams, F., Popay, J. and Oakley, A. (eds.) (1999) Welfare Research: A Critical Review. London: UCL Press. ISBN 1-85728-270-1

In Press 2005 and forthcoming

Ackers, H. L. (2005b) Gender, Mobility and Career Progression in the European Union: Final Report. Brussels: European Commission.

Ackers, H.L. (ed.) (2006) Gender, Mobility and Career Progression in the European Union: A Case Study of Science Careers. Camberley: Edward Elgar.

Hollway, W. (2006) Intersubjectivity and the Capacity to Care. London: Routledge.

Irwin, S. (2005) Reshaping Social Life. London: Routledge.

Neale, B and Flowerdew, J (2006) Moving On: The Changing Lives of Young People after Parental Divorce London: Routledge.

Roseneil S. (2007a) Sociability, Sexuality, Self-Relationality and Individualization. Cambridge: Polity Press.

Roseneil, S. (2007b) Gender. 4 volume set. London: Routledge.

Williams, F. with co-authors Lister, R., Antonnen A.,. Bussebaker, M, Gerhard, U., Johansson, S., Heinen , J. Leira, A. Siim, B., and Tobio, C (2006) Gendering citizenship in Western Europe: new challenges for citizenship research in a cross-national context. Bristol: Policy Press

2. Book Chapters

Deacon, A. (2001) 'Introduction: the realities of welfare reform', in J. Besharov (ed.) Ending Dependency: Lessons from Welfare Reform in the USA'. London: Civitas.

Deacon, A. (2002c) ‘Paternalism, Welfare Reform and Poor Families in the United States’, in A. Carling, S. Duncan and R. Edwards (eds.) Analysing Families: Morality and Rationality in Policy and Practice. Routledge: London. pp. 101-108. ISBN 0 415 250404 (pb), 0 415 250390 (hb).

Deacon, A. (2002d) ‘Moral Arguments for Welfare Reform’, in B. Carlson, A. Deacon, H. Hoogervorst, W. Prewo and J. Turner (eds.) Europe's Welfare Burden. London: Civitas, the Institute for the Study of Civil Society. pp. 11-23. ISBN 1 903 386217.

Deacon, A. (2002e) ‘Squaring the Circle on Pensions’, in A. Deacon (ed.) Debating Pensions: Self-interest, Citizenship and the Common Good. London: Civitas, the Institute for the Study of Civil Society. ISBN 1 903 386241.

Deacon, A. (2003a) ‘The British perspective on reform: Transfers from, and a lesson for, the U.S.’, in R. Walker and M. Wiseman (eds.) The Welfare We Want? The British Challenge for American Reform. Bristol: The Policy Press. pp. 65-80.

Deacon, A. (2003b)  ‘Social security policy’, in N. Ellison and C. Pierson (eds.) Developments in British Social Policy 2. Basingstoke: Palgrave Macmillan. pp. 129-142.

Deacon, A. (2003c) 'Employment measures’, in P. Alcock, A. Erskine and M. May (eds.) The Social Policy Companion Second Edition. Oxford: Blackwell. pp. 342-347.

Deacon, A. (2004a) ‘Transmitted deprivation’, in S. Becker and A. Bryman (eds.) Understanding Research Methods for Social Policy. Bristol: The Policy Press.

Deacon, A (2004b) 'Can Conditionality be Justified?’, in P. Collins and A. Rossiter (eds.) On Condition. London: Social Market Foundation. pp. 36-56. ISBN 1-904899-01-3

Duncan, S., (2000) 'The Rationality Mistake: New Labour's Communitarianism and Supporting Families’, in P. Taylor-Gooby (ed.) Risk, Trust & Welfare. London: Macmillan. ISBN 0-333-76490-0(76493-5).

Duncan, S. (2005a) ‘Mothers’ work-life balance: individualised preferences or cultural construction?’, in D. Perrons et al (eds.) Gender divisions and working time in the new economy: public policy and changing patterns of work in Europe and North America. Cheltenham: Edward Elgar.

Duncan, S. and Barlow, A. (2002) ‘The Rationality Mistake and Family Policy in Britain’, in A. Carling, S. Duncan, and R. Edwards (eds.) Analysing Families: Morality and Rationality in Policy and Practice. London: Routledge. ISBN 0 415 250404 (pb), 0 415 250390 (hb).

Duncan, S. and Edwards, R. (2003) ‘State welfare regimes, mothers’ agencies and gendered moral rationalities’, in K. Kollind and A. Peterson (eds.) Thoughts on Family, Gender, Generation and Class. A Festschrift to Ulla Björnberg. Göteborgs Universitet.

Duncan, S. and Smith, D. (2004) ‘And then the lover: can we all now choose individual fulfilment’, in I. Stewart and R Vaitilingam (eds.) Seven Ages of Man and  Woman. Swindon: ESRC. pp 16-19.

Finch, J. and Mason, J. (2000b) 'Filial Obligations and Kin Support for Elderly People', in J.F. Gubrium and J.A. Holstein (eds.) Ageing and Everyday Life. Oxford: Blackwell. pp 193-213.

Finch, J. and Mason, J. (2000c). 'Family Relationships and Responsibilities', in N. Abercrombie and A. Warde, The Contemporary British Social Reader'. Cambridge: Polity Press. pp 170-177.

Hollway, W. (2000) ‘Practising critical psychology within a British psychology department’, in T. Sloan (ed.) Critical Psychology: Voices for Change. New York: Palgrave Macmillan

Hollway, W. (2001a)  ‘Gender difference and the production of subjectivity’ edited as reading 20 in M.Wetherell, S.Yates and S.Taylor (eds.) Discourse Theory and Practice: a Reader. London: Sage.

Hollway, W. (2004b) ‘What is Human Nature?’, in S.Hinchcliffe and K.Woodward (eds.) The Natural and the Social: DD100 Course Book 2, 2nd edition. London: Routledge and the Open University. pp 7-40. ISBN 0-415-32970-1.

Hollway, W. (2004c) ‘Psychoanalytic Methods’, in Encyclopaedia of Social Science Methods. London: Sage.

Hollway, W. and Jefferson, T. (2000b) ‘Anxiety, biography and the experience of locality’, in P. Chamberlayne, J.Bornat and Wengraf, T. (eds.) The Turn to Biographical Methods in Social Science. London: Routledge. pp 167-80.

Hollway, W. and Jefferson, T. (2000c) ‘Narrative, discourse and the unconscious: a case study of Tommy’, in M. Andrews, S.Day Sclater, C.Squires, and A.Treacher (eds.) Lines of Narrative. London: Routledge. pp 136-49.

Hollway, W. and Jefferson, T. (2000d) ‘The role of anxiety in fear of crime’, in R.Sparks and T.Hope (eds.) High Anxiety? London: Routledge. pp 31-49.

Hollway, W. and Jefferson, T. (2003) ‘The risk society in an age of anxiety: Situating fear of crime’ Reprinted in E.McLaughlin, J.Muncie and G.Hughes (eds.) Criminological Perspectives: Essential Readings. 2nd ed’n. London: Sage. pp 511-518.

Hollway, W. and T.Jefferson (2004) ‘The Free Association Narrative Interview Method’, in Encyclopaedia of Social Science Methods. London: Sage.

Hollway, W., Cooper, T., Johnston, A. and Stevens, R. (2002) ‘The Psychology of Sex and Gender’, in T.Cooper and I.Roth (eds.) Challenging Psychological Issues: DSE212 course Book 2. Milton Keynes: The Open University. pp 113-168. ISBN 0 7492 5355 X.

Irwin, S. (2001a) 'Repositioning disability and the life course: a social claiming perspective',  in  M. Priestley (ed.) Disability and the Life Course: global perspectives. Cambridge: Cambridge University Press. pp.15-25.

Irwin, S. (2001b) ‘Changing families’, in N. Abercrombie and A. Ward. (eds.) The Contemporary British Society Reader. Cambridge: Polity Press. pp.137-146.

Mason, J. (2002b) ‘Qualitative Interviewing: Asking, Listening and Interpreting’, in T. May (ed.) Qualitative Research in Action. London: Sage. pp. 225-241. ISBN 0 761 96068 6 (pb), 0 761 96067 8 (hb).

Neale, B. and Smart, C. (2002) ‘Caring, Earning and Changing? Parenthood and Employment after Divorce’, in A. Carling, S. Duncan and R. Edwards (eds.) Analysing Families: Morality and Rationality in Policy and Practice. London: Routledge. pp.183-198.

Roseneil, S. (2000b) `Life Documents’, in M.Kirby et al Sociology in Perspective. Oxford: Heinemann (second edition).

Roseneil, S. (2000c) `Local and Global Political Protest’, in N. Abercrombie and A. Warde (eds.) The Contemporary British Society Reader. Cambridge: Polity Press. pp.45-52.

Roseneil, S. (2000d) `Postmodern Feminist Politics’, in M. Evans (ed.) Feminism: Critical Concepts. London: Routledge.

Roseneil, S. (2001b) `The Global, the Local and the Personal: the dynamics of a social movement in postmodernity’, in P. Hamel, H. Lustiger-Thaler, J. Nederveen Pieterse and S.Roseneil (eds.) Globalisation and Social Movements. Basingstoke: Palgrave. pp. 89-110.

Roseneil, S. (2001c) `A Moment of Moral Remaking: The Death of Diana, Princess of Wales’, in F. Webster (ed.), Culture and Politics in the Information Age: A New Politics? London: Routledge. pp.96-114.

Roseneil, S. (2002) `The Heterosexual/Homosexual Binary: Past, Present and Future’, in D. Richardson and S. Seidman (eds.) The Lesbian and Gay Studies Handbook. London: Sage. pp. 27-44.

# Roseneil, S. (2004a) `Time and Tide: Memories and Metaphors – Moments and Movement’, in B. Halsaa, H. Rømer Christensen, A. Saarinen (eds.) Crossing Borders: The Re- mapping of Women’s Movements at the Turn of the 21st Century. University Press of Southern Denmark. pp. 346-353.

Roseneil, S. (2005a) `Living and Loving beyond the Boundaries of the Heteronorm: personal relationships in the  21 st Century’, in  L. Mackie, S. Cunningham-Burley and J. McKendrick (eds.) Families in Society: Boundaries and Relationships. Bristol: The Policy Press.

Roseneil, S. and Mann, K. (2001) `Poor Choices? Gender, Agency and the Underclass Debate’, in Family Life and Social Policy, Open University course D311, Open University Press.

Roseneil, S., Hamel, P., Lustiger-Thaler, H. and Nederveen Pieterse, J. (2001a) `The Shifting Global Frames of Collective Action’, in P. Hamel, H. Lustiger-Thaler, J. Nederveen Pieterse and S.Roseneil (eds.) Globalisation and Social Movements. Basingstoke: Palgrave. pp.1-20.

Smart, C (2000a) ‘New Dimensions to Gendered Power Relations in Families’, in J. Cook, J. Roberts and G. Waylen (eds) Towards a Gendered Political Economy. London: Macmillan. pp 188-204

Smart, C. (2000b) ‘Divorce in England 1950-2000: A Moral Tale?’, in S. Katz, J Eekelaar and M. Maclean (eds) Cross Currents: Family Law and Policy in the US and England. Oxford: Oxford University Press.

Smart, C. (2000c) ‘The Children Act 1989: The English Experience’, in 9th Australian National Family Law Conference Handbook. Melbourne: Television Education Network. pp. 199-212

Smart, C. (2003b) ‘Children and the Tansformation of Family Law’, in J. Dewar and S. Parker (eds.) Family Law: Processes, Practices, Pressures. Oxford: Hart Publishing. Chapter 10: pp 223-240.

Smart, C. Wade, A. and Neale, B. (2001) ‘Object van bezorgheid? Kinderen en echtscheiding’ (2001) in C. van Nijnatten and S. Sevenhuijsen (eds.) Dubbelleven: Nieuwe perspectieven voor kinderen no echtscsheiding. Amsterdam: Thela Thesis. pp 11-30.  (Dutch translation of journal article, ‘Objects of Concern’).

Wade, A. and Smart, C. (2003) ‘As fair as it can be? Childhood after divorce’, in A. Jensen and L. McKee (eds.) Children and the Changing Family: Between Transformation and Negotiation. London: Falmer Routledge. pp 105-119.

Williams, F. (2000) ‘Rethinking Social Policy Principles’, in G.Lewis, S. Gewirtz and J. Clarke (eds.) Rethinking Social Policy. Routledge: London.

Williams, F. (2001a) ‘Race, Ethnicity, Gender and Class in Welfare States: A Framework for Comparative Analysis’, in J. Fink, G. Lewis and J. Clarke (eds.) Rethinking European Welfare. London: Routledge.

Williams, F. (2001b) ‘Posisjonering av velferdsbrukeren innen forskning: fra passiv mottaker til velfersaktor’, in M. Sanboek Fra mottaker til aktǿr. Gyldendal Akademisk: Bergen. pp. 72-90

Williams, F. (2003a) ‘Contesting ‘race’ and gender in the European Union: a multi-layered recognition struggle’, in B. Hobson (ed.) Recognition Struggles and Social Movements: Contested Identities, Power and Agency. Cambridge: Cambridge University Press. pp. 121-144.

Williams, F. (2003b) ‘Social Policy: Culture and Nationhood’, in P. Alcock, A. Erskine and M. May (eds.) The Student’s Companion to Social Policy. Oxford: Blackwell Publishing with SPA. pp. 146-152

Williams, F. (2004b) ‘Trends in Women’s Employment, Domestic Service, and Female Migration: Changing and Competing Patterns of Solidarity’, in T.Knijn and A. Komter (eds.) Solidarity between the sexes and generations: transformations in Europe. Aldershot: Edward Elgar. pp. 210-218 .

Williams, F. (2004c) ‘Post-structuralist perspectives’, in S. Becker and A. Bryman (eds.) Understanding Research Methods for Social Policy and Practice. Bristol: Policy Press with SPA. pp 135-137.

Williams, F. (2005a) ‘New Labour’s Family Policy’, in M.Powell (ed.) Social Policy Review 17. Bristol: The Policy Press with SPA.

Williams, F. and Gavanas, A. (2004) ‘Eine neue Variante des Herr-Knecht-Verhältnisses? Überlegungen zum Zusammenspiel von Geschlechterverhältnis, Familienarbeit und Migration’ [‘New Masters / New Servants? The relations of gender, migration and the commodification of care’] in S. Leitner, I.Osner and M.Schratzenstaller (eds.) Wohlfahrstaat und Geschlechterverhältnis im Umbruch. Was kommt nach dem Ernährermodell? Jahrbuch für Europa und Nordamerika-Studien 2003. Opladen: Leske & Budrich. pp. 308-330.

In Press 2005 and forthcoming

Deacon, A. (2005) ‘An Ethic of Mutual Responsibility? Towards a Fuller Justification for Conditionality’, in C. Been and L. Mead (eds.) Welfare Reform and Political Theory. New York: Russell Sage Foundation.

Gavanas, A., Williams, F. and Tobio, C. (2006) ‘Global Care Chains in UK, Spain and Sweden’, in R. Lister, A. Antonne, M. Bussebaker, U. Gerhard, S. Johansson, J. Heinen, A. Leira, B. Siim, C. Tobio and F. Williams Gendering citizenship in Western Europe: new challenges for citizenship research in a cross-national context. Bristol: Policy Press.

Hines, S. (2005a) ‘'I am a Feminist but…': Transgender Men, Women and Feminism’, in J. Reger (ed.) Different Wavelengths: Studies of the Contemporary Women's Movement. London: Routledge.

Roseneil, S. (2005b) `Postmodern Transformations of Sexuality: Queer Challenges for Gender Studies’, in M. Rossini (ed.) Gender Matters – Gender Talks: Gender Studies at the Interface of Biology, Medicine, the Social Sciences and the Humanities. Freiburg: Karger.

Roseneil, S. (2006c) `Foregrounding Friendship: Feminist Pasts, Feminist Futures’, in M. Evans and J. Lorber (eds.) The Gender and Women’s Studies Handbook. London: Sage.

Roseneil,S. (2006d) `Towards a Queerer Sociology: researching personal life in the 21st century’, in M. O’Rourke and N. Giffney (eds.) Critical InQueery: An Interdisciplinary Reader. London: Black Swan Press.

Smart, C. (2005a) ‘Changing Commitments: A Study of Close Kin after Divorce’, in M. Maclean (ed) Family Law and Family Values, Oxford: Hart Publishing Ltd.

Williams, F. (2005b) ‘Welfare State’, in A and J. Kuper (eds.) The Social Sciences Encyclopaedia. London: Routledge. 3rd edition.

Williams, F. (2005c) ‘Care work’, in T. Fitzpatrick et al (eds.) International Encyclopedia of Social Policy. London: Routledge.

3. Conference or Seminar Papers

Ackers, H. L. (2000) ‘From ‘Best Interests’ to Participatory Rights: Children’s Involvement in Family Migration Decisions’. ESRC Seminar Series, Centre For Research on Family, Kinship & Childhood, University of Leeds, March 2000.

Ackers, H. L. (2000) ‘Citizenship of the Union? The Legal Status of Retired Migrants’. Socio-legal Studies Association Annual Conference, Belfast, April 2000.

Ackers, H. L. (2000) 'Attitudes Towards Quota-Based Policies as a Vehicle for the Advancement of Gender Equality in Research Careers: Some Empirical Evidence', Socio-legal Studies Association Annual Conference: Special Meeting on Women Law Professors, Belfast, April 2000.

Ackers, H. L. (2000) ‘Citizenship and the Free Movement of Persons in the European Union’. Law School, University of Bari, Italy, April 2000.

Ackers, H. L. (2000) 'Children, Citizenship and Internal Migration in the EU: Summary Findings'. Research and Youth Policy, Lisbon, Portugal, 18-20 May.

Ackers, H.L. (2000) ‘From ‘Best Interests’ to Participatory Rights: Children’s Involvement in Family Migration Decisions’, CESIS Dissemination Seminar, Lisbon, Portugal, May 2000.

Ackers, H. L. (2000) ‘The Impact of Retirement Migration on Family Resources and Informal Care Arrangements’. Social Policy Association Annual Conference, University of Surrey, Roehampton, 18-20 July.

Ackers, H. L. (2001) 'The Participation of Women Researchers in the TMR Programme of the European Commission: Key Conclusions on the Mobility Dimension’, Invited presentation to the European Molecular Biology Association, Heidelburg, June 2001.

## Ackers, H. L. (2001) ‘Partnering, Parenting and Mobility’. Invited lecture to European Research Area Conference: ‘An Enlarged Europe for Researchers, Brussels, 27-28 June 2001.

Ackers, H. L. (2001) 'Citizenship and Retirement Migration in the European Union'. British Society of Gerontology Conference, University of Stirling, 31 August – 2 September 2001.

Ackers, H. L. (2001) ‘The Changing Legal Context of the Family in Europe’. Keynote lecture to ESF/SCSS Exploratory Workshop: ‘Migration and Family Across the Lifecourse’, School of Geography, University of Leeds, 7-9 September 2001.

Ackers, H. L. (2002) ‘Parenting and Partnering and Barriers to Mobility in Scientific Careers’. Invited lecture to the Faculty of Medicine, University of Geneva, May 2002.

Ackers, H. L. (2002) ‘Working with Children in Cross-National Research’. Centre for Research on Family, Kinship & Childhood, University of Leeds, May 2002.

Ackers, H. L. (2002) ‘Researching Families from a Socio-legal Perspective’. Invited presentation to ESRC Seminar Series: ‘Knowing Families, Centre for Research on Family, Kinship and Childhood, University of Leeds, 22 November 2002.

Ackers, H. L. (2003) ‘The Participation of Women in European Science’. Keynote lecture to the Marie Curie Fellows’ Association Annual General Meeting, Brussels, March 2003.

Ackers, H. L. (2003) ‘Managing Work and Family Life in Peripatetic Careers: The Experiences of Mobile Women Scientists in the European Union’. PHARE Symposium on Science Policy, Mobility and Brain Drain in the EU and Candidate Countries, University of Leeds, 27 July 2003.

Ackers, H. L. (2003) ‘Negotiating Kinship Transnationally’. CAVA International Seminar on Transnational Kinship, 18 September 2003.

Ackers, H. L. (2003) ‘Managing Relationships in Peripatetic Careers: Scientific Mobility in the European Union’ Centre for Interdisciplinary Gender Studies, University of Leeds, October 2003.

Ackers, H. L. (2004) ‘Moving People and Knowledge: The Mobility of Scientists within the European Union’. Invited presentation to the Migration Research Centre, University of Liverpool, 31 March 2004.

Ackers, H. L. (2004) ‘Capturing the Subject in Migration Research’. ESRC Seminar Series: European Cross-National Research and Policy - Researching Family and Childhood from a European Welfare Perspective, Tallin, Estonia, 12 June 2004.

Ackers, H. L. (2004) ‘Gender, Mobility and Progression in Science Careers’. European Science Open Forum Conference in conjunction with the Marie Curie Fellows’ Association Career Workshop, Stockholm, 28 August 2004.

Ackers, H. L. (2004) ‘The Impact of Dual Career or ‘Same Career Partnering’ on Retention and Progression in Science’. ESRC Seminar Series: Critical Perspectives on Career and Family – Friendly Policies, Loughborough Business School, 13 October 2004.

Ackers, H. L. (2004) ‘Moving People and Knowledge: Assessing the Impact of Enlargement on Scientific Mobility within the European Union’. Invited keynote to the European Universities Association Conference ‘Research Training as a Key to a Europe of Knowledge’, Maastricht, The Netherlands, 28-30 October 2004.

Ackers, H. L. (2004) ‘Assessing the IMPACT of the Marie Curie Scheme’. Structuring the European Research Area Human Resources and Mobility: Advisory Group Meeting, European Commission, 13 December 2004.

Ackers, H. L. (2005) ‘Excellence or Exploitation? The Role of Fixed Term Contracts in Junior Research Careers’. European University Association Conference ‘Doctoral Programmes in the European Knowledge Society’, Salzburg, 3 February 2005.

Ackers, H. L. (2005) ‘Gender, Mobility and Progression in Science Careers’, ESRC, DTI and DfES Workshop on Diversity in Science Education and Training, Oxford, 1-2 February 2005.

Ackers, H. L. and Dwyer, P (2002) ‘Senior Citizenship? The Legal Rights and Citizenship Experiences of Retirement Migrants’. Keynote presentation to the European Science Foundation Scientific Network: Older People in Europe, Madrid Workshop, 22-24 March 2002.

Ackers, H. L. and Oliver, L. (2004) ‘Reconciling Work and Family Life in Science Careers: Contracts and Career Progression, Work Life Balance Across the Lifecourse, Centre for Research on Families and Relationships, University of Edinburgh, 30 June 2004.

Ackers, H. L., Foadi, S., Stalford, H. and Redmond, M. (2002) ‘Facilitating Mobility? European Citizenship and The Evaluation of Care’. 1st International Congress on Child Migration ‘Return, Reunite and Reconcile’, Child Migrants Trust, New Orleans, 27-31 October 2002.

Deacon, A. (2000) 'The Employment Service & Welfare Reform'. Paper to seminar to mark the 90th anniversary of the Employment Service, Sheffield Hallam University, 26 June 2000.

Deacon, A. (2000) 'Anglo-US approaches to welfare reform: the limits of ideology and rhetoric'. Paper presented to Fall Research conference of the Association for Public Analysis and Management, Seattle, Washington, USA, 4 November 2000.

Deacon, A. (2001) 'Levelling the playing field, activating the players': New Labour and the cycle of disadvantaged' Paper presented to the Annual Conference of the Social Policy Association, Queens University, Belfast, 25 July 2001

- Deacon, A. (2002) ‘Moral Arguments for Welfare Reform’. Seminar Paper on Europe’s Welfare Burden, Stockholm Network, The Hague, Netherlands, 31 Jan - 1 Feb 2002.

Deacon, A. (2002) ‘Equality, Community and…Coercion? What Values Shape New Labour’s Approach to Welfare Reform?’. ESPRN Conference on Social Values, Social Policies, University of Tilburg, Netherlands, 29-31 August 2002.

- Deacon, A. (2002) ‘Welfare Contractualism to Welfare Mutualism’. Seminar Paper on ‘A New Agenda for Rights and Responsibilities’,  No, 10 Downing St, London, 12 December 2002

- Deacon, A. (2002) ‘Conditionality at the Crossroads’. Seminar Paper on ‘Where will the Rights and Responsibilities Agenda take us?, Institute for Public Policy Research, London, 19 December 2002.

Deacon, A. (2003) ‘Re-thinking the unthinkable: Conditionality, Equality and Welfare Reform’. Social Policy Association Conference, University of Teeside, July 2003.

Deacon, A. (2003) ‘Justifying Conditionality: The case of ‘anti-social’ tenants’. Conference of the Housing Studies Association, University of Bristol, September 2003.

- Deacon, A. (2003) ‘Beyond paternalism: Towards a fuller justification for conditionality in welfare’. Welfare Reform and Political Theory, Wingspread Conference Centre, Racine, Wisconsin, USA, October 2003. Invitation from Johnson Foundation and Russell Sage Foundation.

Deacon, A. and Williams, F. (2004) ‘Personal Qualities and Civic Virtues: Care, Values and the Future of Welfare’. Annual Conference of the European Network for Social Policy Analysis, University of Oxford, September 2004.

Duncan, S. (2001) 'Welfare state regimes, gendered moral rationalities, and gender cultures’. Paper given to Department of Sociology and Social Policy, University of Stirling, March 2001.

Duncan, S. (2002) ‘Cohabitation and Postmodern Intimacy’. British Sociological Association Annual Conference, University of Leicester, March 2002.

Duncan, S. (2002) ‘Cohabitation, Commitment and Postmodern Intimacy’. Socio-Legal Studies Association Annual Conference, Aberystwyth, April 2002.

Duncan, S. (2002) ‘A Mother’s Instinct?  Paid Work, Partnering and Childcare’. Social Policy Association Annual Conference, Middlesborough, July 2002.

Duncan, S. (2002) ‘Emotions, Rationalities and Caring’. Emotional Geographies Conference, Lancaster, September 2002.

Duncan, S. (2002) ‘Localities and Moralities’. Social Policy Research Centre - Space and Locality Seminar, Open University, January 2002.

Duncan, S. (2002) ‘Paid Work, Partnering and Childcare’. Cabinet Office Equality Unit - Gender Research Forum Conference, London, November 2002.

- Duncan, S. (2003) Conference discussant, ‘Employment and Care’, Institute of Education Seminar, Cumberland Lodge, 27 – 28 October 2002.

Duncan, S. (2003) ‘Mothers, Care and Employment: Values and Theories’. Presented to the ‘CAVA Initial Findings Seminar’, University of Leeds, 23 May 2003.

- Duncan, S. (2003) ‘Emotions, caring and rationalities’. ESRC Work-life Seminar, University of Manchester, 31 October 2003.

- Duncan, S. (2004) ‘Combining intensive and extensive research’. ESRC seminar series on ‘Knowing families’, University of Leeds, 19 March 2004.

- Duncan, S. (2004) ‘Explaining gender differences: policy, agency, norms’. Gender equality Centre, Karlstad University, Sweden, 11 May 2004.

- Duncan, S. (2004) ‘Mother knows best? Combining motherhood and employment’. Association of Women in Science and Engineering, Leeds, 18 May 2004.

- Duncan, S. (2004) ‘Mothering, class and rationality’. CPFR International conference on work-life balance, Edinburgh, 30 June 2004.

- Duncan, S. (2004) ‘Choice and provision in local pre-school childcare’. Institute of Education, 21 October 2004.

- Duncan, S. (2004) ‘Emotion, rationality and mothering’. BSA Sexuality and emotions study conference, Birbeck college, London, 23 October 2004.

Duncan, S. (2004) ‘The fragmenting family?  Cohabitation, marriage and commitment’. Keynote paper at Annual Social and Communication Studies Conference, ‘Commitment, cohabitation and the law’, University College Chester, 24 November 2004.

Duncan, S. (2005) ‘Lone Mothers and Paid Work’. Department of Work and Pensions expert panel, London, January 2005.

Duncan, S. (2005) ‘Why don’t they marry? Cohabitation and commitment’. Paper presented to ESRC Seminar Series 'Changing Social Norms, Changing Family Law? Rights and Responsibilities for Partners, Friends and Carers’ Seminar Two ‘The New Family – Unmarried Cohabitation, Temporary Marriage and Legal Rights’, Nuffield Foundation, London, 25 February 2005.

Duncan, S.. (2005) ‘Why don’t they marry? Cohabitation and commitment’. Presented at Socio-Legal Studies Annual Conference, special stream organised by the Department for Constitutional Affairs. University of Liverpool, 30 March 2005.

- Duncan, S. and Edwards, E. (2003) ‘Mothers, self-employment and childcare’. Prowess Women’s Enterprise Conference, Brighton, 6 November 2003.

Duncan, S. and Smith, D. (2004) “’Lovers: the seven ages of man and woman’. ESRC showcase for Social Science Week, London, 18 June 2004.

Duncan, S. and  Williams, F. (2003) ‘The Contours of Care and Intimacy’. Seminar on People, Places and Policy, The Office of the Deputy Prime Minister, London, 19 February 2003.

Duncan, S. and  Williams, F. (2004) ‘Rethinking Families’. House of Commons breakfast briefing for the HoC Social Science Research Committee, 20 June 2004.

- Flowerdew, J. and Neale, B. (2002) ‘Trying to Stay Apace’. Socio-Legal Studies Association Annual Conference, University of Wales, Aberystwyth, 3-5 April 2002.

Flowerdew, J. and Neale, B. (2003) ‘Children’s Kinship after Divorce’. Socio-Legal Studies Association Annual Conference, Nottingham, April 2003.

Gavanas, A. (2000) ‘The Fatherhood Responsibility Movement: The Centrality of Marriage, Work and Male Sexuality in U.S. Reconstructions of Masculinity and Fatherhood’. Paper presented at the American Anthropological Association. Panel: Households and Youth Cultures in the New Economy, San Francisco, 14-19 November 2000.

Gavanas, A. (2001) ‘Masculinizing Domesticity and Domesticizing Masculinity’. Presentation to Center for Women’s Studies as part of Men and Masculinities series, Stockholm University, 19 April 2001.

Gavanas, A. (2001) ‘The Fatherhood Responsibility Movement: Cutting Across Contemporary U.S. Men’s Movements’. Paper presented at Gender and Citizenship Within and Across Policy Borders, Riksbanken Symposium at the Swedish Parliament. 29 October 2001.

Gavanas, A. (2002) ‘Domesticating Masculinity and Masculinizing Domesticity in Contemporary U.S. Fatherhood Politics’. Paper presented at the Conference Collective Interventions on the Terrain of Care and Intimacy. International Perspectives, University of Leeds, England, 1 November 2002.

Gavanas, A. (2003) ‘Att Domesticera Maskulinitet och Maskulinisera Domesticitet’. Presentation at Högre Seminariet at Tema Genus, Linköping University, 11 February 2003.

Gavanas, A. (2003) ‘Domesticating Men: Century-long Dilemmas of U.S. Fatherhood Politics’. Paper presented at the 4th Conference of the International Federation for Research in Women’s History. Panel 39: “Sexuality, Family Boundaries and Gendered Obligation: A Comparative Discussion of Social Policy in the United States and Mandatory Palestine,” Queen’s University, Belfast,13 August 2003.

Gavanas, A. (2003) ‘Masculinizing Domesticity and Domesticating Masculinity’. Paper presented at the Gender and Power 5th European Feminist Research Conference. Panel: “Families, Fatherhood and the Private Sphere’, Lund University, Sweden, 22 August 2003.

Gavanas, A. (2004) ‘Migrant Domestic Work in the EU’. Paper presented at CAVA Advisory Board Conference, Leeds University, UK, 28 May 2004.

Gavanas, A. (2004) ‘Preliminary Findings; Migrant Domestic Work in the EU’. Presented at the Gendered transformations of work across Europe workshop at the European Institute, Florence, Italy, 23 November 2004.

Gavanas, A., Williams, F. and Tobio, C. (2004) ‘Migrant domestic workers in the EU’ Network meeting for edited volume Gender and Citizenship with Ruth Lister and Stina Johansson. Stockholm, 17-18 December 2004.

Hines, S. (2002) 'Feminist Theory and Trans Masculinity'. Paper presented at GENDYS 2002: Seventh Gender Dysphoria Conference, University of Manchester.

Hines, S. (2002) 'Feminism and Transgender Practices'. Paper presented at British Sociological Conference, University of York.

Hines, S. (2002) 'Transgendered Masculinity and Feminist Politics'. Paper given as part of Centre for Interdisciplinary Gender Studies Work in Progress Seminar Series, University of Leeds.

Hines, S. (2003) ‘Transgender Practices of Partnering and Parenting', Paper presented at British Sociological Conference, University of York.

Hines, S. (2004) 'Remembering the Subject: Towards a Queer Sociology of Transgender'. Presented as part of Queer Theories Seminar Series, Queens College Dublin.

Hines, S. 'Tran(s)sexualities: Exploring Sexual Desire, Practice and Identity within Transgender Narratives’. Pleasure and Danger Revisited Conference, University of Cardiff, 2004.

Hines, S. (2004) 'Transgender Politics: Social Movements and Collective Action'. Paper presented at Reflecting Genders: Sex and Gender Diversity Conference, University of Manchester, 30 November 2004.

Hines, S. (2004) '(Trans)gendering Intimacy'. Presented as part of Queer Seminar Series, University College London.

Hollway, W. (2000) ‘Objectivity in British Psychoanalysis’. Keynote speaker at Psychoanalysis and Society, Bolton College, 27 January 2000.

Hollway, W. (2000) ‘Psychological and psychoanalytic approaches to parenting 1945 - present’. Invited speaker at University of Huddersfield, 25 May 2000

Hollway, W. (2000) ‘Theorising differences in the moral capacity of care: the perspective of unconscious intersubjectivity’. Paper presented at Gendering Ethics/ Ethics of Gender conference, University of Leeds, 23-25 June 2000.

Hollway, W. (2000) ‘Institutional sexism in the University context’. Invited keynote to Second European conference on Gender Equality in Higher Education, Zurich, 15-21 September 2000.

Hollway, W. (2000) ‘Who’s there? Questions of method for researching psycho-social subjectivity’. Invited seminar at Launch of the Centre for Psycho-social Studies, Department of Psychology, Birkbeck College, London, 18 September 2000.

Hollway, W. (2001) ‘The Psycho-social subject in evidence-based practice’. Keynote at Qualitative evidence-based practice conference, Coventry University, 14-16 May 2001.

Hollway, W. (2001) ‘A Psycho-Social Paradigm for Research in(to) Higher Education: Principles and Practice’. Keynote at Higher Education Close Up: An International Qualitative Research Conference, Lancaster University, 16-18 July 2001.

Hollway, W. (2002) Introductory plenary speaker, LTSN Psychology Section Day Workshop on Qualitative Project Supervision, Leeds School of Psychology, 12 April 2002.

Hollway, W. (2002) ‘Panic and perjury: a psycho-social case analysis based on the FANI method’. Keynote speaker at Narrrative, Memory and Health conference, University of Huddersfield, 20 April 2002.

Hollway, W. (2002) ‘Psychoanalysis and Research Methods: Some Implications’. Seminar at the Department of Sociology, University of Essex, 31 October 2002.

Hollway, W. (2002) ‘Reaching the Family Dynamics that other Methods don’t reach’. Invited speaker, ESRC seminar series ‘Knowing Families’, Sociology and Social Policy, University of Leeds, 22 November 2002.

Hollway, W. (2003) ‘The Implications of Positing a Psycho-Social Subject for Research Methods’. Plenary speaker at Exploring Psycho-Social Research Methods: A One-day international conference, University of Western England, 25 January 2003.

Hollway, W. (2003) ‘Psychoanalytically-informed methods in social research’. Plenary speaker at Nordic Network of Educational Research conference, University of Roskilde, Denmark, November 2003.

Hollway, W. (2003) ‘The Free Association Narrative Interview Method’. Workshop held at University of Copenhagen, November 2003.

Hollway, W. (2004) ‘The Gender of Parenting’. Seminar at Department of Psychology, University of Auckland, March 2004.

Hollway, W. (2004) ‘Qualitative Methods in Clinical Research’. Staff seminar at Department of Health and Psycho-social Studies, Auckland University of Technology, March 2004.

Hollway, W. (2004) ‘The Gender of Parenting’. Seminar at Department of Psychology, University of Western Sydney, April 2004.

Hollway, W. (2004) ‘The FANI method and qualitative data analysis’. Doctoral student workshop at Department of Psychology, University of Western Sydney, April 2004.

Hollway, W. (2004) ‘In praise of (post-critical) objectivity’. Paper at Society for Australasian Social Psychology annual conference, Auckland, 15-18 April 2004,

Hollway, W. (2004) ‘Further issues in qualitative clinical research’.Two staff workshops at Auckland University of Technology, Department of Health and Psycho-social Studies, 23 April 2004.

Hollway, W. (2004) ‘Care in the Research Relationship: Theory and Practice’. Invited plenary lecture at the 6th International Summer School in Lifelong Learning, Roskilde University, Denmark. 3-13 August 2004.

Hollway, W. (2005) Invited plenary talk at the first meeting of the ESRC-funded Identities and Social Action Programme, Regents College, London, 20 January 2005.

Hollway, W. (2005) Invited Plenary Speaker at Belfast day conference on Qualitative methods in Psychology, Open University and Queen’s University Belfast, 11 March 2005.

Hollway, W. and Jefferson, T. (2000) ‘Free Association and the Research Interview’. Paper presented at Annual conference of the American Sociological Association on Feminisms, psychoanalysis and social research: inner and outer realities, 14-16 August 2000.

Hollway, W. and Jefferson, T. (2001) ‘Ethical practices in interviewing: the defended subject of research’ and ‘Free Association, narrative analysis and the defended subject: the case of Ivy’ Two papers presented at the Centenary British Psychological Society conference on narrative psychology, Glasgow, 28-31 March 2001.

Hollway, W. and Jefferson, T. (2002) ‘The Free Association Narrative Interview Method’. Invited speaker at University of Poznan, Poland, May 2002.

Hollway, W. and Jefferson, T. (2002) ‘Panic and perjury: understanding agency in the case of Vince’. Seminar at University of Bremen, Germany, May 2002.

Hollway, W. and Jefferson, T. (2005) ‘Producing and Analyzing Qualitative Data’. Seminar at Dublin Institute of Technology, 10 February 2005.

Hollway, W. and Sherrard, C. (2000) ‘Validity checking and conflicts of interest’. Paper presented at the annual conference of the British Psychological Society on Ethical Practices in Research Interviewing., University of Dundee, 10-12 July 2000.

Irwin, S. (2000) ‘Changing Life-Times: the end of the modern life course?’. Paper presented to BSA conference, York, April 2000.

Irwin, S. (2001) ‘Reproductive regimes: the shaping of family and household change’. Paper presented to Population Geography Research Group conference, Leeds Metropolitan University, June 2001.

Irwin, S. (2003) ‘Values, care and commitments: pattern and process’. Paper presented to Social Stratification Seminar, Department of Sociology, University of Cardiff.

Irwin, S. (2003) ‘The changing shape of values, care and commitments’. Paper presented to ESPAnet conference: Changing European Societies - the role for Social Policy, Danish National Institute of Social Research, Copenhagen, 13-15 November 2003.

Irwin, S. (2004) ‘Water through the sand? Locating values in changing family life’. Paper presented to ESRC Seminar Series ‘Knowing Families’, seminar 5: ‘Combining qualitative and quantitative approaches in family research’, Centre For Research on Family, Kinship & Childhood, University of Leeds, March 2004.

Irwin, S. (2004) ‘Norms, values and work-life balance’. Paper presented to Centre for Research on Families and Relationships International Conference: Work-life balance across the Lifecourse, University of Edinburgh, 30 June-2 July 2004.

Irwin, S. (2004) ‘Individualisation: a narrow lens on changing social landscapes of interconnection’. Paper presented to ESRC CAVA International Symposium: Rethinking Care Relations, Family Lives and Policies, University of Leeds, 3-5 December 2004.

Irwin, S. and Bottero, W, (2002) ‘Locating Differences: Values, Claims and Changing Social Relations’. Paper presented to PAVIS Centre for Social and Cultural Research conference ‘Cultural Returns: assessing the place of culture in social thought’, 18-20 September 2002.

Irwin, S. and Williams, F. (2002) ‘Understanding Social Values and Social Change: the Case of Care, Family and Intimacy’. Paper presented to the ESPRN Conference on Social Values, Social Policies, University of Tilburg, Netherlands, 29-31 August 2002.

Mason, J. (2000) 'Crafting time: inheritance and family practices'. Paper presented to the BSA Annual Conference, University of York, 17-20 April 2000.

Mason, J. (2000) 'Researching moral agency in family relationships'. Paper presented to Qualitative Research Workshop, Social Policy Research Centre, University of York, 7 June 2000.

Mason, J. (2002) ‘Ethics in Qualitative Research’. Invited Speaker at Women’s Workshop on Qualitative/Household Research Book Launch, Oxford Brookes University, 18 February 2002.

Mason, J. (2003) ‘Kinship and Belonging across Boundaries’. Paper presented to British Sociological Association Conference, University of York, 11-13 April 2003.

- Mason, J. (2003) ‘Qualitative Longitudinal Research’. Presented at ESRC Opportunities for Complementarity between Longitudinal Studies, Royal Statistical Society, London.

Mason, J. (2003) ‘The Transnational Kinship Project’. Presented to the CAVA Initial Findings Seminar, University of Leeds, 23 May 2003.

Mason, J. (2004) ‘Meshing Qualitative and Quantitative Methods in Family Research’. Presented to the ESRC Research Methods Programme Methods Festival, University of Oxford, July 2004.

Mason, J. (2004) ‘Ways, means and motives: a personal journey through 20 years of computer assisted qualitative data analysis’. Plenary Address to the Fifth International Conference on ‘Strategies in Qualitative Research’, University of Durham, 1-3 September 2004.

Mason, J. and Smart, C. (2003) ‘Extending the Reach of Qualitative Research’. ESRC ‘Knowing Families’ Seminar, University of Leeds.

Mason, J. and Tipper, R. V. (2004) 'Researching Agency and Relationality in Children's Kinship'. Presented to the WELLCHI EU Sixth Framework Programme Network Seminar, Leeds.

Neale, B. (2000) ‘Theorising Family, Kinship and Social Change’. CAVA Workshop presentation, University of Leeds, January 2000

Neale, B. (2000) ‘Children’s views on Contact with non-residential Parents’. Invited presentation to one-day symposium on Contact Issues for Family Research, Centre for Family Research, University of Cambridge, March 2000.

Neale, B. (2000) ‘Researching Children’s Family Lives’. Visiting Lecture on Research Methodology Degree. School of Social Sciences, City University, March 2000.

Neale, B. (2000) ‘Children, Citizenship and Divorce’. Keynote Address to Annual General Meeting of Wiltshire Family Mediation Service, June 2000.

Neale, B. (2000) ‘What do Children Value about Family Life?’. Presentation to one-day Practitioner Seminar on Listening to Children in Family Law, Centre For Research on Family, Kinship & Childhood, University of Leeds, June 2000.

Neale, B. (2000) ‘Seeing Children in a Different Way’. Keynote Address to Annual General meeting of UK College of Family Mediators, Swindon, September 2000.

- Neale, B. (2000) ‘Family Citizenship for children’. Invited Presentation, Devon County Council Policy Conference, Supporting Young People in Changing Families, Exeter, October 2000.

- Neale, B. (2000) ‘Changing families, Changing values? Lessons from research’. Invited presentation, Royal Society for the Arts and Sciences, Relate Annual Seminar, University of Leeds, October 2000.

- Neale, B. (2001) ‘Hierarchies and Boundaries in family relationships’. Invited presentation, One Day Conference:  Families First, Institute of Education, University of London, January 2001.

- Neale, B. (2001) Welfare and Citizenship for Children Practitioner Training Seminar: Are we listening to Children? Divorce and Changing Family Practices. Centre For Research on Family, Kinship & Childhood, University of Leeds, February 2001

- Neale, B. (2001) Invited participant to ‘closed’ policy Seminar on Patterns of Ethnic Minority Family Life. National Family and Parenting Institute, London, April 2001.

- Neale, B. (2001) ‘Domestic Violence and Contact in post divorce families’. Invited presentation. South Yorkshire Family Court Magistrates Forum Training Day, Doncaster, May 2001

- Neale, B. (2001) 'When might co-parenting work – and when not?’ Practitioner Training Seminar: The Trials, Tribulations and Triumphs of Co-Parenting, Centre For Research on Family, Kinship & Childhood, University of Leeds, June 2001.

Neale, B. (2001) Invited participant to ‘closed’ policy seminar, One plus One: Two Day Workshop on Marriage and Divorce, June 2001.

Neale, B. (2001) ‘Children's Family Citizenship’. Paper presented in the Childhood and Politics stream European Sociological Association Bi Annual Conference, Helsinki, August 2001.

Neale, B. (2001) Invited participant to ‘closed’ policy seminar on Children’s Involvement in Contact Decisions, National Family and Parenting Institute, September 2001.

Neale, B. (2001) 'Care, respect and fairness: children’s ethics in post divorce families'. Presenter/Joint organiser at  one day conference Children, Family Law and Family Conflict, Young Voice/University of London/Centre For Research on Family, Kinship & Childhood, Covent Garden, London, September 2001.

Neale, B. (2002) ‘Time, Texture and Childhood’. Invited presentation to Longitudinal Qualitative Research Seminar, South Bank University, April 2002.

Neale, B. (2002) ‘Children’s Experience of Divorce’. Keynote Address to the National Family Mediation Northern Regional Conference, York, June 2002.

Neale, B. (2003) ‘Parenting Arrangements for Children after Divorce: Children’s long term perspectives’. Keynote address to UK College of Family Mediators Annual Conference, Swindon, February 2003.

Neale, B. (2003) ‘Longitudinal Qualitative Research’. Invited presentation to ESRC Seminar Series, Knowing Families: Researching Families over Time, Centre For Research on Family, Kinship & Childhood, University of Leeds, March 2003.

Neale, B. (2003) ‘Surviving Post Divorce Family life: Children’s Perspectives’. Keynote address to Gingerbread Regional Bi-Annual Conference, Leeds, April 2003.

Neale, B. (2003) ‘Re-tying the knot? Re-partnering after Divorce. Presentation at the BSA Annual Conference, University of York 11th -13th April 2003.

Neale, B. (2003) ‘Re-tying the Knot? Re- partnering After Divorce’. Presentation for CAVA Initial Findings Seminar, University of Leeds, 23 May 2003.

Neale, B. (2003) ‘The dynamics of parent child relationships after divorce: young people’s long term experiences of contact and shared residence’. Presenter and joint organiser of one day conference Frameworks of Understanding: Multidisciplinary Perspectives on Childhood, Centre For Research on Family, Kinship & Childhood, University of Leeds, June 2003.

Neale, B. (2003) Relationality and Re-partnering after Divorce’. European Sociological Association Bi-Annual Conference, Murcia, Spain, September 2003.

Neale, B. (2004) ‘Enduring Families?: Long term patterns of contact and shared residence after parental divorce’. NTNU, University of Trondheim, Norway, September 2004.

Neale, B. (2004) ‘Contact and Shared Residence: The wider context’. Making Contact Safe, RIBA, London, September 2004.

Neale, B. (2004) ‘Rethinking Parenting: Children’s Perspectives’. ESRC seminar series, Swindon,,October 2004.

Neale, B. (2004) ‘Children’s Citizenship after Parental Divorce: Implications for family law’. CAFCASS Yorkshire and Humberside Regional Management Training Day, Leeds, October 2004.

Neale, B. (2004) ‘The Voice of the Child in Private Law Proceedings: thinking in the long term’. Hear Me Out Conference, Cheshire County Council/CAFCASS North West Region, Cheadle, November 2004.

Neale, B. (2004) ‘Becoming the author of your own life’: the changing lives of young people after parental divorce . EU Wellchi Network International Workshop, University of Leeds, November 2004.

Neale, B. (2005) Invited participant to closed policy seminar on Children and the

Changing law, Children’s Rights Alliance for England, April 2005.

Roseneil, S. (2000) `Sexual Transformations of the Post-War Welfare Subject’. Department of Applied Social Studies, Lancaster University.

Roseneil, S. (2000) `The Women’s Peace Movement in the 1980s’. Department of Peace Studies, University of Bradford.

Roseneil, S. (2000) `Creative Effervescence and the Millennium Square’. Millennium Intervention Group Seminar, Leeds.

Roseneil, S. (2000) `Social Research and Political Activism: Reflections on Researching Greenham’. Social Movements and Political Activism Conference, University of East London.

Roseneil, S. (2000) `The Queer Feminisms of Greenham Common’. The Future of the Queer Past Conference, University of Chicago, September 2000.

Roseneil, S. (2000) `Towards a Society of Friends? Thoughts about the Ethics and Practice of Friendship in the early 21st Century`. Towards an Ethical Sociology Conference, Leeds Metropolitan University, September 2000.

Roseneil, S. (2000) `Common Women, Uncommon Practices: The Queer Feminisms of Greenham’. `Trends in Feminist Thought and Politics’, Women’s Education Research and Resource Centre 10th Anniversary Conference, University College Dublin, December 2000.

Roseneil, S. (2001) `Collective Voices on Parenting and Partnering at the turn of the 21st Century’. University College of Ripon and York St. John.

Roseneil, S. (2001) `Gender Studies in the U.K’. University of St Petersburg.

Roseneil, S. (2001) `The Permissive Society and Its Enemies’. Institute of Contemporary British History Conference, Senate House, University of London.

Roseneil, S. (2001) `Gender Politics and Globalisation”. Panel discussant, Globalisation and Political Protest, North and South, RC47 International Sociological Association Conference, New York University.

Roseneil, S. (2001) `The Queer Women of Greenham’. Work and Play: Lesbian Lives Conference, University College Dublin, February 2001.

Roseneil, S. (2001) `Rethinking Theoretical Approaches to Studying Women’s Movements’. Women’s Movements and Internationalisation Seminar, Helsinki, August 2001.

Roseneil, S. (2001) `Care, Friendship and Non-Conventional Partnership: Queering Welfare Research’. Department of Sociology, University of Greenwich, November 2001.

Roseneil, S. (2001) `Why we should care about friends’. Centre for Gender Studies, University of Hull, November 2001.

Roseneil, S. (2001) `The Queer Feminisms of Greenham: Reflections Twenty Years On’. Women’s Archive of Wales Annual Conference, Cardiff Town Hall, November 2001.

Roseneil, S. (2001) `Care, Friendship and Non-Conventional Partnership: Rethinking Welfare’. University of Umea, Sweden, December 2001.

Roseneil, S. (2002) `Collective Voices around Partnering and Parenting’. Cabinet Office Equality Unit, Gender Research Forum, Palace of Westminster, February 2002.

Roseneil, S. (2002) `Queering Sociality – Queering Social Research’. Queer Research Conference, University of Copenhagen, February 2002.

Roseneil, S. (2002) `Looking Back Queerly: Greenham, Twenty Years On’. Manchester Metropolitan University Annual Women’s Studies Lecture, March 2002.

Roseneil, S. (2002) `The Challenge of a Queer Lens’, `Queer Tendencies: Sexuality and Social Change in Postmodernity’, `Queering the Politics of Care and Welfare’ and `Queering the Study of Social Movements: the Queer Feminisms of Greenham’. Four invited lectures given as part of a National Research Seminar `Queer Theory and the Politics of Postmodernity’, University of Oslo, March 2002.

Roseneil, S. (2002) `Transgressing the Boundaries of Sexuality’. Gender Talks Conference, University of Geneva, April 2002.

Roseneil, S. (2002) `The Future of Social Movement Studies’. Social Movement Studies Conference, London School of Economics, April 2002.

Roseneil, S. (2002) `International Coalition and the Erotics of Women’s Action’. 12th Berkshire Conference on the History of Women, University of Connecticut at Storrs, June 2002.

Roseneil, S. (2002) `Rethinking Care and Intimacy: A Queer Approach’. Department of Anthropology and Sociology, University of Wales, Swansea, October 2002.

Roseneil, S. (2002) `Collective Interventions around Parenting and Partnering: theorizing gender, sexuality and citizenship’. Active Citizenship and Marginality in a European Context, Research Seminar, Vaxjo University, Sweden, October 2002.

Roseneil, S. (2002) `Care and Intimacy beyond the Heteronorm’. Centre for Women’s Studies, University of York, October 2002.

Roseneil, S. (2002) `Living and Loving beyond the Heteronorm: towards a queer analytic for the study of welfare’. Department of Sociology, University of Durham, November 2002.

Roseneil, S. (2002) `Living and Loving beyond the Heteronorm’. Conference on Friendship and Relationships across the Lifecourse, Centre for Research on Families and Relationships, University of Edinburgh, November 2002.

Roseneil, S. (2003) `Thinking beyond Hetero-relations: queer transformations and the study of welfare’. Queeries Seminar Series, University College Dublin, January 2003.

Roseneil, S. (2003) `Care and Intimacy in the 21st Century – a queer perspective on social transformation’. School of Sociology and Anthropology, University of Aberdeen, March 2003.

Roseneil, S. (2003) `Against the Metaphor of “Standpoint’. Symposium on the Work of Sandra Harding, University College Cork, April 2003.

Roseneil, S. (2003) `Ambivalent Affectivities: Angel’s “Arrangement” and the Contemporary Condition of Personal Life’. ESRC CAVA Initial Findings Seminar, University of Leeds, May 2003.

Roseneil, S. (2003) `Re-imagining Care: Transformations of Intimacy, Care and Sociability in the 21st Century’. Social Policy Association Conference, University of Teeside, July 2003.

Roseneil, S.(2003) `Intimate Counter-Normativities: A Queer Analysis of Intimacy in the 21st Century’. 5th European Feminist Research Conference, University of Lund, August 2003.

Roseneil, S. (2003) `Re-Imagining Care: Transformations of Intimacy, Sociability and Welfare in the 21st Century’. Department of Political Science, University of Adelaide, November 2003.

Roseneil, S. (2003) `Why We Should Care about Friends’. Centre for Applied Social Research, RMIT, December 2003.

Roseneil, S. (2003) `Ambivalent Affectivities: Angel’s “Arrangement” and a Psycho-Social Lens on the Contemporary Condition of Personal Life’. The Australian Sociological Association Conference, University of New England, Australia, December 2003.

Roseneil, S. (2004) `The End of Lesbianism?’. 10th Lesbian Lives Conference, University College Dublin, February 2004.

Roseneil, S. (2004) `Queer Affectivities and Heteronormative Policy Worlds: researching contemporary transformations in intimate life’. Kings College London, February 2004.

Roseneil, S. (2004) `Unconventional Couples: Findings from a Longitudinal Study of Individualized Lives’. ESRC Seminar on Non-Familial Intimate Relationships across the Life-Course, University of Leeds, February 2004.

Roseneil, S. (2004) `The Ambivalence of Contemporary Personal Life: A Psycho-Social Analysis’. British Sociological Association, University of York, March 2004.

Roseneil, S. (2004)`Towards a More Friendly Society: Work, Play and Care in the 21st Century’. Centre for Policy Studies in Education, University of Leeds, June 2004.

Roseneil, S. (2004) `Researching Care and Intimacy’. Nordic Research Council Summer School, Soro, Denmark, August 2004.

Roseneil, S. (2004) `A Psycho-Social Approach to the Study of Intimate Life’. Nordic Research Council Summer School, Soro, Denmark, August 2004.

Roseneil, S. (2004) `A sociological perspective on hate crimes against lesbians and gay men’. Conference to launch the Hate Crimes Initiative in Kirklees, Halifax, September 2004.

Roseneil, S. (2004) `Care, Intimacy and Connection in the Age of Individuals’. Department of Sociology, University of Alberta, October 2004.

Roseneil, S. (2004) `Ambivalent Affectivities: a psycho-social lens on the contemporary condition of personal life’. Department of Sociology, University of Alberta, October 2004.

Roseneil, S. (2004) `Women’s Peace Activism and the Memorialization of the Cold War’. Department of Women’s Studies, Santa Clara University, CA, October 2004.

Roseneil, S. (2004) `Beyond the Conventional Family: new ways of thinking about personal relationships’. Invited seminar at Intel, Portland, Oregon, November 2004.

Roseneil, S. (2004) `Sutured Selves, Queer Connections: Intimacy at the Cutting Edge of Individualization’. CAVA Symposium “Rethinking Family Lives”, Weetwood Hall, Leeds, December 2004.

Roseneil, S. (2004) `Homophobic Violence and Gender Violence: a sociological perspective’. Public meeting organized by Calderdale Council, Huddersfield, December 2004.

Roseneil, S. (2005) `Queer Sociality’. In Conversation Seminar, Department of Sociology, University of Manchester, February 2005.

Roseneil, S. (2005) ‘Pour une sociologie plus queer: enqueter sur la vie personelle au XXIe siecle’. Keynote at Epistemologies du genre colloquium organised by GDRE-MAGE (CNRS) and CNAM, Paris, 24 June 2005.

Roseneil, S. and Budgeon, S. (2002) ‘Caring about Friends: A New Agenda for Welfare Research’. ESRC CAVA International Seminar, University of Leeds, January 2002.

Roseneil, S. and Budgeon, S. (2002) `Cultures of Intimacy and Care beyond “the family”: friendship and sexual love relationships in the 21st century’. British Sociological Association Conference, University of Leicester, March 2002.

Roseneil, S. and Budgeon, S. (2002) `Cultures of Care and Intimacy beyond “the Family”: Friendship and Sexual/ Love Relationships in the 21st Century’. World Congress of Sociology, Brisbane, Australia, July 2002.

Roseneil, S. and Marshall, Y. (2004) ‘Local Landscapes of Global Resistance: The Methodology of the Common Ground Project’. Feminism Contesting Globalization Conference, University College Dublin, July 2004.

Roseneil, S. and Marshall, Y. (2004) `An Archaeology of Greenham: queering the memorializing of the Cold War’. Centre for Interdisciplinary Gender Studies, University of Leeds, November 2004.

Roseneil, S. and Rahman, M. (2001) `Our Collective Beckham Obsession: Some Sociological Musings’. ESRC New Sexualities Seminar, University of Leeds, December 2001.

Roseneil, S., Williams, F. and Martin, G. (2002) `Collective Interventions around Parenting and Partnering: The CAVA Project’. ESRC CAVA International Seminar, University of Leeds, November 2002.

Smart, C. (2000) ‘Children’s Moral Agency and Family Life’. STICERD Public Lecture, LSE, 24 February 2000.

Smart, C. (2000) ‘Children and the Transformation of Family Law’. The Rand Lecture, University of New Brunswick Law School, Canada, 23 March 2000.

Smart, C. (2000) ‘Objects of Concern? Children and Divorce’. Forum voor Gezinsbeleid (Seminar organised by the Dutch Family Council and Family Law Association, Utrecht, for Family Law Judges and practitioners), 8 June 2000.

Smart, C. (2000) ‘Law Reform in Children’s Cases: England and Australia. One Step Forward and Two Steps Back?’. Plenary Panel, 9th National Family Law Conference, Sydney, 6-7 July 2000.

Smart, C. (2000) ‘The Children Act 1989 – from the standpoint of children’. International Society of Family Law, 10th World Conference, Plenary Address, 9-13 July 2000.

Smart, C. (2000) ‘Divorce and Changing Family Practices in Post-Traditional Society’. Keynote Address, Australian Institute of Family Studies, Annual Conference, 24-26 July 2000

Smart, C. (2000) ‘Children’s Lives After Divorce’. Leeds Relate Annual General Meeting, 20 September 2000.

Smart, C. (2000) ‘Children and the Transformation of Family Law’. Special Lecture to inaugurate the new Faculty of Law and Social Sciences at the University of Manchester, 29 September 2000.

Smart, C. (2000) ‘Children’s Reflections on Post-Divorce Family Life’. ESRC Children 5-16 Research Programme, Final Conference, London, 20-21 October 2000.

Smart, C. (2000) ‘Children’s Perspectives on Post-Divorce Family Life’. Foundation Lecture to the New School of Social Science, University of Cardiff, 6 December 2000.

Smart, C. (2001) ‘Children and Post-Divorce Family Life’. Centre for Law and Society Seminar Series, University of Edinburgh, 25 January 2001

Smart, C. (2001) 'The Changing Status of Marriage in Family Law'. NPFI One Plus One Seminar, 31 January 2001.

Smart, C. (2001) ‘The Shared Parenting Solution?’. Socio-Legal Studies Association Conference, University of Bristol, 4-6 April 2001.

Smart, C. (2001) ‘The presumption in favour of co-parenting: A good idea?’. Centre for Research on Family, Kinship & Childhood, Practitioner Conference ‘The Trials, Tribulations and Triumphs of Co-Parenting, University of Leeds, 8 June, 2001.

Smart, C. (2001) ‘Children’s Voices’. Plenary Address, Family Courts of Australia 25th Anniversary Conference, Sydney, 26-29 July 2001.

Smart, C. (2001) ‘Hearing Children: How can we do it?’. Panel Session, Family Courts of Australia 25th Anniversary Conference, Sydney, 26-29 July 2001.

Smart, C. (2001) ‘Changing Family Relationships’. Plenary Address at National Family Law Conference, Christchurch, New Zealand, 5-8 October 2001.

Smart, C. (2001) ‘Out of the Mouths of Babes’. Panel Session at National Family Law Conference, Christchurch, New Zealand, 5-8 October 2001.

Smart, C. (2001) ‘Children and Participation’. Plenary Address, CAFCASS Regional Conference, Preston, 29 November 2001.

Smart, C. (2002) ‘Children as Makers of Meaning: Understanding Family Change’. Socio-Legal Studies Association Annual Conference, University of Wales, Aberystwyth, 3-5 April 2002.

Smart, C. (2002) ‘Divorce and the New Family: Perspectives from Children’. Keynote address to Parent Child 2002 Conference on Adolescence, organised by the National Family and Parenting Institute, Business Design Centre, Islington, London, 18-19 April 2002.

Smart, C. (2002) ‘“From Children’s Shoes to Children’s Voices” - The Children of Divorce: Parentage and Citizenship’. Institut d’Infància i Món Urbà, University of Barcelona, 19-20 September 2002.

Smart, C. (2002) ‘Changing Commitments: A Study of Close Kin after Divorce in England’. International Institute for Socio-Legal Studies, Onati, Spain, 26-27 September 2002.

Smart, C. (2003) ‘Researching Children’s Involvement in Mediation on Divorce’. Invited speaker to Children in Focus, NCH Action for Children Conference, Millbank Tower, London, 18 March 2003.

Smart, C. (2003) ‘Landscapes of Family Life: Commitment and Ambivalence’. Public Lecture on the Inauguration of the first Chair of Family Sociology, University of Helsinki, Finland, 2 September 2003.

Smart, C. (2003) ‘Living with Difference and Sameness: Culturally Diverse Families’. Plenary Address to the ‘Family Relationships and Intimacy in a Globalising World’ International Conference, Rauma, Finland, 4-6 September 2003.

Smart, C. (2003) ‘Equal Shares: Children’s Experience of Long Term Shared Residence’. Video recorded presentation to the Queensland Law Society and Family Law Practitioners’ Association Family Law Residential Conference, Surfers Paradise, Queensland, 5-6 September 2003.

Smart, C. (2003) ‘Changing Landscapes of Family Life: Parents, Children & Divorce’. Paper presented at the National Council for One Parent Families Annual Conference: The ‘problem’ of lone motherhood in the 21st Century – more of the same or different?, The Women’s Library, London, 27 November 2003.

- Smart, C. (2003) Ministerial Seminar on research on children and contact/residence disputes. In the presence of Margaret Hodge, Harriet Harman, Lord Filkin, Baroness Scotland, Baroness Hollis and Baroness Ashton, 3 December 2003.

Smart, C. (2004) ‘Children’s Experiences of Long-Term Shared Residence’. DAWN Project Annual Conference ‘Voices and Responses: Talking About Divorce and Separation, Sheffield, 26 February 2004.

Smart, C. (2004) ‘Changing Families: Parents, Children & Divorce’. Keynote speaker at the Families Australia ‘Globalisation, Families and Work’ Conference, Brisbane, 1– 2 April 2004.

Smart, C. (2004) ‘Children’s Experiences of Post-Divorce Family Life’. Children in Focus Symposium, co-hosted by The Attorney General’s Office and Family and Community Services, Canberra, 21 April 2004.

Smart, C. (2004) ‘Children Creating Narratives’. Keynote speaker, University of Sydney Law Faculty Family Law Seminar, 23 April 2004.

Smart, C. (2004) ‘Insights into Long-term Contact: Perspectives from Children’. Keynote address to CAFCASS Conference Evidence into Practice, 22 June 2004.

Smart, C. (2004) ‘Children’s Narratives of Post-Divorce Family Life’. Invited paper, Families Post Divorce Seminar, NTNU, Trondheim, Norway, 6-8 September 2004.

Smart, C. (2004) ‘Text, Talk and Audiotape’. Invited speaker at the Inaugural Symposium of the AHRB Centre for Law, Gender and Sexuality, University of Kent, 25 September 2004.

Smart, C. (2004) ‘Stuck in the Middle’. Address to the Labour Party Fringe Meeting hosted by NCH Action for Children. Panel member with Margaret Hodge, Minister for Children, and David Aaronovich, Guardian Journalist, 27 September 2004.

Smart, C. (2004) ‘Long term conflict in contact and residence cases’. Invited speaker to the NE Judicial Training Seminar, York County Court, 1 October 2004.

Smart, C. (2004) ‘Stuck in the Middle’. Address to the Conservative Party Fringe Meeting hosted by NCH Action for Children.  Panel member with Teresa May, Shadow Minister for the Family, 4 October 2004.

Smart, C. (2004) ‘Dealing with Long-Term Conflict: the perspective of children’. Aire Valley Contact Centres Annual General Meeting, Keighley, 13 October 2004.

Smart, C. (2004) ‘Why can’t they agree’. Lancashire Family Mediation Annual General Meeting, University of Central Lancashire, Preston, 10 November 2004.

Smart, C. (2004) ‘The Ethic of Justice Strikes Back: The new gender wars’. CAVA International Symposium on ‘Rethinking Care’, University of Leeds, 3-4 December 2004.

Smart, C. (2005) ‘Textures of Family Life: further thoughts on change and commitment’. Presented at Negotiating the Family: A postgraduate course, University of Tampere, 18 January 2005.

Smart, C. (2005) ‘Unmanageable Conflict: Parents, Children and Separation’. Judicial Studies Board, Annual Seminar for District Judges, London, 18 March 2005.

Smart, C. with Neale, B. (2003) ‘Changing Commitments: A study of close kin after divorce in England’. Socio-Legal Studies Association Annual Conference, Nottingham Trent University. 14-16 April 2003.

Smart, C. and Shipman, R. (2004) ‘Visions in Monochrome: Families, Marriage and the Individualization Thesis’. Presented at ESRC Seminar Series, Changing social norms, changing family law? Rights and responsibilities for partners, friends and carers, Nuffield Institute, December 2004.

Smart, C. and Shipman, R. (2005) ‘Same-Sex Partnership: What’s love got to do with it?’. Presented at Socio-Legal Studies Annual Conference, special stream organised by the Department for Constitutional Affairs. University of Liverpool, 30 March 2005.

Terry-Schuhmann, J. (2002) ‘Helper/helped relations in volunteer services for disabled older people’. Presentation to Young Voluntary Sector Researchers Conference, Institute for Volunteering Research, London, 2 December 2002.

Williams, F. (2000) ‘Care, Values and the Future of Welfare : Some Conceptual Conundrums’. Paper presented at the ESRC Seminar Series Post-modern Kinship, University of Leeds, 3 March 2000.

Williams, F. (2000) ‘A Research Programme in the Making: Care, Values and the Future of Welfare’. Presented at the JUC/ESRC Postgraduate Training Conference on ‘Evaluating Cutting-Edge Research’ , York University, 25-26 March 2000.

Williams, F. (2000) ‘New Principles for Welfare’ and ‘Care, Values and the Future of Welfare’. Papers presented at the Northwestern University, Chicago, USA, 23-24 May 2000.

Williams, F. (2000) ‘Travels with nanny; Destination Good-Enough: A Personal/ Intellectual Journey through the Welfare State’, Inaugural Lecture, University of Leeds, 11 May 2000.

Williams, F. (2000) Launch Talk. ESRC Research  Group for the Study of Care, Values and the Future of Welfare, University of Leeds, May 2000.

Williams, F. (2000) ‘The Presence of Feminism in the Future of Welfare’. Plenary Paper, Reinventing Feminism: Theory, Politics and Practice for the New Century, Goldsmiths College, University of London, May 2000.

Williams, F. (2000) ‘Towards a New Political Ethic of Care’. Plenary Paper, Gendering Ethics; the Ethics of Gender, University of Leeds, June 2000.

Williams, F. (2000) ‘New Principles for Welfare’. Paper presented to the Irish Social Policy Association Public Seminar, University College Dublin, 6 June 2000.

Williams, F. (2000) ‘In and Beyond New Labour: Balancing the Ethics of Care and Work’. Plenary Paper Critical Social Policy Conference, London, November 2000.

Williams, F. (2000) ‘Time to Care; Time not to Care’. Plenary speaker, ESRC 4th National Social Science Conference, London, November 2000. (Published http://www.esrc.ac.uk/newsociety)

Williams, F. (2000) ‘Feminism, Politics and Care’. Keynote paper, 10th Anniversary Conference of the Women’s Education, Research and Resource Centre, University College, Dublin, December 2000.

Williams, F. (2001) ‘Positioning the Welfare User in Research: from Passive Beneficiary to Active Welfare Subject’. Public Lecture for NOVA, Norwegian Institute of Social Research, Oslo, February 2001.

Williams, F. (2001) ‘Care, Values and the Future of Welfare’. Invited seminar, Social Policy Research Centre, University of New South Wales, Australia, March 2001.

Williams, F. (2001) ‘New Principles for Welfare’. Public Lecture sponsored by the Australian Council of Social Services, University of New South Wales, University of Sydney, Sydney, Australia, March 2001.

Williams, F. (2001) ‘A New Political Ethic of Care: Can it account for difference?’. Invited lecture, Social Relations of Disability Research Network, University of New South Wales, Australia, March 2001.

Williams, F. (2001) ‘Exploring the Active Welfare Subject’. Invited seminar, Macquarie University, Australia, April 2001.

Williams, F. (2001) ‘New Principles for Welfare’. The Brunel Lecture, Brunel University, May 2001.

Williams, F. (2001) ‘Trends in Women’s Employment, Domestic Service and Female Migration in Europe: an Uncomfortable Menage a Trois?’. ‘Solidarity between the sexes and generations: transformations in Europe’, Colloquium of the Royal Academy of Arts and Sciences, Amsterdam, The Netherlands, June 2001.

Williams, F. (2001) ‘Changing Families, Changing Values’. Keynote Speaker, Launch of Parents’ Week, National Family and Parenting Institute, London, 22 October 2001.

Williams, F. (2001) ‘Conceptualising Agency in Welfare Research’, ‘Translating ‘family values’ into moral agency in CAVA research’ and ‘Operationalising moral agency in the CAVA research’. Keynote Speaker, 3 papers to Norwegian Social Research Council Seminar ‘Agency Perspectives in Welfare and Marginalisation Research’, 30-31 October 2001.

Williams, F. (2001) ‘Identity Politics and the Politics of Justice’.  Panel presentation at Gender and Citizenship within and across Borders Symposium at the Ledamotshuset, Stockholm, funded by the Bank of Sweden, October 2001.

Williams, F. (2001) ‘Towards a New Political Economy of Care’. Staff Seminar, Dept. of Sociology and Social Policy, University of Newcastle, 7 November 2001.

Williams, F. (2001) ‘Towards a New Political Economy of Care’. Staff Seminar, Dept. of Sociology and Social Policy, Unversity of Greenwich, 19 November 2001.

Williams, F. (2002) ‘Changing Lives in a Changing World’. Keynote Lecture, ParentChild 2002, an International Conference on Adolescence, organised by the National Family and Parenting Institute, Business Design Centre, Islington, London, UK, 18-19t April 2002.

Williams, F. (2002) ‘Migration, Care and Welfare Regimes’. Ercomer Lecture, University of Utrecht, The Netherlands, 13 May 2002.

Williams, F. (2002) ‘Ethnicity, Migration and the Analysis of Welfare States’. Faculty of Social Sciences Postgraduate Lecture, University of Stockholm, Sweden, 22 October 2002.

Williams, F. (2002) ‘The New Focus on Welfare Subjects and Agency: the theoretical challenges’. Seminar of the Welfare Research Programme of the Nordic Council of Ministers on Active Citizenship and Marginality in a European Context, Teleborg Castle, Växjö University, Sweden, 24-25 October 2002.

Williams, F. (2003) ‘The Changing Contours of Care and Intimacy: Towards a New Political Ethic of Care'. Public Lecture for the Centre for Policy Studies in Education, University of Leeds, 23 January 2003.

Williams, F. (2003) ‘Family Values or an Ethic of Care?’. University of Oxford, Dept of Social Policy and Social Work, 24 February 2003.

Williams, F. (2003) ‘The Changing Contours of Care and Intimacy: Family Values or an Ethic of Care?’. University of Loughborough, Department of Social Sciences, 7 March 2003.

Williams, F. (2003) ‘The struggle not to fall between two stools: gender, race and migration in EU lobbying politics’. National Feminisms in a Transnational Arena: The European Union and Gender Politics, Conference at The European Center, University of Wisconsin, Madison, USA, 4-6 April 2003.

Williams, F. (2003) ‘Reflections on Researching Social Policy’. Keynote Speaker, Social Policy Association and JUC Postgraduate Conference, University of Birmingham, 25 April 2003.

# Williams, F. (2003) ‘The Politics of Parenting and Partnering in Local Support Groups’ presented to the CAVA Initial Findings Seminar, University of Leeds, 23 May 2003.

Williams, F. (2003) ‘The Local Politics of Parenting and Partnering’. Paper presented to the Social Policy Association Annual Conference, Teesside University, Middlesborough, 16-18 July 2003.

Williams, F. (2003) ‘Work/Life Balance to ‘Forward Left’. Public meeting organised by Catalyst, Leeds Civic Hall, 11 October 2003.

Williams, F. and Sevenhuijsen, S. (2003) ‘Recent parenting policies: an analysis with the ethic of care’. Paper for the Institute of Education seminar ‘Employment and Care’, Cumberland Lodge, 27-28 October 2003.

Williams, F. (2004) Presentation to the EU Advisory Group on Social Sciences and Humanities, Gender, equality, citizenship and governance, Maison des Sciences de l’Homme, Paris, 19 March 2004.

Williams, F. (2004) ‘Changing Values…Changing Families’. Keynote presentation National Family and Parenting Institute International Conference ‘Family Futures’, Queen Elizabeth II Conference Centre London, 17-18 June 2004.

Williams, F. (2004) Presentation to All-Party Group on Social Sciences, House of Commons, Westminster, London, 23 June 2004.

Williams, F. (2004) Launch of Rethinking Families, Keynote, Royal Institute of Chartered Surveyors, London, 23 June 2004.

Williams, F. (2004) ‘Rethinking Families; Rethinking Care’. Keynote lecture, Irish Social Policy Association Annual Conference, Dublin, 16-17 September 2004.

Williams, F. (2004) Invited participant, Renewing Social Democracy Seminar organised by Compass and Catalyst, Egham, 3-4 September 2004.

Williams, F. (2004) ‘Do Communities Care? Care, Values and the Future of Welfare’. Concept Public Lecture, University of Edinburgh, 27 October 2004.

Williams, F. (2004) ‘Work, Family and Care and the Future of Social Policy in Europe’. Plenary paper presented to the Conference of STAKES Work and Family Project, Hilton Hotel, Helsinki, 10 November 2004.

Williams, F. (2004) Opening Talk and discussant to Joan Tronto ‘Vicious Circles of Privatized Care’. Paper presented at Rethinking Care Relations, Family Lives and Policies, CAVA International Symposium, Weetwood Lodge, Leeds, 3-4 December 2004.

Williams, F. (2004) ‘Rethinking families; rethinking care; rethinking policy’. Paper for ESRC Seminar Series: Changing social norms, changing family law? Seminar 1: Rights and responsibilities for partners, friends and carers, Institute of Education, London, 10 December 2004.

Williams, F. (2005) ‘Changes in families and personal relationships: the implications for a political ethic of care’. Public Lecture, University College Cork, 24 January 2005.

Williams, F. (2005) ‘The Practical and Political Ethics of Care and the Implications for Child Welfare’. Staff seminar, Huddersfield University, 27 January 2005.

Williams, F. (2005) ‘Making sense of changing family lives and personal relationships’. Keynote to Delivering Services for Children and Young People - Evidence from Research and Best Practice, ESRC LARCI seminar, London, 18 March 2005.

Williams, F. (2005) Plenary paper, Social  Policy Association Annual Conference, University of Bath, 27-29th June 2005.

Williams, F. and Deacon, A. (2004) ‘Personal qualities and Civic Virtues: Care, Values and the Future of Welfare’. Social Policy Association Annual Conference, Nottingham University, 13-15 July 2004.

Williams, F. and Deacon, A. (2004) ‘Personal Qualities and Civic Virtues: Care, Values and the Future of Welfare’. Paper presented to the Annual Conference of the European Network for Social Policy Analysis, University of Oxford, 9-11 September 2004.

Williams, F. and Duncan, S. (2003) ‘The Contours of Care and Intimacy: People, Places and Policy’. Seminar at The Office of the Deputy Prime Minister, London, 19 February 2003.

Williams, F. and Gavanas, A. (2003) ‘New Masters / New Servants? The social relations of gender, migration and care’. Paper presented at the VI European Sociological Association Conference“Ageing Societies, New Sociology” Research Network:“Gender Relations in the Labour Market and the Welfare State”, Murcia, Spain, 21-25 September 2003.

Williams, F. and Gavanas, A. (2004) ‘The diversity of care practices and strategies – within countries and across them’. Paper to  Workshop on Transformations of Work: Gendered Labour and the shifting boundaries between paid and unpaid work, European University Institute, Florence, Italy, 22-23 November 2004.

Williams, F. and Irwin, S. (2002) ‘Understanding Social Values and Social Change: the Case of Care, Family and Intimacy’. Paper presented to the European Social Policy Research Network Annual Conference, University of Tilburg, the Netherlands, 29-31 August 2002.

Williams, F. Roseneil, S. and Martin, G. (2002) ‘Interventions on the Terrain of Care and Intimacy: Theorising the Politics of Parenting and Partnering and Welfare in Contemporary Britain’. World Congress of Sociology, Joint Session of RC 47 and 19: Brisbane, Australia, 7-13 July 2002.

Forthcoming Conference Papers

Williams, F. (2005) ‘Commitments to Care: Moving from Public Responsibility for Care to Care as a Public Value’ Plenary Paper, Social Policy Association Conference 2005, Bath University, 27-29 June 2005.  (http://www.york.ac.uk/depts/spsw/spa/conf.htm#)

Williams, F. (2005) ‘Intersecting Issues of  Gender, ‘Race’ and Migration in the Changing Care Regimes of EU, Sweden and Spain’, paper  to be presented to Retheorizing Welfare States: Restructuring States, Restructuring Analysis, RC19 ISA Annual Conference, Northwestern University, Chicago.

4. Journal Articles

Ackers, H. L. (2000a) ‘From ‘Best Interests’ to Participatory Rights: Children’s Involvement in Family Migration Decisions’, Child and Family Law Quarterly, 12(2), pp 167-184.

Ackers, H. L. (2000b) ‘The Development of Affirmative Action in European Commission Policy-Making: Assessing the Risks’, Journal of Social Welfare and Family Law, 22(3), pp. 347-360.

Ackers, H. L. (2000c) 'Citizenship, Retirement and Mobility in the European Union’, Journal of Social Welfare and Family Law. 22(4), pp. 477-491.

Ackers, H.L. (2004a) ‘Managing Work and Family Life in Peripatetic Careers: The Experiences of Mobile Women Scientists in the European Union’. Women’s Studies International Forum, 27(3), pp. 189-201.

Ackers, H. L. (2004b) ‘Citizenship, Migration and the Valuation of Care in the European Union’, Journal of Ethnic and Migration Studies. 30(2), pp. 373-396.

Ackers, H. L. (2005d), ‘Promoting Scientific Mobility and Balanced Growth in the European Research Area’, Innovation: The European Journal of Social Science Research, 18(3).

Ackers, H. L. & Dwyer, P. (2004) ‘Fixed Laws, Fluid Lives: the citizenship status of post-retirement migrants in the European Union’. Ageing and Society. 24, pp. 451-475.

Ackers, H. L. and Gill, B. (2005), ‘Attracting and Retaining ‘Early Career’ Researchers in English Higher Education Institutions’, Innovation: The European Journal of Social Science Research, 18(3).

Budgeon, S. and Roseneil, S. (2004) `Editors’ Introduction: Beyond the Conventional Family’. Current Sociology. 52(2), pp 127-134.

Deacon, A. (2000) 'Learning from the USA? The Influence of American ideas upon 'New Labour' thinking on welfare reform'. Policy and Politics. 28(1), pp 5-18. ISBN 1305 5736.

Deacon, A. (2002f) ‘Echoes of Sir Keith? New Labour and the Cycle of Disadvantage’, Benefits, Vol. 10, No. 3, pp. 179-184.

Deacon, A. (2003d) ‘Ending consensus as we began to know it; Welfare reform and the Republicans after 2002’. Social Policy and Society. 2 (2), pp 171-175.

Deacon, A. (2003e) ‘Levelling the playing field, activating the players: New Labour and the cycle of disadvantage’. Policy and Politics. 31 (2), pp 123-137.

Deacon, A. (2004c) 'Justifying conditionality: The case of anti-social tenants'. Housing Studies. 19(6), pp 911-26.

Deacon, A. (2004d) ‘Different interpretations of agency within welfare debates’. Social Policy and Society. 3(4), pp 447-455.

Deacon, A. and Williams, F. (2004) ‘Implications for Welfare Policies and Practices’. Social Policy and Society. 4(1), pp 385-390.

Duncan, S. (2002a) ‘Policy Discourses in “Reconciling Work and Life” in the EU’. Social Policy and Society. 1(4), pp 305-314.

Duncan, S. (2005b) ‘Mothering, class and rationality’. Sociological Review. 53(2), pp 50-76.

Duncan, S. and Barlow, A. (2000a) 'New Labour's Communitarianism, Family Law & the Rationality Mistake' Part 1. Journal of Social Welfare & Family Law. 22(1), pp 23-42.

Duncan, S. and Barlow, A.  (2000b) 'New Labour's Communitarianism, Family Law & the Rationality Mistake' Part 2. Journal of Social Welfare & Family Law. 22(2), pp 129-143.

Duncan, S. and Edwards, R. (2001) 'Alleinerziehende mütter, moralische rationalität und der rationalitätsfehler von New Labour'. Feministsche Studien.

Duncan, S. and Irwin, S. (2004)  ‘The social patterning of values and rationalities: mothers’ choices in combining caring and employment’. Social Policy and Society. 3(4), pp 391-400.

Duncan, S. and Smith D. (2001a) 'Families and localities: the geography of partnering and parenting'. Anthropolis. 3. Available at:  http://www.anthopolis.de.

Duncan, S. and Smith D (2001b) 'Patterns of partnering and parenting in Yorkshire and Humberside'. Regional Review. 11(1), pp 17-18.

Duncan, S. and Smith, D. (2002a) ‘Family Geographies and Gender Cultures’. Social Policy and Society. 1(1), pp 21-34.

Duncan, S. and Smith, D. (2002b) ‘Geographies of Family Formations: Spatial Differences and Gender Cultures in Britain’. Transactions of the Institute of British Geographers. 27(4), pp 471-493.

Available at:

http://www.ingentaconnect.com/content/bpl/tran/2002/00000027/00000004;jsessionid=7og9pmq1kglhk.victoria

Duncan, S. and Strell, M. (2001) 'Lone mothers, ideal type care regimes and the case of Austria’. Journal European Social Policy. 11(2), pp 149-164.

Duncan, S. and Strell, M. (2004) ‘Combining lone motherhood and paid work: the rationality mistake and Norwegian social policy’. Journal European Social Policy. 14(1), pp 41-54.

Duncan, S. and Williams, F. (2002b) ‘Introduction’. Special Issue of Critical Social Policy: New Divisions for Labour: Alternatives for Caring and Working. 22 (1), pp 5-11. ISSN 0261-0183.

Duncan, S. and Williams, F. (2002c) ‘Introduction: New Divisions of Labour? Alternatives for Caring and Working’. Critical Social Policy - Special Issue. 22(1), pp 5-11.

- Duncan, S., Edwards, R., Allred, P. and Reynolds, T. (2003) ‘Motherhood, paid work and partnering:, values and theories’. Work, Employment and Society. 17(2), pp 309-30.

Duncan, S., Edwards, R., Allred, P. and Reynolds, T. (2004) ‘Mothers and childcare: policies, values and theories’. Children and Society. 18(4), pp 245-65.

- Flowerdew, J. and Neale, B. (2003) ‘Trying to stay apace: Children with multiple challenges in their post divorce family lives’. Childhood. 10(2), pp 147-161.

Flowerdew, J., Neale, B. and Smart, C. (2004) ‘Shared Residence: Not a magic solution’. Solicitors Family Law Association Review. January, 104, pp 16-17

Gavanas, A. (2004b) ‘Domesticating masculinity and masculinizing domesticity in contemporary U.S. fatherhood politics’. Social Politics. 11, pp 247-266.

Hollway, W. (2001b)  ‘The psycho-social subject in “evidence-based practice”‘. Journal of Social Work Practice. 15(1), pp 9-14.

Hollway, W. (2001c) ‘Critical psychology: Inside the belly of the beast’. International Journal of Critical Psychology. Launch Issue, pp 110-113.

Hollway, W. (2001d) ‘From motherhood to maternal subjectivity’. International Journal of Critical Psychology. 2, pp 13-38.

Hollway, W (2004d) ‘Introduction’. Psychosocial Research, Special issue of International Journal of Critical Psychology. 10, pp 5-12.

Hollway, W. (2005a) ‘An appropriate research paradigm for evaluating psychoanalytically - informed practices’. International Journal of Infant Observation and its Applications, 7(2/3), pp. 12-26

Hollway, W. and Jefferson, T (2001) ‘Free Association, narrative analysis and the defended subject: the case of Ivy’. Narrative Inquiry. 11(1), pp 103-22.

Hollway, W. and Jefferson, T (2002) ‘Heterosexual relating, unconscious intersubjectivity and fear of crime’. Journal of Psychoanalysis, Culture and Society. 7(2), pp 196-201.

Irwin, S. (2000) ‘Reproductive Regimes. Changing relations of inter-dependence and fertility change’. Sociological Research Online. 5(1). Available at: http://www.socresonline.org.uk/5/1/irwin.html

Irwin, S. (2003) ‘Interdependencies, values and the reshaping of difference: gender and generation at the birth of twentieth-century modernity’. British Journal of Sociology. 54(4), pp 565-84.

Irwin, S. (2004) ‘Attitudes, care and commitment: pattern and process’. Sociological Research Online. 9(3).  Available at: http://www.socresonline.org.uk/9/3/irwin.html

Irwin, S. and Bottero, W. (2000) ‘Market Returns? Gender and theories of change in employment relations’. British Journal of Sociology. 51(2), pp 261-80.

Irwin, S. and Bottero, W. (2003) ‘Locating difference: class, ‘race’ and gender, and the shaping of social inequalities’. The Sociological Review. 51(4), pp 433-62.

Martin, G. (2000) 'New Age Travellers'. Sociology Review, 9(4),  pp 2-5.

Mason, J. (2004a) ‘Personal narratives, relational selves: residential histories in the living and telling’. The Sociological Review. 52(2), pp 162-179.

Mason, J. (2004b) ‘Managing kinship over long distances: the significance of “the visit”’. Social Policy and Society. 3(4), pp 421-429.

Neale, B. (2001) ‘Family Values: Children’s reflections on Post Divorce Family Life’. Childrenz Issues (NZ). 5(1), pp 6-9.

- Neale, B. (2002) ‘Dialogues with Children: Children, Divorce and Citizenship’. Childhood. 9(4), pp 455-475.

Neale, B. and Flowerdew, J. (2003) ‘Time, Texture and Childhood: The Contours of Longitudinal Qualitative Research’. International Journal of Social Research Methodology: Theory and Practice. 6(3), July-Sept, pp 189-199.

Neale, B. and Smart, C. (2000a) ‘Post Divorce Childhoods: Perspectives from Children’. Seen and Heard (Journal of the National Association of Guardians Ad Litem & Reporting Officers. 10(2), pp 31-36.

Neale, B. and Smart, C. (2000b) ‘Separate Lives’. Community Practitioner. 73(6) June, pp 635-6.

Neale, B., Flowerdew, J. and Smart, C. (2003) ‘Drifting towards Shared Residence?’. Family Law. 33, December, pp 904-908.

Roseneil, S. (2000e) `Postmoderneja seksuaalisuuden muutoksia: Queer viitekehyksena ja vaikutteena’ (`Postmodern Transformations of Sexuality: Queer Frameworks and Queer Tendencies’). Naistutkimus: kvinnoforskning (Finnish Journal of Women’s Studies). 2, pp 28-43.

Roseneil, S. (2000f) `Queer Frameworks and Queer Tendencies: Towards an Understanding of Postmodern Transformations of Sexuality’. Sociological Research Online. 5(3), pp 1-19.

Available at: http://www.socresonline.org.uk/5/3/roseneil.html

Roseneil, S. (2001d) `Speaking of Sexuality and Subcultures: A Conversation between Judith Halberstam and Sasha Roseneil’. International Feminist Journal of Politics. 3(3), pp 423–434.

Roseneil, S. (2003a) `Queer Frameworks and Queer Tendencies: Towards an Understanding of Postmodern Transformations of Sexuality’. Kvinder, Køn & Forskning (Danish Journal of Gender Studies), 1, pp 18-34.

Roseneil, S. (2003b) `We’d Rather Be with Friends’. New Statesman,.15 December 2003, pp. 80-81.

Roseneil, S. (2004b) ‘Why We Should Care About Friends: An Argument for Queering the Care Imaginary in Social Policy’. Social Policy and Society. 3(4), pp 409-419.

Roseneil, S. and Budgeon, S. (2004) ‘Cultures of Intimacy and Care Beyond ‘the Family’: Personal Life and Social Changes in the Early 21st Century’. Current Sociology. 52(2), pp 135-159.

Roseneil, S. and Hogan, L. (2001b) `Editorial: Gendering Ethics / The Ethics of Gender’. Special Issue of Feminist Theory: An International Interdisciplinary Journal, 2(2), pp 115-118.

Roseneil, S. and Hogan, L. (2003b) `Ethical Relations – agency, autonomy, care’. Feminist Theory: An International Interdisciplinary Journal. 4(2), pp 115-118.

Roseneil, S. and Williams, F. (2004a) ‘Introduction to Special Issue: New Contexts for Collective Action: The Politics of Parenting, Partnering and Participation’. Special Issue of Social Politics: International Studies in Gender, State and Society.11(2), pp 147-153.

Roseneil, S. and Williams, F. (2004b) `Valeurs publiques en matiere de parentalite et de couple’. Cahiers Marxistes. 228(Aug – Sept), pp 77-98.

Smart, C. (2000d) ‘The Children Act 1989: The English Experience’. 9th National Family Law Conference Handbook July 2000. Melbourne: Television Education Network Pty Ltd. Pp 199-212.

Smart, C. (2000e) 'Reconsidering the Recent History of Child Sexual Abuse, 1910-1960’. Journal of Social Policy. 29(1), pp 1-17.

Smart, C. (2000f) ‘Stories of Family Life: Cohabitation, Marriage and Social Change’. Canadian Journal of Family Law. 17(1), pp 20-53.

Smart, C. (2000g) ‘Divorce and changing family practices in a post-traditional society’. Family Matters (Publication of the Australian Institute of Family Studies, Melbourne). 56, pp 10-19.

Smart, C. (2001) ‘Changing Childhoods, Changing Families: International Perspectives on Divorce and Separation’. Family Today – The Family Policy and Research Journal. 2, pp 12-14.

Smart, C. (2002) ‘From Children’s Shoes to Children’s Voices’. Family Court Review: An International Journal. 40(3), pp 305-317.

Smart, C. (2003c) ‘Towards an Understanding of Family Change: Gender Conflict and Children’s Citizenship’. Australian Journal of Family Law. 17, pp 1-17.

Smart, C. (2003d) ‘New Perspectives on Childhood and Divorce: an introduction’. Childhood: A global journal of child research. 10(2), pp 123-9. issn 0907-5682.

Smart, C. (2004a) ‘Equal Shares: Rights for Fathers or Recognition for Children’. Critical Social Policy. 24(4), pp 484-503.

Smart, C. (2004b) ‘Changing Landscapes of Family Life: Rethinking Divorce’. Social Policy and Society. 3(4), pp 401-8.

Smart, C. (2004c) ‘Retheorising Families’. Review Essay, Sociology. 38(5), pp 1037-42.

Smart, C. and Neale, B. (2000a) ‘It’s my life too: Children’s perspectives on post-divorce parenting’. Family Law. March 2000, pp 163-169.

Smart, C. and Neale, B. (2000b) ‘Post Divorce Childhoods: Perspectives from Children’. Seen and Heard (Journal of the National Association of Guardians Ad Litem & Reporting Officers). 10(2), pp 31-36.

Smart, C. and May, V. (2004a) ‘Residence and Contact Disputes in Court’. Family Law. 34, pp 1-7.

Smart, C. and May, V. (2004b) ‘Silence in Court?: Hearing children in residence and contact disputes’. Child and Family Law Quarterly. 16(3), pp 305-16.

Smart, C. and May, V. (2004c) ‘Why can’t they agree: the underlying complexity of contact and residence disputes’. Journal of Social Welfare and Family Law. 26(4), pp 1-14.

Smart, C. and Shipman, R. (2004) ‘Visions in Monochrome: Families, Marriage and the Individualization Thesis’. British Journal of Sociology. 55(4), pp 491-509.

Available at: http://www.blackwell-synergy.com/toc/bjos/55/4

Williams, F. (2001c) ‘In and beyond New Labour: towards a new political ethic of care’. Critical Social Policy. 21(4), pp 467-493.

Williams, F. (2002) ‘The Presence of Feminism in the Future of Welfare’. Economy and Society. 31(4), pp 502-519.

Williams, F. (2004d) ‘Hoivan uudelleenarviointia sosiaalipolitiikassa’. Janus. 12(1), pp 6-24.

Williams, F. (2004e) ‘What matters is who works: commentary on the Green Paper Every Child Matters’. Critical Social Policy. 24(3), pp 406-427.

Williams, F. (2004f) ‘The Local Politics of Parenting and Partnering’. Social Policy and Society. 4(1), pp 431-438.

Williams, F. and Roseneil, S. (2004b) ‘Public Values of Parenting and Partnering: Voluntary Organisations and Welfare Politics in New Labour’s Britain’. Social Politics: International Studies in Gender, State and Society.11(2), pp 181-216.

In Press 2005 and forthcoming

Ackers, H. L. (2005c), ‘Moving People and Knowledge: Scientific Mobility in the European Union’. International Migration. In press.

Ackers, H. L. and Oliver, L. (2005), ‘The Effect of Regulation in the Area of Fixed Term Contracts on the Recruitment and Retention of Early Career Researchers in the UK’. International Studies of Management and Organization.

Hines, S. (2005b) ‘Intimate Transitions: Transgender Practices of Partnering and Parenting’. Sociology.

Hines, S. (2005c) ‘Tran(s)sexualities: Negotiating Sexual Identity, Desire and Practice through Gender Transition’. Sexualities.

Hollway, W. and Jefferson, T. (2005a) ‘Panic and perjury: A psycho-social exploration of agency’. British Journal of Social Psychology, 44.

Hollway, W. and Jefferson, T. (2005b) ‘But why did Vince get sick?’ Response to two discussants of ‘Panic and Perjury’. British Journal of Social Psychology, 44.

Neale, B (2005) Re-Tying the Knot? Relationality and Re-partnering after Divorce. Sociology.

Smart C. (2005b) ‘Textures of Family Life: Further thoughts on change and commitment’. Journal of Social Policy, Vol 34(4), pp.1- 16.

Smart, C. (2006) ‘Children’s Narratives of Post-Divorce Family Life: From individual experience to an ethical disposition’. The Sociological Review.

Williams, F. (2005d) ‘Towards a good enough life: developing a political ethic of care’. Soundings: a journal of politics and culture.

5. Newspaper, Newsletter or Bulletin Article

5.1. By CAVA Members

Phillips, A. (2003) 'Children before Money'. The Guardian, 30 July 2003.

- Phillips, A. (2003) ‘A Child is not a Home’. The Guardian, 17 October 2003.

Roseneil, S. (2000) `Out of the Kitchen’ in Women of the Year Lunch and Assembly Millennium Festival of Women’s Work Programme, pp.34-7, 2000.

Roseneil, S. (2004) `Towards a More Friendly Society?’ The Edge Issue 15, pp.12-14, March 2004.

Smart, C. (2004) ‘Families in Transition’ in Private Lives, Spring, Issue 3, 2004.

Williams, F. (2000), ‘Care Values and the Future of Welfare’, Leeds University Review, 14, p. 18..

Williams, F. (2001) ‘New Principles for Welfare’ Impact, Magazine of the Australian Council of Social Services, October, 2001.

Williams, F. (2002) ‘Love, Care, Intimacy, Children and Tony Blair’, Times Higher Education Supplement, September 27, pp. 22-23.

Williams, F. (2003) Interview, Leeds University Review, Autumn.

Williams, F. (2004) ‘How mothers juggle care and work’ Family Today, March 2004.

5.2. CAVA Press Releases

Social Policy Must Adapt to New ‘Family Values’, Wednesday 16 June 2004.

Contact in Context – Post-Divorce Family Lives, Tuesday 15 June 2004.

CAVA Welcomes Family Policy Debate, Monday 5 April 2004.

CAVA Director Receives New Year Honour, Tuesday 6 January 2004.

Talking Home Truths in Leeds, Monday 17 November 2003.

Shared Residence Not a 'Magic Solution', Friday 17 October 2003.

5.3. Articles connected to CAVA research

The Guardian, 28 February 2000, ‘Off cuts: Column on research on children and divorce’. (Taylor, L.)

The Observer Review, 5 March 2000, ‘Sharing and Caring’: Full page report on research findings on children and divorce. (Hill, D.)

Sydney Morning Herald, 26 July 2000, ‘Divorce not all bad news for children’.

Times Higher Education Supplement: Millenium Magazine, 22 December 2000, ‘Study of Care, Values and the Future of Welfare’.

ESRC Social Sciences Newsletter 47, January 2001, ‘New Society or New Individualisation?’.

Irish Times, 15 June 2001, ‘The trouble fathers have with talking about love’. (Ferguson, H.)

The Guardian, 26 Sept 2001, Full page article on parenting page regarding London conference and launch of book on children and divorce by C. Smart and B. Neale. (Freely, M.)

The Guardian, 26 November 2001, ‘Big rise in support for unmarried parents’. (Carvel, J.)

The Guardian, 17 October 2003, 'Why a child is not a house'. (Phillips, A.)

The Independent, 20 October 2003, 'Not all fathers deserve the right to be parents'. (Alibhai-Brown, Y.)

Yorkshire Post, 20 October 2003, 'Divorce brings home-share difficulties'.

The Sydney Morning Herald, 22 November 2003, ‘Middle ground’. (Martin, L.)

The Guardian, 12 December 2003, 'Friends are the new family'. (Phillips, A.)

The Guardian, 3 January 2004, ‘Tories new credo has US roots'. (Watt, N.)

The Sunday Times, 8 February 2004 ‘Justice for the fathers but what about the kids?’. (Driscoll, M.)

The Age, 20 March 2004, ‘Children give 50-50 parenting mixed report’.

The Sydney Morning Herald, 20 March 2004, ‘Children’s views vital for parent sharing to work’.

The Guardian, 27 March 2004, ‘Location, location, orientation’. (Bindel, J.)

The Sydney Morning Herald, 27 March 2004, ‘New etiquette of the step-by-step parent’. (Horin, A.)

The Observer, 13 June 2004, 'Most "problem kids" go on to thrive'. (Bright, M.)

PA News, 16 June 2004, 'Southern Mothers ‘More Likely to Quit Full-Time Work’'. (Linden, M.)

London Evening Standard, 16 June 2004, 'Staying Apart for Sake of Children'. (Frean, A.)

London Evening Standard, 16 June 2004, 'Mothers in South More Likely to Leave Their Jobs'. (Hopkirk, E.)

The Daily Mail, 17 June 2004, 'Highflying Mothers Who Would Rather Stay at Home'. (Doughty, S.)

The Journal (Newcastle), 17 June 2004, 'Mums Who Quit Work'.

Brighton Evening Argus, 18 June 2004, 'Staying Mum' (Leader).

Brighton Evening Argus, 18 June 2004, 'Would You Quit Work For Baby?'.

The Daily Mail, 18 June 2004, '1 in 5 Babies Grow Up With No Fathers'. (Doughty, S.)

The Guardian, 18th June 2004, 'Parenting Helplines get £6m Boost'. (Jones, S.)

The Daily Mail, 19 June 2004, 'The Gay Myth'. (Condron, S.)

Financial Times, 21 June 2004, 'Stepfamilies and Older People on the Increase'. (Daneshku, S.)

The Independent, 21 June 2004, 'Little Britons: Smart, Wealthy…Unhappy'. (Brown, J.)

Community Care Magazine, 24 June 2004, 'Labour Must Regain Universal Principles'. (Roberts, Y.)

The Evening Chronicle, 24 June 2004, 'North Mums Go Back to Full-Time Work'.

PA Features, 24 June 2004, 'These Days, a Woman’s Place is No Longer Just in the Home - She Works, Just Like a Man'. (Salmon, L.)

Blackpool Gazette, 26 June 2004, 'Most New Mums Decide to go Back to Work'.

Bolton Evening News, 26 June 200, 'A Mother's Dilemma: To Work or Not to Work'.

Bradford Telegraph and Argus, 26 June 2004, 'Academic Produces Gay Map of Britain'. (Pallister, K.)

Huddersfield Examiner, 26 June 2004, 'Backing Family Life' (and Leader).

York Evening Press, 26 June 2004, 'Women Try to Work it Out'.

Burton Daily Mail, 29 June 2004, 'Working Mums, Working Wonders'.

Portsmouth News, 29 June 2004, 'Kids or Career - It's Not an Easy Decision'.

The Guardian: Analysis, 30 June 2004, 'Mother Knows Best'. (Phillips, A.)

Mansfield and Ashfield Recorder, 1 July 2004, 'Women Working in the Family'.

The Observer: Comment, 4 July 2004, 'Home Alone? No Planning a Party'. (Roberts, Y.)

The Observer: Review , 4 July 2004, 'Happy Ever After – On Separate Floors'. (Neustatter, A.)

The Reporter, 5 July 2004, 'Caring and diverse: a wake-up call for politicians about the modern family'.

The Gloucestershire Echo, 6 July 2004, 'Should Mothers Be Returning to Work?'.

Kettering Evening Telegraph, 6 July 2004, 'The Last Word'.

Northampton Chronicle and Echo, 6 July 2004, 'The Last Word'.

Southern Daily News, 6 July 2004, 'Keeping Mum'.

The Observer: Comment, 11 July 2004, 'Children Have Rights, Too'. (Riddell, M.)

Oldham Evening Chronicle, 13 July 2004, 'Working Wonders'.

Nottingham Recorder, 15 July 2004, 'Coping with Full-Time Motherhood'.

Telford Journal, 15 July 2004, 'A Tough Decision for New Mums'.

Yorkshire Post, 16 July 2004, 'Justice 4 Children'.

Aberdeen Press and Journal, 16 July 2004, 'Working Mums'.

Derby Express, 23 July 2004, 'Should Mums Work or Not?'.

Newcastle-Under-Tyne Journal, 3 August 2004, ‘Research into Working Mums Doesn’t Help’.

House of Fraser Seasonal, 18 August 2004, ‘Trading Places’.

Yorkshire Post, 3 September 2004, ‘Society needs to find a different way of living, concludes research report’. (Benfield, C.)

The Times, 20 September 2004, ‘Why children are so grown up about divorce’. (Frean, A.)

The Times, 21 September 2004, ‘One heart, two homes’. (Brayfield, C.)

The Times: Body and Soul, 25 September 2004, ‘Split Focus on Kids’. (Godson, S.)

Guardian Special Report: The World in 2020, 25 September 2004, ‘Family Fortunes’. (Bunting, M.)

Community Care, 7 October 2004, ‘Rethinking Families’. (Wilson, L.)

The Guardian – Analysis, 13 October 2004, ‘Most Fathers Get Justice’. (Phillips, A.)

Boston Globe, 12 December 2004, ‘Violence towards gays and lesbians escalates in the UK’. (Leibowitz, S.)

Daily Mail, 20 December 2004, ‘The Step Generation’.

Western Mail, 20 December 2004, ‘Stressful times for divorcees’ children who are ‘being shared’.

Scunthorpe Evening Telegraph, 20 December 2004, ‘Stressful for Youngsters’.

The Times, 17 May 2005, ‘Meet the LATS – decsendants of the Sixties’

The Reporter, 6 June 2005, In the News’.

6. Working Paper or Report

6.1. Miscellaneous

Ackers, H.L. (2000) ‘The participation of women researchers in the TMR programme of the European Commission: An Evaluation’. European Commission Research Directorate

Ackers, H. L. (2001) ‘The participation of women researchers in the TMR programme of the European Commission: An Evaluation’. Brussels European Commission (DG12).

Duncan, S. (2003) ‘Mothers, Care and Employment: Values and Theories’, CAVA Working Paper 1, University of Leeds. Available at: www.leeds.ac.uk/cava

Gerodetti, N. (2004) ‘Disabling Femininities, Homosexuality & Eugenics: Modern Swiss Sexualities'. CAVA Working Paper 2, University of Leeds. Available at: www.leeds.ac.uk/cava

Hines, S. (2002) "Absent Subjects: Feminist Discourse and Trans Masculinities" in Purnell, A. (ed.) 'Gendys 2002: Report of the Seventh Gender Dysphoria Conference', Gendys Publishing.

Roseneil, S. (2001) Developing Mechanisms for Accountability in Women’s Equality Work, Centre for Interdisciplinary Gender Studies Research Report for Leeds City Council, pp.75, 2001.

6.2. CAVA Worskhop Papers

Workshop One: Frameworks for Understanding Policy and Culture

29 October 1999

Williams, F. (1999) ‘Understanding The Dynamics Of Social Change, Social Relations & Welfare Settlements Towards An Analytical Framework’. CAVA Workshop One: Frameworks for Understanding Policy and Culture, University of Leeds, 29 October 1999. Available at: www.leeds.ac.uk/cava

Smart, C. (1999) ‘Divorce In England 1900-2000: A Moral Tale?’. CAVA Workshop One: Frameworks for Understanding Policy and Culture, University of Leeds, 29 October 1999. Available at: www.leeds.ac.uk/cava

Duncan, S. (1999) ‘Comparative Research: The Case Of Genderfare’. CAVA Workshop One: Frameworks for Understanding Policy and Culture, University of Leeds, 29 October 1999. Available at: www.leeds.ac.uk/cava

Deacon, A. (1999) ‘Competing Formulations Of Moral Agency In Relation To Welfare, Partnership & Parenting’. CAVA Workshop One: Frameworks for Understanding Policy and Culture, University of Leeds, 29 October 1999. Available at: www.leeds.ac.uk/cava

Duncan, S. (1999) ‘Challenging Rational Action Theory’. CAVA Workshop One: Frameworks for Understanding Policy and Culture, University of Leeds, 29 October 1999. Available at: www.leeds.ac.uk/cava

Workshop Two: Statistics and Theories for Understanding Social Change

21 January 2000

Neale, B. (2000) ‘The Proper Thing To Do? Theorising Family, Kinship & Social Change: A Qualitative Approach’. CAVA Workshop Two: Statistics and Theories for Understanding Social Change, University of Leeds, 21 January 2000. Available at: www.leeds.ac.uk/cava

Irwin, S. (2000) ‘A Conceptualising Social Change: Family, Work & The Changing Pattern Of Social Reproduction’. CAVA Workshop Two: Statistics and Theories for Understanding Social Change, University of Leeds, 21 January 2000. Available at: www.leeds.ac.uk/cava

Irwin, S. (2000) ‘Patterns Of Change In Family & Household Structure & Resourcing: An Overview’. CAVA Workshop Two: Statistics and Theories for Understanding Social Change, University of Leeds, 21 January 2000. Available at: www.leeds.ac.uk/cava

Roseneil, S. (2000) ‘Towards An Understanding Of Postmodern Transformations Of Sexuality & Cathexis’. CAVA Workshop Two: Statistics and Theories for Understanding Social Change, University of Leeds, 21 January 2000. Available at: www.leeds.ac.uk/cava

Hollway, W. (2000) ‘Psychological & Psychoanalytic Parenting & Partnering: The Post-War Period’. CAVA Workshop Two: Statistics and Theories for Understanding Social Change, University of Leeds, 21 January 2000. Available at: www.leeds.ac.uk/cava

Workshop Three: Analysing Policy Change and Implementation

11 February 2000

Deacon, A. (2000) ‘Cava & The Moral Reordering Of Welfare Under New Labour’. CAVA Workshop Three: Analysing Policy Change and Implementation, University of Leeds, 11 February 2000. Available at: www.leeds.ac.uk/cava

Duncan, S. (2000) ‘New Labour's 'Rationality & Morality Mistakes' - & Some Alternatives’. CAVA Workshop Three: Analysing Policy Change and Implementation, University of Leeds, 11 February 2000. Available at: www.leeds.ac.uk/cava

Hollway, W. (2000) ‘Doing Qualitative Research Differently: Free Association, Narrative Of The Interview Method’. CAVA Workshop Three: Analysing Policy Change and Implementation, University of Leeds, 11 February 2000. Available at: www.leeds.ac.uk/cava

Mason, J. (2000) ‘Deciding Where To Live: Relational Reasoning And Narratives Of The Self’. CAVA Workshop Three: Analysing Policy Change and Implementation, University of Leeds, 11 February 2000. Available at: www.leeds.ac.uk/cava

Workshop Four: Methodologies for Researching Moral Agency

17 March 2000

Mason, J. (2000) ‘Researching Morality’. CAVA Workshop Four: Methodologies for Researching Moral Agency, University of Leeds, 17 March 2000. Available at: www.leeds.ac.uk/cava

Hollway, W. (2000) ‘Moral Intersubjectivity, Methodology & Empirical Research’. CAVA Workshop Four: Methodologies for Researching Moral Agency, University of Leeds, 17 March 2000. Available at: www.leeds.ac.uk/cava

Williams, F. (2000) ‘A Conceptual Chart For Cava’. CAVA Workshop Four: Methodologies for Researching Moral Agency, University of Leeds, 17 March 2000. Available at: www.leeds.ac.uk/cava

Duncan, S. (2000) ‘Localities Paper 1: The Use & Abuse Of Locality Research’. CAVA Workshop Four: Methodologies for Researching Moral Agency, University of Leeds, 17 March 2000. Available at: www.leeds.ac.uk/cava

Duncan, S. (2000) ‘Localities Paper 2: Choosing Case Study Areas For Strand 3 Research - Localities & Neighbourhoods’. CAVA Workshop Four: Methodologies for Researching Moral Agency, University of Leeds, 17 March 2000. Available at: www.leeds.ac.uk/cava

Duncan, S. (2000) ‘Localities Paper 3: Variations In Parenting And Partnering At The Local Level’. CAVA Workshop Four: Methodologies for Researching Moral Agency, University of Leeds, 17 March 2000. Available at: www.leeds.ac.uk/cava

Duncan, S. (2000) ‘Undertaking Fieldwork & Getting Data: A 4 Pronged Approach’. CAVA Workshop Four: Methodologies for Researching Moral Agency, University of Leeds, 17 March 2000. Available at: www.leeds.ac.uk/cava

Workshop Five: New Conceptualisations of Care, Values and Welfare

5 May 2000

Williams, F. (2000) ‘The Politics Of Recognition’. CAVA Workshop Five: New Conceptualisations of Care, Values and Welfare, University of Leeds, 5 May 2000. Available at: www.leeds.ac.uk/cava

Martin, G. (2000) ‘New Social Movements, Welfare & Social Policy: A Critical Assessment’. CAVA Workshop Five: New Conceptualisations of Care, Values and Welfare, University of Leeds, 5 May 2000. Available at: www.leeds.ac.uk/cava

Smart, C. (2000) ‘The Ethics Of Care’. CAVA Workshop Five: New Conceptualisations of Care, Values and Welfare, University of Leeds, 5 May 2000. Available at: www.leeds.ac.uk/cava

Workshop Six: Cross-National Perspectives on Care, Values and Welfare

16 June 2000

Roseneil, S. (2000) ‘Why We Should Care About Friends: Some Thoughts (For Cava) About The Ethics & Practice Of Friendship’. CAVA Workshop Six: Cross-National Perspectives on Care, Values and Welfare, University of Leeds, 16 June 2000. Available at: www.leeds.ac.uk/cava

Martin, G. (2000) ‘Social Movements Of Care’. CAVA Workshop Six: Cross-National Perspectives on Care, Values and Welfare, University of Leeds, 16 June 2000. Available at: www.leeds.ac.uk/cava

Williams, F. (2000) ‘Debates & Discourses In Cross-National Comparative Research’. CAVA Workshop Six: Cross-National Perspectives on Care, Values and Welfare, University of Leeds, 16 June 2000. Available at: www.leeds.ac.uk/cava

Williams, F. (2000) ‘EU Discourses & Debates’. CAVA Workshop Six: Cross-National Perspectives on Care, Values and Welfare, University of Leeds, 16 June 2000. Available at: www.leeds.ac.uk/cava

Duncan, S. (2000) ‘Reconciling Work & Life' In The EU: Policy Discourses Social Trends & Case Countries’. CAVA Workshop Six: Cross-National Perspectives on Care, Values and Welfare, University of Leeds, 16 June 2000. Available at: www.leeds.ac.uk/cava

Additional Working Papers

Duncan, S. (2003) ‘Mothers, Care and Employment: Values and Theories’, CAVA Working Paper 1, University of Leeds. Available at: www.leeds.ac.uk/cava

Gerodetti, N. (2004) ‘Disabling Femininities, Homosexuality & Eugenics: Modern Swiss Sexualities'. CAVA Working Paper 2, University of Leeds. Available at: www.leeds.ac.uk/cava

6.3. Centre for Research on Family Kinship & Childhood Working Papers

Duncan, S., Edwards, R., Reynolds, T. and Alldred, P. (2002) ‘A Mother’s Instinct? Paid Work, Partnering and Childcare’. Centre For Research on Family, Kinship & Childhood, Working Paper 26, University of Leeds.

Duncan, S. (2003) ‘Mother Knows Best: Social Divisions, Work and Childcare’. Centre For Research on Family, Kinship & Childhood, Working Paper 31, University of Leeds.

- Flowerdew, J. and Neale, B  (2002) ‘Trying to Stay Apace: Children with Multiple Challenges in their Post Divorce Family Lives’. Centre For Research on Family, Kinship & Childhood, Working Paper  31, University of Leeds.

Mason, J. (2000) 'Deciding Where to Live: Relational Reasoning and Narratives of the Self'. Centre For Research on Family, Kinship & Childhood, Working Paper 19, University of Leeds.

Neale, B. and Smart, C. (2001) ‘Caring, Earning and Changing: Parenting and Employment after Divorce’. Centre For Research on Family, Kinship & Childhood, Working Paper 24, University of Leeds.

Neale, B and Flowerdew, J. (2002) ‘Time, Texture and Childhood: The Contours of Longitudinal Qualitative Research with Children’. Centre For Research on Family, Kinship & Childhood,  Working Paper 30, University of Leeds.

Smart, C. (2000) ‘Divorce in England 1950-2000: A Moral Tale?'. Centre for Research on Family, Kinship & Childhood, University of Leeds, Working Paper No 20, University of Leeds.

Smart, C. (2004) ‘Textures of Family Life: Further thoughts on change and commitment’. Centre For Research on Family, Kinship & Childhood,  Working Paper 32, University of Leeds.

Smart, C. (2005) ‘Living with Difference and Sameness: Culturally Diverse Families’. Centre For Research on Family, Kinship & Childhood,  Working Paper 36, University of Leeds.

6.4. Centre for Interdisciplinary Gender Studies e-Papers

Roseneil, S. (ed) (2001-) Centre for Interdisciplinary Gender Studies e-papers (1-13)

Batt, C. Brown-Grant, R. Richardson, B. and Swan, M. (2000) 'Gender, Culture and Society in Western Europe, from the Fifth to the Sixteenth Centuries'. Centre for Interdisciplinary Gender Studies e-paper 1.

Baylies, C. (2000) 'Feminist Scholarship in Development Studies'. Centre for Interdisciplinary Gender Studies e-paper 2.

Beaney, M. (2000) 'Re-engendering Logic: Feminism and the History and Philosophy of Logic'. Centre for Interdisciplinary Gender Studies e-paper 3

Hogan, L. (2000) 'Feminist Research in Theology'. Centre for Interdisciplinary Gender Studies e-paper 4

Jones, V. (2000) 'Feminism and English Studies'. Centre for Interdisciplinary Gender Studies e-paper 5

Knott, K. (2000) ' Religious Studies, Feminist Research and Gender Studies'. Centre for Interdisciplinary Gender Studies e-paper 6

Liddington, J. (2000) 'History, Feminism and Gender Studies'. Centre for Interdisciplinary Gender Studies e-paper 7

Ramsay, M. (2000) 'Political Theory and Feminist Research'. Centre for Interdisciplinary Gender Studies e-paper 8

Rodgers, J. (2000) 'Gender and Feminism in International Relations'. Centre for Interdisciplinary Gender Studies e-paper 9

Roseneil, S. (2000) 'The Coming of Age of Feminist Sociology'. Centre for Interdisciplinary Gender Studies e-paper 10

Williams, F. (2000) 'Feminism and Social Policy'. Centre for Interdisciplinary Gender Studies e-paper 11

L'Estrange, E. (2001) 'Going Beyond the Curtain: Childbirth Narrative in the Late Middle Ages'. Centre for Interdisciplinary Gender Studies e-paper 12

Gerodetti, N. (2001) 'Sexualities and the Swiss Nation'. Centre for Interdisciplinary Gender Studies e-paper 13

7. Broadcast

Deacon, A. (2001) Interview on prospects for welfare reform after the election on World at One, Radio Four, 4 June 2001.

Duncan, S. (2003) 'Women and Rationality' on Woman’s Hour, Radio 4, 6 August 2003. (RADIO)

Neale, B. (2004) Young people’s experience of post divorce family life, Interviews on BBC radio Wales, BBC radio Scotland. (RADIO)

Neale, B. (2004) ‘ Interviews and contribution to phone-in discussion on young people’s experience of living across two homes, BBC local radio (Dublin, Gloucester, Worcester), December 2004. (RADIO)

Phillips, A. (2003) 'Fathers Campaigning for Equal Access' on Woman’s Hour, Radio 4, 24 October 2003. (RADIO)

Phillips, A. (2003) 'Serial Monogamy' on Woman’s Hour, Radio 4, 23 December 2003. (RADIO)

Roseneil, S. (2000) Academic consultant and interviewee on gender and family change, The Essential Guide to the 21st Century and linked programme Visionaries, BBC World Service, January 2000. (RADIO)

Roseneil, S. (2000) Phone-in guest following Essential Guide, BBC World Service, January 2000. (RADIO)

Roseneil, S. (2003) 'Peace campaigners' on Woman’s Hour, Radio 4, 21 January 2003. (RADIO)

Roseneil, S. (2003) Interview on changing patterns of relationship formation and individualisation, BBC World Service, March 2003. (RADIO)

Roseneil, S. (2003) 'The Company of Women' on Woman’s Hour, Radio 4, 3 April 2003. (RADIO)

Roseneil, S. (2003) ‘Do lesbians really want to marry?’ on Woman’s Hour, Radio 4, 17 July 2003. (RADIO)

Roseneil, S. (2004) Interview on age and friendship, BBC Radio Shropshire, September 2004. (RADIO)

Roseneil, S. (2004) 'Greenham Common changed my life’ on Timeshift, BBC Four and BBC Two, February and March 2004, May 2005. (TV)

Smart, C. (2000) Interview with Laurie Taylor on Thinking Allowed, Radio 4, 23 February 2000. (RADIO)

Smart, C. (2000) Interview with Melissa Benn on The History of Divorce, Radio 4, 26 July and 2 August 2000. (RADIO)

Smart, C. (2001) Interview on Children and Parent Conflict on Women's Hour, Radio4, February 2001 (RADIO)

Smart, C. (2001) Interview with Geraldine Doogue on Divorce and Changing Family Practices on Life Matters, ABC Australian National Radio. 21 March 2001. (RADIO)

Smart, C. (2002) Interview with Jenny Murray on ‘Contact after Divorce’ on Woman’s Hour, BBC Radio 4,  7 October 2002. (RADIO)

Smart, C. (2003) Interview on ‘Marriage’ on Analysis, BBC Radio 4, 13 March 2003. (RADIO)

Smart, C. (2003) Interview on ‘Changing Commitments’ on Thinking Allowed, BBC Radio 4, 29 April 2003. (RADIO)

Smart, C. (2003) 'Changing Nature of Family' on Thinking Allowed, Radio 4, 4 June 2003. (RADIO)

Smart, C. (2003) Interview on ‘The Language of the Family’ with Language in Focus, BBC World Service, 13 September 2003. (RADIO)

Smart, C. (2004) Interview on ‘Changing Commitments’, ABC (Australian National Radio), 23 March 2004. (RADIO)

Smart, C. (2004) ‘Children’s Narratives of Divorce’ on Life Matters, ABC Radio (Australia), 1 April 2004. (RADIO)

Smart, C. (2004) ‘Marriage’ on Radio Four, You and Yours, Radio Four, 21st July 2004. (RADIO)

Smart, C. (2004) Interview on ‘Cohabitation in Later Life’ on Woman’s Hour, BBC Radio 4, 25 November 2004. (RADIO)

Williams, F. (2001) Interview with Geraldine Doogue on Divorce and Changing Family Practices on Life Matters, ABC Australian National Radio. 20 March 2001. (RADIO)

Williams, F. (2003) ‘The British Airways Strike' on Six O'clock News, BBC1, 26 July 2003. (TV)

Williams, F. (2004) Interview on Independent Radio News Network, 18 June 2004. (RADIO)

Williams, F. (2004) 'Rethinking Families, Rethinking Care'  on News Talk 106, City Edition (Dublin), 27 September 2004 (RADIO)

Williams, F. (2004) Interview on Radio Eirann,  27 September 2004.(RADIO)

Williams, F. (2005) Interview on Radio Berkshire, 18 May 2005. (RADIO)

Williams, F. (2005) Interview on Radio Eirann, 18 May 2005. (RADIO)

Williams, F. (2005) Interview on Radio Scotland, 18 May 2005. (RADIO)

Williams, F. (2005) Interview on Woman’s Hour, BBC Radio 4, 2 June 2005. (RADIO)

8. Datasets

8.1. Mothers, Care And Employment

- 48 interviews, transcribed and in NVivo.

- 3 focus groups interviews, transcribed and in NVivo.

- Basedata avilable for all interviews.

8.2. Divorce

- 55 interviews. 47 transcribed and in NVivo.

- 8 summaries compiled for interviews conducted through interpreters or where tape recording was of poor quality.

- Basedata available for all interviews.

8.3. Transnational Kinship

- 69 interviews, transcribed and in NVivo.

- Basedata avilable for all interviews.

8.4. Friends And Non-Conventional Partnerships (FNCP) And FNCP Revisited

- 53 interviews, transcribed and in NVivo.

- 25 re-interviews, in NVIVO.

- Basedata available for all interviews.

8.5. Collective Voices

- 55 interviews, transcribed and coded in NVivo.

- 55 case-studies, with reduced basedata

8.6. Marrying In

- 6 interviews (with 4 couples and 2 individuals), transcribed.

8.7. Local Schools Survey

- 102 survey responses.

8.8. Geographies Of Family Formations 1991-2001

Selected census variables and indices derived from them, and from Key Population and Vital Statistics, in ecxel format, with mapping of selected output.

- CENSUS 1991

1. Local authority level for GB

Motherhood Employment effect (compares % in FT employment of partnered mothers and partnered non-mother women in same age range)

% cohabitant births ( births to couples accounted for by cohabiting, non-married, couples)

% non-traditional households (% single, multi-family, same-sex (not necessarily partners) households, excluding pensioners)

% dependent women (% married women without paid work)

% independent women ( % unpartnered women 16-65 with FT employment)

% lone parents ( % lone parent households of all households with children)

% separated / divorced (% separated/ divorced of all adults)

2. Local ward level for selected LAs in W Yorkshire,

Leeds, Bradford, Calderdale

As above (but not motherhood employment effect) and also

% mothers in FT employment, FT:PT employment ratio for women, % international migrants, % non-English mother tongue.

- CENSUS 2001

1. Local authority level for GB

Motherhood Employment effect (compares % in FT employment of partnered mothers and partnered non-mother women in same age range)

% cohabitant births ( births to couples accounted for by cohabiting, non-married, couples)

% non-traditional households (% single, multi-family, same-sex (not necessarily partners) households, excluding pensioners)

% dependent women (% married women without paid work)

% independent women ( % unpartnered women 16-65 with FT employment)

% lone parents ( % lone parent households of all households with children)

% separated / divorced (% separated/ divorced of all adults)

% non-partner households (below retirement age)

% same-sex households

2. Local ward level for selected LAs in W Yorkshire

Leeds, Bradford, Calderdale

Selected outputs of above

8.9. The CAVA National Family Survey

Subsequent to completion of the main body of qualitative field work and analysis, the  CAVA Management Group sought to triangulate the results with some nationally representative quantitative data.  These data were collected and collated by QA Research Ltd during May-June 2005.

The Survey comprised two elements, a statistically representative sample by age and sex of the general GB population and a specific Black and Minority Ethnic (BME) booster sample. The survey employed Computer Aided Telephone Interviews in England, Scotland and Wales for the general survey, and face – to - face interviews in North London, Birmingham and Bradford for the BME sample. An overall response rate of 555 was achieved, from a target of 600, and 99 of 100 BME interviews.

9. Software or Multi-Media Package

10. Consultancy, Advisory Service or Course

Duncan, S. (2002) Overview of the ESRC portfolio and developments in the ‘Lifecourse, Lifestyles and Health’ and ‘Social Stability and Exclusion’ themes.

Duncan, S. and Williams, F. (2005). Consultation for BBC programme on geographies of family formation, June 2005.

Neale, B. (2004-) CAFFCASS Yorkshire and Humberside Regional Steering Group for Children’s Participation.

Roseneil, S. (2000-1) Consultant to Leeds City Council on Developing Mechanisms for Accountability in the Work of the Equal Opportunities Unit.

Roseneil, S. (1999-2000) Consultant to United Nations Department of Disarmament Affairs on Gender and Disarmament.

Roseneil, S. (2001) Council funded Research Seminar for Doctoral Students at the University of Oslo, based on my work: `Queer Theory and the Politics of Postmodernity’.

Williams, F. (2003) Submission to the Department for Education and Science Consultation Process on the Green Paper, ‘Every Child Matters’,  November 2003.

Williams, F. (2004) Presentation ‘Intersecting issues of ‘race’, ethnicity, migration and welfare’ to ‘Gender, equality, citizenship and governance’ consultation meeting for FP6 Priority 7 research area ‘Knowledge-based society and social cohesion’, Paris, 19 March 2004.

Williams, F. (2004) ‘Developing an ethic of care: its relevance to families and the well-being of children’, Paper presented to the Commission on the Future of the Family and the Well being of Children, 19 October 2004.

Williams, F., Groves, K. and Phillips, A.  (2004) Training session Communicating your Research to Faculty of Social Sciences at University Leeds, organised by the Staff and Departmental Development Unit (SDDU) at the University of Leeds, 10 May 2004.

11. Degree or other Honour

Deacon, A. (2004) Academician, Academy of Learned Societies in the Social Sciences, September 2004.

Williams, F. (2003) Academician, Academy of Learned Societies in the Social Sciences, September 2003

Williams, F. (2004) New Year’s Honours, 2004 OBE for services to Social Policy

Hines, S. (2004) PhD, University of Leeds, December 2004

12. Research Facility

The Enduring Families and Family Dynamics studies have established the foundation for an archive of qualitative longitudinal data on family life, gathered over an eight year period. We plan to expand and develop this resource as part of future QL projects at the University of Leeds.

13. Invention or Product

14. Audio Visual Recordings and Material

Smart, C. (2003) ‘Equal Shares: Children’s Experience of Long Term Shared Residence’. Video recorded presentation to the Queensland Law Society and Family Law Practitioners’ Association Family Law Residential Conference, Surfers Paradise, Queensland, 5-6 September 2003.

Williams, F. and Roseneil, S. (2004) `Family, Friends and Relationships: Citizens’ Dialogues on the Future of Welfare’. Digital film on CD-ROM from The ESRC Research Group for the Study of Care, Values and the Future of Welfare, 42 minutes, produced/edited by Fiona Williams and Sasha Roseneil.

Williams, F. (2001) ‘Exploring the Active Welfare Subject’. Macquarie University, Australia. Video-recorded presentation for South Western Australia Community Services, 18 April 2001.

15. Other Type of Publication or Output

Neale, B., Flowerdew, J., Wade, A. and Smart, C. (2003) Enduring Families: Children’s Long term reflections on post divorce family life. ESRC No R000239248, End of Award Report, Graded Outstanding

Smart, C., Neale, B. and Wade, A. (2001) A response to: Making Contact Work: A Consultation Paper issued by the Children Act Sub-Committee of the Advisory Board on Family Law. June 2001.

Smart, C., Neale, B. and Wade, A. (1999) New Childhoods? Children and Co-Parenting after Divorce, ESRC L129251049, End of Award Report: Graded Outstanding

Annex B - Resources

1. Staffing

| Title | Initials | Surname | Date of Birth | Grade / % | Apt. Date | Departure Date | Destination Type and Post |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Prof | L | Ackers | 23/01/60 | LB Pt.5 Year 3 50% Year 4 10% | Oct 2000 | Sep 2003 | Academic Post, Jean Monnet Chair in European Law, University of Leeds |
| Dr | S. | Budgeon | 29/04/67 | R1A Pt. 6-10 50% for Jul 00 to Aug 00. 100% from Sep 00 to Apr 03 | Jul 2000 | Apr 2003 | Academic Post, Senior Lecturer, University of Birmingham |
| Prof | A | Deacon | 5/12/46 | Rep Teaching at R1a Pt.6 Year 1 60% Year 2 30% Year 3 30% Year 4 20% Year 5 60% | Oct 1999 | Mar 2005 | Academic Post, Prof of Social Policy, University of Leeds |
| Prof | S | Duncan | 26/8/49 | Year 1 50% Year 2 20% Year 3 50% Year 4 10% Year 5 40% | Oct 1999 | Mar 2005 | Academic Post, Prof of Comparative Social Policy, University of Bradford |
| Dr | J | Flowerdew | 04/03/51 | R1A Pt. 6 50% for Jul 00 to Sep 00 | Jul 2000 | Sept 2000 | Academic Post, Research Fellow, Centre for Research on Family, Kinship and Chil;dhood, University of Leeds |
| Dr | J | Gabb | 17/05/63 | R1A Pt. 6 50% for Jan 03 to Feb 03 | Jan 2003 | Feb 2003 | Academic Post, Open University. |
| Dr | K | Groves | 17/05/77 | 50% for Nov 02 to Dec 02. 100% for Jan 03 to Mar 03 | Nov 2002 | Mar 2003 | Academic Post, Communications Co-ordinator, CAVA, University of Leeds |
| Dr | K | Groves | 17/05/77 | Admin1 Pt.4 100% for Apr 03 to Feb 05 | Apr 2003 | Feb 2005 | Academic Post, Research Manager, Centre for Study of Law and Policy in Europe, Department of Law, University of Leeds |
| Prof | W | Hollway | 20/04/49 | LA Pt.2 Year 1 50% Year 5 10% | Oct 1999 | Mar 2005 | Academic Post, Professor of Psychology, Open University |
| Dr | Y | Hussain | 07/11/70 | R1A Pt. 6 100% for Jan 01 to Feb 02 | Jan 2001 | Feb 2002 | Academic Post, Research Fellow, University of Leeds |
| Dr | S | Irwin | 22/07/61 | Rep Teaching at R1a Pt.6 Year 1 50% Year 2 10% Year 5 10% | Oct 1999 | Mar 2005 | Academic Post, Senior Lecturer in Sociology, University of Leeds |
|  | A | Jackman | 18/10/65 | C4 Pt.1 100% for Oct 01 to Nov 02 | Oct 2001 | Nov 2002 | Clerical Post, Secretary, Centre for Research on Family, Kinship and Childhood, University of Leeds |
| Dr | G | Martin |  | R1A Pt. 6-9 100% for Jan 00 to Oct 02 | Jan 2000 | Oct 2002 | Personal |
| Dr | J | Mason | 24/04/58 | Rep Teaching at R1a Pt.6 Year 1 20% Year 2 20% Year 3 10% Year 4 50% Year 5 10% | Oct 1999 | Mar 2005 | Academic Post, Reader in Sociology, University of Leeds |
|  | S | Mosby | 30/07/76 | C2 Pt.4 50% from Feb 00 to Dec 02. 100% from Dec 02 to Mar 05 | Feb 2000 | Mar 2005 | Clerical Post, University of Leeds |
| Dr | B | Neale | 15/01/52 | R2 Pt.16 – R3 Pt.5 Year 1 80% Year 2 80% Year 3 80% Year 4 80% Year 5 80% | Jan 2000 | Sep 2004 | Academic Post, ESRC Principal Research Fellow, University of Leeds |
| Prof | S | Roseneil | 28/08/66 | Rep Teaching at R1a Pt.6 Year 1 80% Years 2-5 60% | Oct 1999 | Mar 2005 | Academic Post, Prof of Sociology and Gender Studies, University of Leeds |
| Dr | L | Saugeres | 02/12/64 | R1A Pt. 6 100% for Oct 00 to Sep 02 | Oct 2000 | Sep 2002 | Academic Post, Postdoctoral Research Fellow in Women’s Studies and Sociology, Monash University, Australia |
|  | J | Shipman | 03/02/79 | R1A Pt. 4 100% for Jun 02 to Nov 02 | Jun 2002 | Nov 2002 | Doctoral Candidate, University of Adelaide, Australia |
|  | R | Shipman | 03/05/76 | R1A Pt. 4-5 100% for Sep 02 to Oct 03 | Sep 2002 | Oct 2003 | Academic Post, Research Fellow, Centre for Research on Family, Kinship and Chil;dhood, University of Leeds |
| Prof | C | Smart | 20/12/48 | Rep Teaching at R1a Pt.6 Year 1 80% Year 2 80% Year 3 80% Year 4 100% Year 5 100% | Oct 1999 | Mar 2005 | Academic Post, Prof of Sociology, University of Leeds |
| Dr | H | Stalford | 26/01/73 | 50% for Jan 00 to Apr 00 | Jan 2000 | Apr 00 | Academic Post, Lecturer in Law, University of Liverpool |
|  | H | Waite | 19/10/76 | C4 Pt.1 100% for Jan 00 to Jan 02 | Jan 2000 | Jan 2002 | Personal |
| Prof | F | Williams | 22/07/47 | Rep Teaching at R1a Pt.6 Years 1-5 100% | Oct 1999 | Mar 2005 | Academic Post, Prof of Social Policy, University of Leeds |

2. Funding

| 2.1. CAVA Funding |  |  |  |  |
| --- | --- | --- | --- | --- |
| Year Awarded | Principal Applicant | Funder | Amount | Title / Details |
| 1999-2005 | Williams, F. | ESRC | £1,411,554 | ‘Care, Values and the Future of Welfare’ Research Project |
| 1999-2005 | Williams, F. | University of Leeds | £193,521 | Host Institution Contribution with reference to ESRC grant for ‘Care, Values and the Future of Welfare’ Research Project. |
| 2002 | Williams, F. | ESRC | £44,139 | Additional funding pump-priming projects for ‘Care, Values and the Future of Welfare’ Research Project.. Dec 02. |
| 2003-4 | Williams, F. | ESRC | £15,000 | Additional Grant for Communication Strategies for ‘Care, Values and the Future of Welfare’ Research Project.. |
| 2003 | Williams, F. | ESRC | £9,000 | Supplementary Grant for Citizens Survey for ‘Care, Values and the Future of Welfare’ Research Project. |
| 2.2. Co-funding |  |  |  |  |
| Year Awarded | Principal Applicant | Funder | Amount | Title / Details |
| 1999 | Smart, C. | Joseph Rowntree Foundation | £82,709 | ‘Supporting Young Children at Times of Family Transition’ |
| 2000 | Duncan, S. and Barlow, A. | Nuffield | £93,000 | ‘Family restructuring, the common law marriage myth and legal realism’ |
| 2000 | Neale, B. | Nuffield | £5,000 | Grant towards cost of publishing Parent Problems, (2000) in collaboration with Young Voice. |
| 2000 | Neale, B. | Nuffield | £2,000 | Grant towards cost of publishing Good to Talk (2001) in collaboration with Young Voice. |
| Nov 2000 | Deacon, A. (ext funded int visit) | Rockefeller Foundation | $2,700 | Funding to support special session at APPAM conference in Seattle. |
| 2001-3 | Neale, B. | ESRC | £100,408 | ‘Enduring Families’. Established as a ‘sister’ project to CAVA. Complements and enriches CAVA by bringing childhood dimension into the work. This project developed out of earlier work on post divorce family life (Smart and Neale), which fed into the development of the CAVA programme. |
| Jan 2002 – Aug 2004 | Wade, A. | ESRC | £163,755 | ‘Continuity and Change in Parent-Child Relations over 3 Generations’ |
| Jan 2002 – Aug 2004 | Smart, C. | Dept for Constitutional Affairs (Lord Chancellor’s Department) | £159,385 | ‘Contact and Residence Disputes in Court’ |
| Jul 2002 | Deacon, A. | Social Policy Association / Lancaster University | £2750 | Funding for workshop on Cycle of Deprivation. |
| 2002 | Hollway, W. | British Psychological Society | £3,000 | ‘Talking Across the two Social Psychologies’. Seminar Series |
| Sep 2002 – Aug 2004 | Mason, J. | ESRC | £12,343 | ‘Knowing Families’. Seminar Series |
| 2002 | Ackers, H. L. | ESRC (Science and Society Programme) | £40,768 | ‘MOBEX: Mobility and Excellence in the European Research Area’. |
| 2002 | Ackers, H. L. | Wellcome Trust | £180,000 | ‘Citizenship and Retirement Migration In the EU’ |
| 2002 - 2003 | Ackers, L. | Marie Curie | £41,970 | Fellowship to support Spanish researcher working with Professor Louise Ackers. |
| 2002 | Ackers, L. and Dwyer, P. | ESRC CASE Award in conjunction with Women and Equality Unit / DTI | £25,000 | Studentship awarded to Liz Oliver. |
| 2002 | Ackers, L. | European Commission | €413,667 | ‘Equal Pay, Career Progression and the Socio-Legal Valuation of Care’. |
| Jan 2003 – Mar 2004 | Ackers, L. | European Commission DG Employment / UK DTI | £225,575 | MOBISC Project on recruitment and retention of women in mobile science careers. |
| May 2003 – Jul 2005 | Ackers, L. | European Commission DG research | £61,500 | IMPAFEL Project on impact of Marie Curie Scheme. |
| Jun 2003 – Jul 2005 | Ackers, H. L. | European Universities Association | £22,184 | MORESS: Mapping Research in European Social Sciences and Humanities |
| Jul 2003 | Ackers, L. | European Commission | £28,325 | PHARE grant for symposium on scientific mobility. |
| Sep 2003 – Jul 2004 | Williams, F. and University of Leeds. | The Leverhulme Trust | £16,584 | Visiting Fellowship for Professor Selma Sevenhuijsen. |
| Oct 2003 – Apr 2006 | Smart, C. | ESRC | £159,898.52 | ‘Gay and Lesbian ‘Marriage’/’ An exploration of the meanings and significance of legitimating same sex relationships. |
| Oct 2003 – Mar 2004 | Williams, F. | Calouste Gulbenkian Foundation | £15,000 | Grant for ‘Rethinking Families’ book. |
| 2003 | Ackers, L. | European Commission DG research | £22,184 | MORESS: Mapping Social Science Research in the EU. |
| Dec 2003 – Dec 2005 | Williams, F. and Gavanas, A. | European Commission | £107,363.20 | ‘Migrant Domestic Workers in European Care Regimes’. Marie Curie Intra-European Fellowship for Dr Anna Gavanas. |
| 2004-5 | Neale, B. | ESRC | £44,800 | ‘Family Dynamics after Divorce: A Meta-Analysis of Longitudinal Qualitative Data’. One year project - an extension to ‘Enduring Families’ with same complementary role to CAVA. |
| Mar 2004 – Oct 2005 | Williams, F. | NESS, University of London | £82,513 | ‘National Sure Start Evaluation: Community Empowerment’. |
| 2004 | Smart, C. Partner 8 Leader | EU 6th Framework, Coordination Action | €30,499 | Wellchi: ‘The Well Being of Children: The impact of changing family forms, working conditions of parents, social policy and legislative measures’. |
| 2004 | Mason, J. | ESRC | £744,379 | ‘Multi-Dimensional Methods for Real Lives Research’, Real Life Methods Node of the National Centre for Research Methods |
| 2004-2006 | Mason, J. | ESRC | £152,858 | ‘Children Creating Kinship’ |
| Oct 2004 – Mar 2006 | Mason, J. | University of Leeds (LSSI) | £114,000 | ‘Meshing Qualitative and Quantities Methodologies in Family Research’ |
| 2004 | Duncan, S. | ESRC | £13,500 | ‘Changing social norms, changing family law’. Seminar Series. |
| 2004 - 2006 | Roseneil, S. and Schofield, J. | Arts Council | £45,000 | ‘The Common Ground Project: Rediscovering Greenham’s Cold War Landscape’ |
| 2004 | Ackers, H. L. | ESRC (Science and Society Programme) | £182,788 | MOBEX2: The Impact of Enlargement on Scientific Mobility in European Union 18 months – until 2006. |
| 2004 | Ackers, H. L. | Anglo-German Foundation | £31,505 | MOBEX2: Science Mobility and Balanced Growth in an Enlarging Europe |
| Sep 2004 – Jan 2005 | Ackers, L. | HEFCE | £10,000 | ‘Scoping study of Human Resources Management for junior researchers in higher education institutions’. |
| 2004 - 2005 | Head, E. | ESRC | £26,497 | Post-doctoral Fellowship for Emma Head. (Mentor: Williams, F.) |
| 2005 - 2007 | Neale, B. | ESRC | £178,000 | ‘Time, Texture and Young Lives: Developing Qualitative Longitudinal Data’. ESRc Fellowship. Builds on above projects. |
| May 2005 | Ackers, L. | ESRC | £3,000 | PIPE Award to support workshop on highly-skilled mobility. May 2005. |
| 2005 - 2007 | Gavanas, A. | Swedish Research Council | £24,000 | ‘DJs, Technology and Masculinity’. Part of a larger research project on Gender and Popular Music. |
| 2005 - 2010 | Ackers, H. L. | European Commission (FP6) | €24,000 | E-MeP Laboratory: Exploring the Human Capital Dimension of a European Cell Biology Project 2005-2010. |
| 2005 | Hollway, W. and Phoenix, A. | ESRC | £189,000 | Identities in Process: Becoming African Caribbean, Bangladeshi and White mothers, ESRC (Identities and Social Action programme), Open University. |
| 2005 – 2006 | Hines, S. | ESRC | £25,640 | Post-doctoral Fellowship for Sally Hines. (Mentor: Roseneil, S.) |
| 2.3. Funding Sought but Unsuccessful |  |  |  |  |
| Year Awarded | Principal Applicant | Funder | Amount | Title / Details |
| 2000 | Mason, J. and Smart, C. | Joint Infrastructure Fund | £1,058,870 | Leeds Institute for Qualitative Research Unsuccessful |
| 2000 | Smart, C. | ESRC | £2,172,376 | ESRC Centre Status for CRFKC Short-listed but unsuccessful |
| 2002 | Mason, J. | ESRC | NK | e-Science and qualitative research Unsuccessful |
| 2003 | Mason, J. | ESRC | £1,476,164 | ESRC National Centre for e-Social Science Competition Short-listed but unsuccessful |
| 2002 | Duncan, S. | ESRC | £290,300 | ESRC Professorial Fellowship Unsuccessful |
| 2004 | Williams, F. | ESRC | £339,267 | ESRC Professorial Fellowship Short-listed but unsuccessful |
| 2005 | Smart, C. | Leverhulme | £945,427 | ‘Families we live by’ Research Programme Short-listed but unsuccessful |
| 2005 | Smart, C. | ESRC | £171,000 | ‘Staying Together’ Unsuccessful |
| 2005 | Hollway, W. (co-applicant) and Silva, E. (PI) | Leverhulme | £1,250,000 | ‘Family and Intergenerational Research’. Short-listed but unsuccessful |

3. Datasets (Listed in Section 8 of Annex A)

3.1. MOTHERS, CARE AND EMPLOYMENT

- 48 interviews, transcribed and in NVivo.

- 3 focus groups interviews, transcribed and in NVivo.

- Basedata avilable for all interviews.

3.2. DIVORCE

- 55 interviews. 47 transcribed and in NVivo.

- 8 summaries compiled for interviews conducted through interpreters or where tape recording was of poor quality.

- Basedata available for all interviews.

3.3. TRANSNATIONAL KINSHIP

- 69 interviews, transcribed and in NVivo.

- Basedata avilable for all interviews.

3.4. FRIENDS AND NON-CONVENTIONAL PARTNERSHIPS (FNCP) AND FNCP REVISITED

- 53 interviews, transcribed and in NVivo.

- 25 re-interviews, in NVIVO.

- Basedata available for all interviews.

3.5. COLLECTIVE VOICES

- 55 interviews, transcribed and coded in NVivo.

- 55 case-studies, with reduced basedata

3.6. MARRYING IN

- 6 interviews (with 4 couples and 2 individuals), transcribed.

3.7. LOCAL SCHOOLS SURVEY

- 102 survey responses.

3.8. GEOGRAPHIES OF FAMILY FORMATIONS 1991-2001

Selected census variables and indices derived from them, and from Key Population and Vital Statistics, in ecxel format, with mapping of selected output.

- CENSUS 1991

1. Local authority level for GB

Motherhood Employment effect (compares % in FT employment of partnered mothers and partnered non-mother women in same age range)

% cohabitant births ( births to couples accounted for by cohabiting, non-married, couples)

% non-traditional households (% single, multi-family, same-sex (not necessarily partners) households, excluding pensioners)

% dependent women (% married women without paid work)

% independent women ( % unpartnered women 16-65 with FT employment)

% lone parents ( % lone parent households of all households with children)

% separated / divorced (% separated/ divorced of all adults)

2. Local ward level for selected LAs in W Yorkshire,

Leeds, Bradford, Calderdale

As above (but not motherhood employment effect) and also

% mothers in FT employment, FT:PT employment ratio for women, % international migrants, % non-English mother tongue.

- CENSUS 2001

1. Local authority level for GB

Motherhood Employment effect (compares % in FT employment of partnered mothers and partnered non-mother women in same age range)

% cohabitant births ( births to couples accounted for by cohabiting, non-married, couples)

% non-traditional households (% single, multi-family, same-sex (not necessarily partners) households, excluding pensioners)

% dependent women (% married women without paid work)

% independent women ( % unpartnered women 16-65 with FT employment)

% lone parents ( % lone parent households of all households with children)

% separated / divorced (% separated/ divorced of all adults)

% non-partner households (below retirement age)

% same-sex households

2. Local ward level for selected LAs in W Yorkshire

Leeds, Bradford, Calderdale

Selected outputs of above

3.9. THE CAVA NATIONAL FAMILY SURVEY

Subsequent to completion of the main body of qualitative field work and analysis, the  CAVA Management Group sought to triangulate the results with some nationally representative quantitative data.  These data were collected and collated by QA Research Ltd during May-June 2005.

The Survey comprised two elements, a statistically representative sample by age and sex of the general GB population and a specific Black and Minority Ethnic (BME) booster sample. The survey employed Computer Aided Telephone Interviews in England, Scotland and Wales for the general survey, and face – to - face interviews in North London, Birmingham and Bradford for the BME sample. An overall response rate of 555 was achieved, from a target of 600, and 99 of 100 BME interviews.

4. Financial Details and Commentary

| Year | Oct 99 – Sep 00 | Oct 00 – Sep 01 | Oct 01 – Sep 02 | Oct 02 – Sep 03 | Oct 03 – Mar 05 | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Research Staff | 51,204.89 | 126,331.31 | 138,706.96 | 72,151.55 | 35,794.25 | 424,188.96 |
| Research Staff – fte | 66,916.48 | 65,702.39 | 56,035.36 | 54,011.37 | 91,422.40 | 334,088.00 |
| Technical Staff | - | - | - | - | - | - |
| Other Staff | 16,770.58 | 23,504.32 | 26,073.75 | 25,230.83 | 51,355.41 | 142,934.89 |
| Travel and Subsistence | 2,036.34 | 10,087.01 | 11,393.02 | 9,045.20 | 15,503.67 | 48,065.24 |
| Consumables and Exceptional Items | 10,083.49 | 18,413.31 | 19,339.41 | 34,708.52 | 25,857.05 | 108,401.78 |
| Equipment | 2,564.18 | 5,920.57 | 1,198.31 | 1,862.38 | 1,285.18 | 12,830.62 |
| Total | 149,575.96 | 249,958.91 | 252,746.81 | 197,009.85 | 221,217.96 | 1,070,509.49 |
| Overheads | 62,050.30 | 99,147.49 | 101,575.39 | 69,641.13 | 82,143.15 | 414,557.45 |
| Grand Total | 211,626.26 | 349,106.40 | 354,322.20 | 266,650.98 | 303,361.11 | 1,485,066.94 |
| Host Institution Contribution | 62,651 | 36,237 | 30,401 | 43,259 | 20,973 | 193,521 |

4.1. Host Institution Contribution

Main areas of expenditure:

- £125,910 towards academic staff costs, including payment for Hazel May, Deborah Phillips and Keleigh Groves; end of contract payment for Greg Martin; and additional promotion costs for Bren Neale.

- £8,362 towards clerical or other staff costs, including payment for Marie Ross, E. Slater, Keleigh Groves, Steve Mosby and Angela Jackman; and end of contract payment to Helen Waite.

- £4,253 in transcription fees paid to Helen Harvey.

- £36,000 in student maintenance fees.

- £2,597 in web consultancy fees.

- £2,622 in fees to Kelly Services Employment Agency.

- £5,000 contribution to office refurbishment.

- £1,710 contribution towards CAVA’s National Survey

- £7,068 in assorted travel and organisational costs.

4.2. ESRC CAVA Grant

Please see Annual Reports for detailed commentary.

4.2.1. Staff Costs

- Over the period, over 60% of the grant went on staff costs. This supported 6 full-time staff with contributions to 1 further full-time post. The grant further supported existing academic members to be ‘bought out’ of teaching and administrative duties. Six of these staff were based in the Department of Sociology and Social Policy where ESRC staff costs contributed to the recruitment from 1999 of four full-time lecturers on fixed-term appointments.

- 4.2.2. Non-Staff Costs

- Main expenditure was as follows:

1999 - 2000

Travel for the Advisory Group;

Computers and related equipment;

Fax Machine;

Graphic Design;

Stationery;

Cartography;

General costs associated with the Launch.

2000 - 2001

Travel for the Advisory Group;

Travel for the Research Group;

Travel for the International Seminars;

Conference Attendance;

Computers and related equipment;

Books;

Tapes and Minidisks;

Catering;

Transcription;

Research.

2001 - 2002

Travel for the Advisory Group;

Travel for the Research Group;

Travel for the International Seminars;

Conference Attendance;

Catering;

Books;

Advertising (for the Strands);

NVivo Software and Training;

Zip Drives;

Transcription;

Translation;

2002 - 2003

Travel for the Advisory Group;

Travel for the Research Group;

Travel for the International Seminars;

Conference Attendance;

Catering;

Books;

NVivo Software and Training;

Powerpoint Machine;

Transcription;

Coding.

2003 -  End of Project

Travel for the Advisory Group;

Travel for the Research Group;

Travel for the International Seminars;

Conference Attendance;

Citizens Dialogues Costs;

Editing of video for Citizens Dialogues;

Symposium Costs;

Catering;

Books;

Analysis by Darren Smith;

Laptop;

Digital Recorder;

Memory Sticks;

National Survey.

- 4.2.3. Indirect Costs

- The 46% of indirect costs attached to staff costs was divided up in the following way:

- Department of Sociology and Social Policy:			60%

- CAVA:								20%

- Centre for Research on Family, Kinship and Childhood:		10%

- Centre for Interdisciplinary Gender Studies:			10%

- In general, CAVA’s 20% went on:

- Staff training;

- Conference attendance not specified in the Strand budgets;

- Catering and equipment costs associated with all day workshops and Advisory Group meetings;

- Consultancies;

- Publications not covered by Strand budgets;

- Travel and subsistence costs not allocated in Strand budgets (e.g. for fact-finding surveys);

- Costs associated with visits from international academics;

- Where members of CAVA were employed in other departments at the University of Leeds, or in Professor Duncan's case, at the University of Bradford, staff costs followed them to their department and they also received indirect costs of 40%. The 6% was retained to cover administrative and service costs provided by CAVA and the Department of Sociology and Social Policy.

- 4.2.4. Changes

- Approval was sought from the ESRC for the late start of Dr. Hussain in January 2001, rather than October 2000, in order to enable her to finish the research project on which she was employed.  This extended the finish date of the Transnational Kinship Project to December 2003.

- It was decided to increase the equipment expenditure by buying a colour printer to enable us to print our own leaflets and newsletter. The overall saving was presented to the ESRC who approved the purchase.

- Between October 2001 and July 2002, ESRC Hardship Costs covered the sickness costs paid to Ms Helen Waite, the CAVA Secretary. Her staff costs were paid to temporary cover, Ms A. Jackman.

- From February 2002, Dr Hussain’s staff costs were used in the employment of replacement staff and the 6 month increase of Dr Neale’s contract from 80% - 100%.

- The original HIC included the salary costs of a full-time lecturer for 5.5 years who would spend 50% of their time co-ordinating a network of possible sponsors for CAVA’s research. Dr Hazel May was appointed in January 1999 and moved to a permanent lectureship post at Sheffield University in August 2001. The Director then re-negotiated the budget plans for the HIC with the University’s Resource Centres Monitoring Committee. It was agreed in December 2001 that the Department of Sociology and Social Policy would retain the 50% lectureship but that the remaining 50% salary costs would be absorbed by: (i) necessary dissemination and international networking costs in years 4 and 5, for which the Group had originally under budgeted; (ii) increases in Studentship Costs; and (iii) bridging funds for research staff. Subsequently the Group decided to use £10,000 of the dissemination costs towards the appointment of a Communications Co-ordinator for the final 18 months of the research programme.

- In 2003 we received £15,000 additional sum as a contribution towards a new 18 month post of Communications Co-ordinator. To this we added £9,000 staff costs from the then vacant half-time secretarial post and £10,000 from the part of the Host Institution Contribution that had been designated for dissemination. This re-arrangement worked particularly well with the appointment of the ESRC of a Media Fellow.

- No-cost Extensions:

- We requested from the ESRC to be allowed to move funding of £2,400 for our 5th International Seminar from March 2003 to September 2003. This was because the interviewing, coding and analysis work of the Transnational Kinship Project, to which this seminar was attached, had been delayed in 2002 with the departure of Dr. Hussain and the need to employ interviewers with specialist language skills. It was felt that organising a seminar would be too much of a further disruption. In addition, two of the key speakers from Australia were not available until September 2003. This was allowed and the seminar took place in September 2003.

- We further requested in December 2003 that we be allowed to spend money allocated for a final dissemination event in December 2004 rather than in July 2004 as originally intended. This was because we were already organising a major dissemination event for June 2004 and because Edinburgh University was organising a conference on a topic close to our own in July 2004. The Symposium took place in December 2004.

- Following on from the organisation of our Citizens’ Dialogues, we considered the research opportunities to be gained from having a more extensive testing of some of the data from our qualitative projects through the Leeds Citizens’ Panel. This consists of 1,000 people representative of the city in terms of age, ethnicity, gender, housing tenure and employment status. To conduct a survey would have cost £9,000 and we considered this would provide particularly good added-value to our work. For this reason we applied to the ESRC for this amount, which was granted. However, Leeds City Council decided it needed to reconstitute its panel, which meant a further 9 month delay. We therefore decided to commission QA Market research to do a National Survey to triangulate our findings. This took place in March 2005. The extra cost of the Survey (£1,710 on top of the additional grant of £9,000) was met by the Host Institution Contribution. (See above).

- Staff Costs during No-Cost Extension: Steve Mosby’s contract was extended from October 2004 to March 2005 and Keleigh Groves’s contract was extended from October 2004 to February 2005. Money to pay for these extensions came from the main ESRC grant (and is included in the Salary costs above).

Annex C - Advisory Committee

| Member | Period |
| --- | --- |
| Professor Clare Callendar, Chair (Professor of Social Policy, London South Bank University) | 1999-2004 |
| Professor Janet Finch (Vice Chancellor, Keele University) | 1999-2004 |
| Bill Kilgallon (Social Care Institute for Excellence) | 1999-2004 |
| Mary MacLeod (National Family and Parenting Institute) | 1999-2004 |
| Angela Phillips (Senior Lecturer in Journalism, Goldsmiths College) | 1999-2004 |
| Professor Ann Phoenix (Professor of Social and Developmental Psychology, Open University) | 1999-2004 |
| Professor Jennie Popay (Professor of Sociology and Public Health, Lancaster University) | 1999-2004 |
| Ceridwen Roberts (Senior Research Fellow, University of Oxford) | 1999-2004 |
| Professor Selma Sevenhuijsen (emeritus, Utrecht University) | 1999-2004 |
| David Skidmore, OBE (Board for Social Responsibility, Church of England) | 1999-2004 |
| Ed Straw (Chair, Relate Marriage Guidance, and Price Waterhouse Coopers)) | 1999-2004 |
| Liz Atkins (National Society for the Prevention of Cruelty to Children) | 1999-2002 |
| Kevin Bond (Yorkshire Water) | 1999-2000 |
| Catrin Roberts (ESRC) | 1999-2000 |
| Ellen Townsend (ESRC) | 2000-2001 |
| Stephen Struthers (ESRC) | 2001-2003 |
| Lynne Cameron (Pro-Dean, Research, Faculty of Economics, Social Sciences and Law, University of Leeds) | 2002-2004 |
| John Fisher (Pro-Vice Chancellor, Research, University of Leeds) | 2002-2004 |

Annex D - Other Activities

1. Conferences and Seminars organised by CAVA

1.1. CAVA Launch

(2000) Launch of Cava, University of Leeds, 12 May 2000. Speakers included Mary MacLeod, Director of the National Family and Parenting Institute, and Professor Janet Finch.

1.2. Strands 1 and 2 Workshops

(1999) CAVA Strands 1 and 2 Workshop One. Frameworks for Understanding Policy and Culture, University of Leeds,  29 October 1999. See Annex A for papers and speakers.

(2000) CAVA Strands 1 and 2 Workshop Two. Statistics and Theories for Understanding Social Change, University of Leeds, 21 January 2000. See Annex A for papers and speakers.

(2000) CAVA Strands 1 and 2 Workshop Three. Analysing Policy Change and Implementation, University of Leeds, 11 February 2000. See Annex A for papers and speakers.

(2000) CAVA Strands 1 and 2 Workshop Four. Methodologies for Researching Moral Agency, University of Leeds, 17 March 2000. See Annex A for papers and speakers.

(2000) CAVA Strands 1 and 2 Workshop Five. New Conceptualisations of Care, Values and Welfare, University of Leeds, 5 May 2000. See Annex A for papers and speakers.

(2000) CAVA Strands 1 and 2 Workshop Six. Cross-National Perspectives on Care, Values and Welfare, University of Leeds, 16 June 2000. See Annex A for papers and speakers.

1.3. Strand 4 International Seminars

(2001) CAVA International Seminar One: New Divisions of Labour? University of Leeds. 19-20 January 2001.

- Björnberg, U. (2001) ‘Ideology and choice in Swedish family policy for working parents’. CAVA International Seminar One: New Divisions of Labour?, University of Leeds, 19-20 January 2001.

- Hancock, L. (2001) ‘Reshaping the Australian settlement: changing work, welfare and families’. CAVA International Seminar One: New Divisions of Labour?, University of Leeds, 19-20 January 2001.

- Land, H. (2001) ‘Spheres of care in Britain: separate and unequal?’. CAVA International Seminar One: New Divisions of Labour?, University of Leeds, 19-20 January 2001.

- Nyberg, A. (2001) ‘Economic power, work and gender’. CAVA International Seminar One: New Divisions of Labour?, University of Leeds, 19-20 January 2001.

- Orloff, A. (2001) ‘Welfare reform, liberalism and full-time care in the USA’. CAVA International Seminar One: New Divisions of Labour?, University of Leeds, 19-20 January 2001.

- Plantenga, J. (2001) ‘Equality, part-time work and the Netherlands polar model’. CAVA International Seminar One: New Divisions of Labour?, University of Leeds, 19-20 January 2001.

(2001) CAVA International Seminar Two: Divorce, Separation and Changing Family Practices. University of Leeds, 21-23 September 2001.

- Brinkgreve, C. (2001) 'Divorce and the Increasingly Fluid Boundaries of Childhood in The Netherlands'. CAVA International Seminar Two: Divorce, Separation and Changing Family Practices, University of Leeds, 21-23 September 2001.

- Hogan, D. (2001) 'Changing Families, Changing Childhoods: Separation, Divorce and Family Life in Ireland'. CAVA International Seminar Two: Divorce, Separation and Changing Family Practices, University of Leeds, 21-23 September 2001.

- McClean, M. (2001) 'Divorcing Families: The Economic Realities'. CAVA International Seminar Two: Divorce, Separation and Changing Family Practices, University of Leeds, 21-23 September 2001.

- Moxnes, K. (2001) 'What Helps, What Hurts? Children's Experiences of Parental Divorce in Norway'. CAVA International Seminar Two: Divorce, Separation and Changing Family Practices, University of Leeds, 21-23 September 2001.

- Nemenyi, M. (2001) 'Political, Scientific and Everyday Discourses on the Family in Post-Socialist Hungary'. CAVA International Seminar Two: Divorce, Separation and Changing Family Practices, University of Leeds, 21-23 September 2001.

- Pike, L. (2001) 'Heads or Tails, There Are No Real Winners. An Australian Perspective of Outcomes for Contact or Residential Single Fathers'. CAVA International Seminar Two: Divorce, Separation and Changing Family Practices, University of Leeds, 21-23 September 2001.

(2002) CAVA International Seminar Three: Friendship and Non-Conventional Partnership: Comparative Perspectives. University of Leeds, 25-27 January 2002.

- Adam, B. (2002) ‘Care, Intimacy and Partnering among Gay Men’. CAVA International Seminar Three: Friendship and Non-Conventional Partnership: Comparative Perspectives, University of Leeds, 25-27 January 2002.

- Bawin-Legros, B. (2002) ‘Intimacy and a New Postmoral Sentimental Order?’. CAVA International Seminar Three: Friendship and Non-Conventional Partnership: Comparative Perspectives, University of Leeds, 25-27 January 2002.

- Budgeon, S. and Roseneil, S. (2002) ‘Friendship and Non-Conventional Partnerships: the CAVA Project’. CAVA International Seminar Three: Friendship and Non-Conventional Partnership: Comparative Perspectives, University of Leeds, 25-27 January 2002.

- Levin, I. (2002) ‘Living Apart Together - One Couple, Two Homes’. CAVA International Seminar Three: Friendship and Non-Conventional Partnership: Comparative Perspectives, University of Leeds, 25-27 January 2002.

- Pahl, R. (2002) ‘Unpacking Friendships in Personal Communities’. CAVA International Seminar Three: Friendship and Non-Conventional Partnership: Comparative Perspectives, University of Leeds, 25-27 January 2002.

- Stacey, J. (2002) ‘Fellow Families? Gay Male Intimacies and Kinship in a Global Metropolis’. CAVA International Seminar Three: Friendship and Non-Conventional Partnership: Comparative Perspectives, University of Leeds, 25-27 January 2002.

(2002) CAVA International Seminar Four: Collective Interventions on the Terrain of Parenting and Partnering: Comparative Perspectives. University of Leeds, 1-2 November 2002.

- Bergman, S. (2002) ‘Collective Organising and Claim-making on Mothering/ Parenting in ‘Norden’: Blurring the Boundaries between the ‘Inside’ and the ‘Outside’’. CAVA International Seminar Four: Collective Interventions on the Terrain of Parenting and Partnering: Comparative Perspectives, University of Leeds, 1-2 November 2002.

- Dobrowolsky, A. and Jenson, J. (2002) ‘Shifting Patterns of Representation: ‘Children’, ‘Families’, ‘Women’’. CAVA International Seminar Four: Collective Interventions on the Terrain of Parenting and Partnering: Comparative Perspectives, University of Leeds, 1-2 November 2002.

- Gavanas, A. (2002) ‘Domesticating Masculinity and Masculinizing Domesticity in Contemporary US Fatherhood Politics’. CAVA International Seminar Four: Collective Interventions on the Terrain of Parenting and Partnering: Comparative Perspectives, University of Leeds, 1-2 November 2002.

- Williams, F., Roseneil, S. and Martin, G. (2002) ‘Collective Interventions on the Terrain of Care and Intimacy: The CAVA Project’. CAVA International Seminar Four: Collective Interventions on the Terrain of Parenting and Partnering: Comparative Perspectives, University of Leeds, 1-2 November 2002.

(2003) CAVA International Seminar Five: Moving and Caring: The Impact of Migration on Kinship and Care. University of Leeds, 18–19 September 2003.

- Ackers, L. and Katariya, P. (2003) ‘Caring at a Distance’. CAVA International Seminar Five: Moving and Caring: The Impact of Migration on Kinship and Care, University of Leeds, 18–19 September 2003.

- Baldock, C. and Baldassar, L. (2003) ‘Long distance migration and transnational family relations between Australia and Europe’. CAVA International Seminar Five: Moving and Caring: The Impact of Migration on Kinship and Care, University of Leeds, 18–19 September 2003.

- Ballard, R. (2003) ‘Challenges to – and Transformations in – the Dynamics of Kinship and Marriage within Transnationally Extended South Asian Families’. CAVA International Seminar Five: Moving and Caring: The Impact of Migration on Kinship and Care, University of Leeds, 18–19 September 2003.

- Chamberlain, M. (2003) ‘Caribbean Kinship in a Global Setting’. CAVA International Seminar Five: Moving and Caring: The Impact of Migration on Kinship and Care, University of Leeds, 18–19 September 2003.

- Kofman, E. and Raghuram, P. (2003) ‘Transnationalism and Familial Relations - The Case of Skilled Migrants’. CAVA International Seminar Five: Moving and Caring: The Impact of Migration on Kinship and Care, University of Leeds, 18–19 September 2003.

- Warnes, T. (2003) ‘Older Migrants in Europe: Groups, Kinship Networks and Needs for Support and Care’. CAVA International Seminar Five: Moving and Caring: The Impact of Migration on Kinship and Care, University of Leeds, 18–19 September 2003.

1.4. Other CAVA Seminars

(2000) Women and the New Economy. Co-hosted by CAVA, Centre for Interdisciplinary Gender Studies, the Cabinet Office Women’s Unit, the Smith Institute and the Yorkshire and Humberside Government Office. University of Leeds, 15 May 2000. Speakers included Tessa Jowell MP.

(2001) Workshop on Research for Evidence-based Policy Making with Dr. Ray Pawson, the ESRC Centre for Evidence-based Policy and Practice and Professor Jennie Popay of the Campbell Collaboration.University of Leeds, 11 May 2001.

(2001) CAVA Workshop on Ethics. University of Leeds, 2 November 2001. Speakers: Linda Hogan, Eithne McLaughlin and Tom Shakespeare.

(2002) Social Movements and Social Welfare. One-day conference on behalf of the BSA Protest and Social Movements Study Group, University of Leeds, 17 January 2002.

(2002) The Defence of Marriage Act (DOMA) and American exceptionalism, or the "gay marriage" panic in the United States, Dr Barry Adam, University of Windsor. Joint Seminar with Centre for Interdisciplinary Gender Studies and Centre for Research on Family, Kinship & Childhood, University of Leeds, 24 January 2002.

(2002) CAVA Workshop on Care. University of Leeds, 15 February 2002. Speakers: Colin Barnes, Mary Daly and Selma Sevenhuijsen.

- (2002) ‘The Cycle of Deprivation: Thirty Years On’. Workshop to mark the 30th anniversary of Sir Keith Joseph’s speech. University of Leeds, 3 July 2002.

(2002) CAVA Initial Findings Seminar. University of Leeds, 23 May 2003.

- Duncan, S. (2003) 'Mothers, Care and Employment'. CAVA Initial Findings Seminar, University of Leeds, 23 May 2003.

- Irwin, S. (2003) 'Values, Care and Commitments amongst Parents of Primary School Children'. CAVA Initial Findings Seminar, University of Leeds, 23 May 2003.

- Mason, J. (2003) 'Transnational Kinship'. CAVA Initial Findings Seminar, University of Leeds, 23 May 2003.

- Roseneil, S. (2003) 'Friendship and Non-conventional Partnerships'. CAVA Initial Findings Seminar, University of Leeds, 23 May 2003.

- Smart, C. and Neale, B. (2003) 'Divorce and Marital Separation'. CAVA Initial Findings Seminar, University of Leeds, 23 May 2003.

- Williams, F. (2003) 'Collective Voices on Care and Intimacy'. CAVA Initial Findings Seminar, University of Leeds, 23 May 2003.

(2003) Work and Family at the High Water Mark of a 1950s Gender Culture, Dr. John Murphy, RMIT University, Melbourne. Joint Seminar with Centre for Interdisciplinary Gender Studies, University of Leeds, 22 October 2003.

(2004) Trace: a method for normative policy analysis from the ethic of care. Workshop by Selma Sevenhuijsen, University of Leeds, 27 May 2004.

(2004) Rethinking Care Relations, Family Lives and Policies. CAVA International Symposium, Weetwood Hall, Leeds, 3-4 December 2004.

- Duncan, S. (2004) ‘Class, Culture and Rationality: Mothers and Employment'. Rethinking Care Relations, Family Lives and Policies, CAVA International Symposium, Weetwood Hall, Leeds, 3-4 December 2004.

- Feder-Kittay, E. (2004) ‘Thinking Globally about Long-Term Care’. Rethinking Care Relations, Family Lives and Policies, CAVA International Symposium, Weetwood Hall, Leeds, 3-4 December 2004.

- Gerhard, U. (2004) ‘Theories of Individualisation from a Gender Perspective’. Rethinking Care Relations, Family Lives and Policies, CAVA International Symposium, Weetwood Hall, Leeds, 3-4 December 2004.

- Himmelweit, S. (2004) ‘Paying for Care’. Rethinking Care Relations, Family Lives and Policies, CAVA International Symposium, Weetwood Hall, Leeds, 3-4 December 2004.

- Irwin, S. (2004) ‘Individualisation: A Narrow Lens on Social Landscapes of Interconnection’. Rethinking Care Relations, Family Lives and Policies, CAVA International Symposium, Weetwood Hall, Leeds, 3-4 December 2004.

- Land, H. (2004) ‘Shifting the Basis of Care from Status to Contract: Some Policy Issues’. Rethinking Care Relations, Family Lives and Policies, CAVA International Symposium, Weetwood Hall, Leeds, 3-4 December 2004.

- Macleod, M. (2004) ‘The State and the Family: Can Government Get It Right?’. Rethinking Care Relations, Family Lives and Policies, CAVA International Symposium, Weetwood Hall, Leeds, 3-4 December 2004.

- Roseneil, S. (2004) ‘Sutured Selves, Queer Connections: Intimacy at the Cutting Edge of Individualization’. Rethinking Care Relations, Family Lives and Policies, CAVA International Symposium, Weetwood Hall, Leeds, 3-4 December 2004.

- Smart, C. (2004) ‘The Ethic of Justice Strikes Back: Family Law and the Rise of the New Paternity’. Rethinking Care Relations, Family Lives and Policies, CAVA International Symposium, Weetwood Hall, Leeds, 3-4 December 2004.

- Tronto, J. (2004) ‘Vicious Circles of Privatized Care’. Rethinking Care Relations, Family Lives and Policies, CAVA International Symposium, Weetwood Hall, Leeds, 3-4 December 2004.

- White, S. (2004) ‘Reciprocity, Care Work and Citizenship’. Rethinking Care Relations, Family Lives and Policies, CAVA International Symposium, Weetwood Hall, Leeds, 3-4 December 2004.

(2004-2005) Changing social norms, changing family law? ESRC Seminar Series.

1.5. Centre for Research on Family, Kinship and Childhood Seminars

May, V. (2001) ‘Lone motherhood in Finnish Women’s Life Stories’, 17 October 2001.

Harold, G. (2001) ‘Understanding How Conflict Between Parents Affects their Children’, 12 December 2001.

Bates, I. (2002) ‘Young People, Their Learning and the Family Context’, 23 January 2002.

Haskey, J. (2002) ‘Some Aspects of Social Statistics which you always want to know but never dared ask’, 20 February 2002.

MacLeod, M. (2002) ‘The Family and its Discontents’, 6 March 2002.

Scott, S. (2002) ‘Child Projects and the Project of Childhood’, 20 March 2002.

Heath, S. (2002) ‘Shared Households, Quasi-Communes and Neo-Tribes: Single Young Adults and the Redefinition of Intimacy’, 12 June 2002.

- Smart, C. (2002) ‘Kinship after Divorce’, 16 October 2002.

Green, J. (2003) Changes in women's expectations and experiences of childbirth 1987-2000. 5 February 2003.

Wade, A. (2003) "The pear never falls far from the tree": Changes in parenting over generations, 26 March 2003

Hadfield, L. and Mauthner, M. (2003) Sibling Relationships in Middle Childhood – Children’s Views, 15 October 2003.

Shaw, A. (2004) Infant death & the impact of a genetic diagnosis: some British Pakistani perspectives, 28 January 2004.

McNeish, D. (2004) Making Policy For Children: is research relevant? 21 April 2004.

Morrow, V. (2004) Searching for 'Social Capital' in children's accounts of network and neighbourhood, 23 June 2004.

1.6. ESRC Postmodern Kinship Seminar Series.

(1999) ESRC Postmodern Kinship Seminar Four: The Construction of Family/ Blood Ties. University of Leeds, 8 October 1999. Speakers: Graham Allen, Gill Dunne, Sarah Franklin and Bob Simpson.

(1999) ESRC Postmodern Kinship Seminar Five: Changing Families/ changing Childhoods. University of Leeds, 10 December 1999. Speakers: Julia Brannen, Allison James, Margaret O’Brien and Amanda Wade.

(2000) ESRC Postmodern Kinship Seminar Six: Family change and Policy. University of Leeds, 3 March 2000. Speakers: Louise Ackers, Lorraine Harding, Mavis Maclean, Fiona Williams.

1.7. ESRC Knowing Families Seminar Series.

(2002) ESRC Knowing Families Seminar One: Researching Families from Different Disciplinary Perspectives: Methodological Issues and Challenges. University of Leeds, 22 November 2002.

- Ackers, L. (2002) ‘Researching families from a socio-legal perspective’. ESRC Knowing Families Seminar One: Researching Families from Different Disciplinary Perspectives: Methodological Issues and Challenges, University of Leeds, 22 November 2002.

- Boyle, P. (2002) ‘Placing families’. ESRC Knowing Families Seminar One: Researching Families from Different Disciplinary Perspectives: Methodological Issues and Challenges, University of Leeds, 22 November 2002.

- Gillis, J. (2002) ‘Virtual families: a cultural approach’. ESRC Knowing Families Seminar One: Researching Families from Different Disciplinary Perspectives: Methodological Issues and Challenges, University of Leeds, 22 November 2002.

- Green, A. (2002) ‘Family support and care-delivery for young people with diabetes: a multidisciplinary, multi-methods, cross cultural comprison between Scotland and Italy’. ESRC Knowing Families Seminar One: Researching Families from Different Disciplinary Perspectives: Methodological Issues and Challenges, University of Leeds, 22 November 2002.

- Hollway, W. (2002) ‘Reaching the family dynamics that other methods don’t reach’. ESRC Knowing Families Seminar One: Researching Families from Different Disciplinary Perspectives: Methodological Issues and Challenges, University of Leeds, 22 November 2002.

- Jamieson, L. (2002) ‘Insights and blind spots: the sociology of families’. ESRC Knowing Families Seminar One: Researching Families from Different Disciplinary Perspectives: Methodological Issues and Challenges, University of Leeds, 22 November 2002.

(2003) ESRC Knowing Families Seminar Two: Researching Families Over Time: Longitudinal Approaches. University of Leeds, 7 March 2003.

- Dale, A. (2003) ‘The Strenghts and Limitations of Longitudinal Survey Data for Understanding Family Dynamics’. ESRC Knowing Families Seminar Two: Researching Families Over Time: Longitudinal Approaches, University of Leeds, 7 March 2003.

- Neale, B. (2003) ‘Time, Texture and Childhood: longitudinal qualitative’. ESRC Knowing Families Seminar Two: Researching Families Over Time: Longitudinal Approaches, University of Leeds, 7 March 2003.

- Scott, J. (2003) ‘Linked lives: family influence across the generations’. ESRC Knowing Families Seminar Two: Researching Families Over Time: Longitudinal Approaches, University of Leeds, 7 March 2003.

- Thomas, R. (2003) ‘Researching Young People's Lives Over and in Time: a longitudinal qualitative method’. ESRC Knowing Families Seminar Two: Researching Families Over Time: Longitudinal Approaches, University of Leeds, 7 March 2003.

(2003) ESRC Knowing Families Seminar Three: 'Evidence' for Policy? Connecting Family Research and Policy. University of Leeds, 16 May 2003.

- Frost, N. (2003) 'Linking evidence, policy and practice in family research - some issues and problems’. ESRC Knowing Families Seminar Three: 'Evidence' for Policy? Connecting Family Research and Policy, University of Leeds, 16 May 2003.

- Grundy, E. (2003) ‘Supporting exchanges between adult children and their parents: Implications for parental and child generations’. ESRC Knowing Families Seminar Three: 'Evidence' for Policy? Connecting Family Research and Policy, University of Leeds, 16 May 2003.

- Mason, J. and Smart, C. (2003) 'Extending the reach of qualitative family research'. ESRC Knowing Families Seminar Three: 'Evidence' for Policy? Connecting Family Research and Policy, University of Leeds, 16 May 2003.

- Melhuish, E. (2003) 'Evaluating Sure Start: an intervention for children, families and communities'. ESRC Knowing Families Seminar Three: 'Evidence' for Policy? Connecting Family Research and Policy, University of Leeds, 16 May 2003.

(2003) ESRC Knowing Families Seminar Four: Narrative, Identity and Self and Family and Relationship Research'. University of Leeds, 21 November 2003.

- Bornat, J. (2003) 'You're never to old to be a parent: older people's responses to family change’. ESRC Knowing Families Seminar Four: Narrative, Identity and Self and Family and Relationship Research', University of Leeds, 21 November 2003.

- Chamberlain, M. (2003) ‘Language, identity and Caribbean family narratives’. ESRC Knowing Families Seminar Four: Narrative, Identity and Self and Family and Relationship Research', University of Leeds, 21 November 2003.

- Lawler, S. (2003) 'Between choice and determinism: making a self through kinship narratives’. ESRC Knowing Families Seminar Four: Narrative, Identity and Self and Family and Relationship Research', University of Leeds, 21 November 2003.

- May, V. (2003) 'Narrative, Identity and Lone Motherhood’. ESRC Knowing Families Seminar Four: Narrative, Identity and Self and Family and Relationship Research', University of Leeds, 21 November 2003.

(2004) ESRC Knowing Families Seminar Five: Combining Qualitative and Quantitative Approaches in Family Research'. University of Leeds, March 2004.

- Clarke, L. (2004) ''Grandparenthood: a three-dimensional role at least!'. ESRC Knowing Families Seminar Five: Combining Qualitative and Quantitative Approaches in Family Research', University of Leeds, March 2004.

- Duncan, S. (2004) 'Combining intensive and extensive research: discovering issues and interpreting evidence'. ESRC Knowing Families Seminar Five: Combining Qualitative and Quantitative Approaches in Family Research', University of Leeds, March 2004.

- Edwards, R. and Gillies, V. (2004) 'Resources in Parenting: Rationale and Practice of a Mixed Methodology’. ESRC Knowing Families Seminar Five: Combining Qualitative and Quantitative Approaches in Family Research', University of Leeds, March 2004.

- Irwin, S. (2004) 'Water through the sand? locating values in changing family life'. ESRC Knowing Families Seminar Five: Combining Qualitative and Quantitative Approaches in Family Research', University of Leeds, March 2004.

(2004) ESRC Knowing Families Seminar Six: Visualising Families: Researching the Visual & Material Cultures of Family Life. University of Leeds, June 2004.

- Coffey, A. (2004) 'Ethnography for the Digital Age'. ESRC Knowing Families Seminar Six: Visualising Families: Researching the Visual & Material Cultures of Family Life, University of Leeds, June 2004.

- Holliday, R. (2004) 'Filming the Closet: the role of video diaries in researching sexualities’. ESRC Knowing Families Seminar Six: Visualising Families: Researching the Visual & Material Cultures of Family Life, University of Leeds, June 2004.

- Silva, E. (2004) 'What's to be seen? Materiality and relationships in researching the domestic'. ESRC Knowing Families Seminar Six: Visualising Families: Researching the Visual & Material Cultures of Family Life, University of Leeds, June 2004.

- Wade, A. (2004) 'The weight of the world: memorabilia and the telling of lives'. ESRC Knowing Families Seminar Six: Visualising Families: Researching the Visual & Material Cultures of Family Life, University of Leeds, June 2004.

1.8. Centre for Research on Family, Kinship & Childhood Annual Lectures

2000 (Davidoff, L.) The Legacy of the Nineteenth Century Bourgeois Family and the Wool Merchants Son.  Annual Lecture, University of Leeds, June 2000.

2001 (Jamieson, L.) Recent Histories of Intimacy: Family, Kinship and Childhood. Annual Lecture, University of Leeds, March 2001.

2002 (Macleod, M.) The Family and its Discontents. Annual Lecture, University of Leeds, March 2002.

(2003) Frameworks of Understanding: Multidisciplinary Perspectives on Childhood. Annual Conference, University of Leeds, 6 June 2003.

- Aldrige, J. (2003) ‘Medical Practice and New Thinking about Children’. Frameworks of Understanding: Multidisciplinary Perspectives on Childhood, Centre for Research on Family, Kinship & Childhood Annual Conference, University of Leeds, 6 June 2003.

- Grieve, K. (2003) ‘Children’s Rights and Parental Responsibilities: a view from practice’. Frameworks of Understanding: Multidisciplinary Perspectives on Childhood, Centre for Research on Family, Kinship & Childhood Annual Conference, University of Leeds, 6 June 2003.

- McKendrick, J. (2003) ‘But where are the maps? Contemporary geographies of children and childhood’. Frameworks of Understanding: Multidisciplinary Perspectives on Childhood, Centre for Research on Family, Kinship & Childhood Annual Conference, University of Leeds, 6 June 2003.

- Neale, B. and Flowerdew, J. (2003) ‘Enduring Families: Children’s long term reflections on family life after divorce’. Frameworks of Understanding: Multidisciplinary Perspectives on Childhood, Centre for Research on Family, Kinship & Childhood Annual Conference, University of Leeds, 6 June 2003.

- Phoenix, A. (2003) ‘Beyond passive innocence: Children, young people, racialisation, gender and social class’. Frameworks of Understanding: Multidisciplinary Perspectives on Childhood, Centre for Research on Family, Kinship & Childhood Annual Conference, University of Leeds, 6 June 2003.

- Such, E. (2003) ‘Being responsible and responsible beings: children’s understanding of responsibility’. Frameworks of Understanding: Multidisciplinary Perspectives on Childhood, Centre for Research on Family, Kinship & Childhood Annual Conference, University of Leeds, 6 June 2003.

- Woodhead, M. (2003) ‘A place for Developmental Psychology in Childhood Studies?’. Frameworks of Understanding: Multidisciplinary Perspectives on Childhood, Centre for Research on Family, Kinship & Childhood Annual Conference, University of Leeds, 6 June 2003.

(2004) Lives and Times: Intergenerational Relationships and Intergenerational Research. Centre for Research on Family, Kinship & Childhood Annual Conference, University of Leeds, 21 May 2004.

- Bawin-Legros, B. (2004) ‘Intergenerational relationships: selective affinities’. Lives and Times: Intergenerational Relationships and Intergenerational Research, Centre for Research on Family, Kinship & Childhood Annual Conference, University of Leeds, 21 May 2004.

- Hockey, J. and Robinson, V. (2004) ‘A cross-generational study of the making of heterosexual relationships’. Lives and Times: Intergenerational Relationships and Intergenerational Research, Centre for Research on Family, Kinship & Childhood Annual Conference, University of Leeds, 21 May 2004.

- McNulty, A. (2004) ‘Putting ‘teenage pregnancy’ in its place: intergenerational research’. Lives and Times: Intergenerational Relationships and Intergenerational Research, Centre for Research on Family, Kinship & Childhood Annual Conference, University of Leeds, 21 May 2004.

- Nilsen, A. (2004) ‘Contexts of intergenerational relationships: a comparative study’. Lives and Times: Intergenerational Relationships and Intergenerational Research, Centre for Research on Family, Kinship & Childhood Annual Conference, University of Leeds, 21 May 2004.

- Wade, A. (2004) ‘Continuity and change in parent-child relationships over three generations’. Lives and Times: Intergenerational Relationships and Intergenerational Research, Centre for Research on Family, Kinship & Childhood Annual Conference, University of Leeds, 21 May 2004.

1.9. Other CRFKC Seminars

(2000) ‘Quality in Pre-school and Childcare Provision, Half day Seminar for teachers and policy makers, 13 May 2000

(2000) ‘Ascertaining the Wishes and Feelings of the Child’, Day Seminar for family law practitioners: 22 June 2000.

(2000) Children’s Experience of Post-Divorce Family Life. University of Leeds, 15 November 2000

(2001) Are we listening to children? Divorce and Changing Families. Practitioners’ Seminar, University of Leeds, 16 February 2001.

(2001) The Trials, Tribulations and Triumphs of Co-Parenting. Practitioners’ Seminar, University of Leeds, 8 June 2001.

(2001) Children, Family Law and Family Conflict. One day conference organised in collaboration with Young Voice and the Social Science Research Unit, Institute of Education, University of London, 26 September 2001.

(2002) Culture, Religion and Family Life. One day conference organised for the BSA Family Studies Group, February 2002.

(2002) Organiser and Chair, Researching Children: The Methodological Challenge – Annual Conference for the Centre for Research on Family, Kinship and Childhood, 24 May 2002.

(2002) Kinship after Divorce. Centre for Research on Family, Kinship and Childhood, University of Leeds, 16 October 2002.

(2005) Childhood, Youth, Personal Relationships and the Life Course: Developing a sociology of Young Lives, One Day international conference, University of Leeds, April 2005

1.10. Centre for Interdisciplinary Gender Studies Work in Progress Workshops

Richards, B. (1999) The Work of the Equal Opportunities Unit and the Women's Advisory Group in Leeds, 20 October 1999.

Flannery, D. (1999) Sibling Love and Queer Subjectivity, 3 November 1999.

Burgess, G. (1999) Lone Mothers and the New Deal: Rational and Moral Actions as Mothers and Workers, 17 November 1999.

Heenan, C. (1999) Is There a Future for Feminist Therapy?, 1 December 1999.

Alimo-Metcalfe, B. (2000) Gender and Leadership: All Snakes and No  Ladders?, 26 January 2000.

Eldred, J. (2000) Older Christian Women's Communities: Lived Resurrections?, 9 February 2000.

Hollway, W. (2000) Expert Discourses on Mothering: Discursive Positioning and the Real, 23 February 2000.

Kamenou, N. (2000) The Career Progression of Ethnic Minority Women in English Organisations, 8 March 2000.

Swan, M. (2000) What has Late Old English Prose to do with Women?, 22 March 2000.

Cooper, B. (2000) The Role of Empathy in Teacher/Pupil Relationships, 5 April 2000.

#### L’Estrange, E. (2000) Going Beyond the Curtain: Childbirth Narrative in the Late Middle Ages, 4 October 2000.

## Gerodetti, N. (2000) Sexualities and the Swiss Nation, 18 October 2000.

##### Eves, A. (2000) She’s Got the Look: Butch / Femme Genders and Lesbian Aesthetics, 1 November 2000.

McLaughlin, J. (2000) Feminist Technology Assessment: Evaluating the Social and Ethical Impacts of Ultra Sound Technology, 22 November 2000.

##### Liddington, J. (2000) Emily Bronte and Anne Lister: early Victorian narratives of rivalry and revenge, 29 November 2000.

Aspden, K. (2001) The University of Leeds and the Yorkshire Ripper, 24 January 2001.

Leonardi, V. (2001) Gender Issues in Translation Studies, 7 February 2001.

Valier, C. (2001) Myra Hindley: Notoriety and Punishment, 21 February 2001.

Ferguson, J. (2001) Using Queer Theory to Explore Health and Homosexuality, 7 March 2001.

Burgess, G. (2001) Lone Mothers, Morality and Caring: Thoughts Post-Fieldwork, 21 March 2001.

Irwin, S. (2001) Claims and Interdependence: The Changing Landscape of Social Life, 25 April 2001.

Smith, D. (2001) Lesbian Lifestyles in the Greentrified Spaces of the Upper Calder Valley, 16 May 2001.

Gerodetti, N. (2001) ‘Disenfranchised Agents: Pressure Groups and Sexual Politics during the Unification of Swiss Criminal Law’, 7 November 2001.

Siegfried, S. (2001) ‘Painting as Woman: Ingres’s Raphael and the Fornarina’, 20 November 2001.

Gough, B. (2001) ‘Discourse Analysis, Psychoanalysis and Masculinities’, 5 December 2001.

Budgeon, S. and Roseneil, S. (2002) ‘Gender, Sexuality and Practices of Friendship’, 6 February 2002

Rodd, M. and Bartholomew, H. (2002) ‘Not Twinkling but Glimmering: Young Women Mathematics Undergraduates’ Strategies for Survival and Expectations of Success’, 27 February 2002.

Garthwaite, A. (2002) ‘Feminist Video as Resistance and Empowerment’, 13 March 2002.

Lee, H. (2002) ‘Queer(y)ing Health Promotion’, 1 May 2002.

Williams, L. (2002) ‘Visual Representations of Masculinities in late Twentieth-Century China’, 5 June 2002.

Colley, H. (2002) ‘Gender, Biography and Vocational Culture: the Making of a Child Care Tutor in FE’, 23 October 2002.

Aspden, K. (2002) “The Richest Unmarried Woman in England”: The Life and Times of Dorothy Paget (1905-60), Racehorse Owner’, 6 November 2002.

Hines, S. (2002) ‘Absent Subjects: Feminist Discourse and Trans-Masculinities’, 4 December 2002.

Flannery, D. (2003) ‘Sibling love, queer subjectivity and writing on AIDS: three forces in Chuck Palahniuk and Jamaica Kincaid', 5 February 2003.

Liddington, J. (2003) ‘Votes for women: political past, private lives and realms of memory', 19 March 2003.

Holliday, R. and Potts, T. (2003) ‘All that Glitters: Gender, Sexuality and Kitsch', 28 May 2003.

Ackers, L. (2003) ‘Managing Work and Family Life in Peripatetic Careers: the Experiences of Mobile Women Scientists in the EU’, 22 October 2003.

Wade, A. (2003) ‘Love and Commitment in Narratives of Fathering’, 19 November 2003.

Plock, P. (2003) ‘Censorship and Sensibility: the religious male body in Counter Reformation Rome, gender and male nudity in Nicolas Poussin’s Venus and Adonis’, 10 December 2003.

## Liddington, J. (2004) Votes for Women Everywhere: Suffrage Historiography & New Regional Evidence, 6 October 2004.

### Roseneil, S. and Marshall, Y. (2004) The Common Ground Project - An Archaeology of Greenham: Queering the Memorialising of the Cold War, 24 November 2004.

## Heaphy, B. (2004) Gender, Sexuality & Aging, 1 December 2004.

Shipman, R. (2005) Same-Sex Marriage: Ideas from an Empirical Study, 16 February 2005.

Knott, K. and Franks, M. (2005) A Gender Perspective on Religion in Two Secular Institutions, 16 March 2005.

1.11. Centre for Interdisciplinary Gender Studies Visiting Speaker Seminars

Rowbotham, S. (1999) New Entry Points: Gender and Labour in US History 1969-99, 10 November 1999.

Vélu, C. (1999) Feminism in Contemporary France: When Theory Meets Practice, 24 November 1999.

Adam, A. (2000) A Feminist Ethics of Technology, 2 February 2000.

MacInnes, J. (2000) The Crisis of Masculinity and the End of Gender, 16 February 2000.

Durham, M. (2000) Fascism and the Construction of Gender, 1 March 2000.

Scott, J. (2000) Working Mothers: Public Attitudes and State Policies, 15 March 2000.

Kaplan, C. (2000) Femininity and Feminism: Whose Problem?, 10 May 2000.

Duruz, J. (2000) Rewriting the Village, 8 November 2000.

Johnson, C. (2000) The Bodies That Should Not Touch (In Public): Challenging Heteronormative Citizenship and the Politics of Passing, 6 December 2000.

Lennon, K. (2000) Borderlands and Gendered Homes, 17 January 2001.

Abu-Haidar, F. (2001) The Liberating Voice of Literature: Women and Writing in the Middle East, 31 January 2001.

Battersby, C. (2001) Foucault, Modernity and the Question of Gender, 14 February 2001.

Ifekwunigwe, J. (2001) Re-membering the War: The Science and Fiction of Feminist Ethnography, 28 February 2001.

Shuttleworth, S. (2001) Tickling Babies: Gender, Authority and Baby Science in the Late 19th Century, 14 March 2001.

Hird, M. (2001) Sexual Difference: The Big Lie, 18 April 2001.

Geraghty, C. (2001) Rethinking 50s Cinema: Kay Kendall, Feminism and the "New Look"’, 9 May 2001.

Frosh, S. (2002) ‘Taking the Stand: Exploring the Positioning of Subjects in Masculinities’, 13 February 2002.

Battersby, C. (2002) ‘The Postmodern Sublime and the Female Sublime’, 24 April 2002.

Berlant, L. (2002) ‘Remembering Love, Forgetting Everything Else: Now, Voyager’, 29 May 2002.

O’Grady, H. (2002) ‘Women and Self-Surveillance’, 9 October 2002.

Herman, D. (2002) ‘“Bad Girls Changed My Life”: Homonormative Values in a  Women’s Prison Drama’, CIGS Annual Lecture, 6 November 2002.

Gorman, R. and Mojab, S. (2002) ‘Testimony and Trauma: Toward a Dialectical Feminist Understanding of Women and War’, 20 November 2002.

Lewis, R. (2001) ‘Orientalising Gender: The Performance of Ottoman Femininity in the Representation of the Harem’, 28 November 2001.

Mottier, V. (2003) Welfare states, gender regimes and eugenics: a comparative approach, 26 February 2003.

Doan, L. (2003) Sapphic Reactionaries? The Conservative Contours of Sapphic Modernity, 30 April 2003.

## Fairbairns, Z. (2004) The Personal is Political, and Fiction is Both - Reflections of a Feminist Novelist, 20 October 2004.

## Binnie, J. (2004) Theorising Queer Globalisation, 10 November 2004.

## Hollows, J. (2005) Are Feminists Afraid to Go Home? Feminism, Post-Feminism & Domesticity, 2 March 2005.

## 1.12. Other CIGS seminars

2000 (Roseneil, S. and Hogan, L.) Gendering Ethics / The Ethics of Gender. Centre for Interdisciplinary Gender Studies, Two day Conference, University of Leeds. 23-24 June 2000.

- Abozaglo, P. (2000) ‘Gender and Development Issues North and South: A Comparative Praxis’. Gendering Ethics / The Ethics of Gender, Centre for Interdisciplinary Gender Studies, University of Leeds. 23-24 June 2000.

- Cockburn, C. (2000) ‘Gender and the Consolidation of Peace’. Gendering Ethics / The Ethics of Gender, Centre for Interdisciplinary Gender Studies, University of Leeds. 23-24 June 2000.

- Hunter, L. (2000) ‘Legitimating Differentiated Public Voices’. Gendering Ethics / The Ethics of Gender, Centre for Interdisciplinary Gender Studies, University of Leeds. 23-24 June 2000.

- Jantzen, G. (2000) ‘Flourishing: Towards an Ethics of Natality’. Gendering Ethics / The Ethics of Gender, Centre for Interdisciplinary Gender Studies, University of Leeds. 23-24 June 2000.

- Lovibond, S. (2000) ‘’Gendering’ as an Ethical Concept’. Gendering Ethics / The Ethics of Gender, Centre for Interdisciplinary Gender Studies, University of Leeds. 23-24 June 2000.

- Macnay, L. (2000) ‘Agency and Expectation in Feminist and Social Theory’. Gendering Ethics / The Ethics of Gender, Centre for Interdisciplinary Gender Studies, University of Leeds. 23-24 June 2000.

- Mama, A. (2000) ‘Duplicity or Dissent? Feminist Ethics in Authoritarian Contexts’. Gendering Ethics / The Ethics of Gender, Centre for Interdisciplinary Gender Studies, University of Leeds. 23-24 June 2000.

- Latif Palijo, A. (2000) ‘Women, Human Rights, Traditions and Ethics’. Gendering Ethics / The Ethics of Gender, Centre for Interdisciplinary Gender Studies, University of Leeds. 23-24 June 2000.

- Ramamurthy, P. (2000) ‘Feminist Critiques of Development: Global Modernism, Ethno-philosophy or Radical Cosmopolitics?’. Gendering Ethics / The Ethics of Gender, Centre for Interdisciplinary Gender Studies, University of Leeds. 23-24 June 2000.

- Sevenhuijsen, S., Williams, F. and Smart, C. (2000) ‘Towards a New Political Ethics of Care’. Gendering Ethics / The Ethics of Gender, Centre for Interdisciplinary Gender Studies, University of Leeds. 23-24 June 2000.

- Tronto, J. (2000) ‘Time’s Place’. Gendering Ethics / The Ethics of Gender, Centre for Interdisciplinary Gender Studies, University of Leeds. 23-24 June 2000.

- Yural-Davis, N. (2000) ‘Transversal Ethics and Conflic Resolution - Some Preliminary Ponderings’. Gendering Ethics / The Ethics of Gender, Centre for Interdisciplinary Gender Studies, University of Leeds. 23-24 June 2000.

2001 (Roseneil, S.) Luce Irigaray in Dialogue. Centre for Interdisciplinary Gender Studies and CentreCATH, Leeds Art Gallery, 22-24 June 2001.

1.13. Other Seminars Organised by CAVA Members

(1998-2000) Parenting, motherhood & paid work: rationalities and ambivalences.  ESRC Seminar Series.

(1999-2002) Social Capital and Communities Seminar Series, University of Bradford/Bradford New Deal for Communities.

(2001) Globalization and Political Protest, North and South. International Sociological Association RC 47 Conference, New York University, USA, April 2001

(2001) New Sexualities. ESRC Seminar under the Seminar Series on ‘Sexualities: Representation and Lived Experience’, University of Leeds, 7 December 2001.

(2002) BSA Protest and Social Movements Study Group Session. Including a round table discussion of anti-globalization movements. BSA Annual Conference, University of Leicester, 27 March 2002.

(2002) Feminist Challenges to Sociological Theory. World Congress of Sociology, Brisbane, Australia, July 2002.

(2002) Social Movements and Social Welfare. World Congress of Sociology, Brisbane, Australia, July 2002.

(2002) Feminist Theory Anniversary Lecture by Judith Butler, UCL, 8 March 2002.

(2003) Dialoguing across divisions in British Social Psychology. Seminar series funded by the British Psychological Society (£3K). 4 meetings between September and December 2003.

(2003) PHARE Syposium on Science Policy, Mobility and Brain Drain in the EU and Candidate Countries. University of Leeds, 27-28 July 2003.

(2004) ESRC Non-Familial Relationships Across the Lifecourse Seminar Series (organised by Allan, G., Crow, G., Jamieson, L. and Roseneil, S.)

(2004) ESRC Non-Familial Relationships Across the Lifecourse Seminar One: Unconventional Couples. University of Leeds, 20 February 2004.

- Heckert, J. (2004) ‘Resisting Orientation: relationships across the borders’. ESRC Non-Familial Relationships Across the Lifecourse Seminar One: Unconventional Couples, University of Leeds, 20 February 2004.

- Holmes, M. (2004) 'Love lives at a distance: couple in distant relationships'. ESRC Non-Familial Relationships Across the Lifecourse Seminar One: Unconventional Couples, University of Leeds, 20 February 2004.

- Roseneil, S. (2004) ‘Unconventional Couples: Findings from a Longitudinal Study of Individualized Lives’. ESRC Non-Familial Relationships Across the Lifecourse Seminar One: Unconventional Couples, University of Leeds, 20 February 2004.

- Weeks, J. (2004) ‘Unconventional couples across the lifecourse’. ESRC Non-Familial Relationships Across the Lifecourse Seminar One: Unconventional Couples, University of Leeds, 20 February 2004.

(2004) ESRC Non-Familial Relationships Across the Lifecourse Seminar Two: Friendship. University of Keele, 24 May 2004.

- Budgeon, S. (2004) ‘Thinking Through Friendship: Formations of Sociality in Late Modernity'. ESRC Non-Familial Relationships Across the Lifecourse Seminar Two: Friendship, University of Keele, 24 May 2004.

- Dorrington, L. (2004) ‘Identity.com: The presentation of identity in internet Chat Rooms’. ESRC Non-Familial Relationships Across the Lifecourse Seminar Two: Friendship, University of Keele, 24 May 2004.

- Hey, V. (2004) ‘Retheorising Friendship: Sociality in Late Modernity’. ESRC Non-Familial Relationships Across the Lifecourse Seminar Two: Friendship, University of Keele, 24 May 2004.

- Pahl, R. (2004) ‘Friendship: The One Good Thing?’. ESRC Non-Familial Relationships Across the Lifecourse Seminar Two: Friendship, University of Keele, 24 May 2004.

(2004) ESRC Non-Familial Relationships Across the Lifecourse Seminar Three: Caring Relationships. University of Edinburgh, 13 September 2004.

- Anderson, B. (2004) “"They’re foreign, illegal and very, very small”: the role of “race” in negotiating employment relations in private households’. ESRC Non-Familial Relationships Across the Lifecourse Seminar Three: Caring Relationships, University of Edinburgh, 13 September 2004.

- Pockney, R. (2004) ‘Friend or facilitator: people with learning disabilities and their paid carer’. ESRC Non-Familial Relationships Across the Lifecourse Seminar Three: Caring Relationships, University of Edinburgh, 13 September 2004.

- Riddell, S. (2004) ‘Direct payments for disabled people and non-familial caring relationships: tensions in policy and practice’. ESRC Non-Familial Relationships Across the Lifecourse Seminar Three: Caring Relationships, University of Edinburgh, 13 September 2004.

- Ungerson, C. (2004) 'Dependency in old age and non-familial intimate relationships'. ESRC Non-Familial Relationships Across the Lifecourse Seminar Three: Caring Relationships, University of Edinburgh, 13 September 2004.

(2004) ESRC Non-Familial Relationships Across the Lifecourse Seminar Four: Neighbours. University of Southampton, 6 December 2004.

- Boyce, I. (2004) 'Neighbourliness and privacy on a deprived estate'. ESRC Non-Familial Relationships Across the Lifecourse Seminar Four: Neighbours, University of Southampton, 6 December 2004.

- Halford, S. (2004) 'Organisational space and friendships at work'. ESRC Non-Familial Relationships Across the Lifecourse Seminar Four: Neighbours, University of Southampton, 6 December 2004.

- Savage, M. (2004) 'The ethics of elective belonging'. ESRC Non-Familial Relationships Across the Lifecourse Seminar Four: Neighbours, University of Southampton, 6 December 2004.

- Stokoe, L. (2004) 'Neighbour disputes'. ESRC Non-Familial Relationships Across the Lifecourse Seminar Four: Neighbours, University of Southampton, 6 December 2004.

(2005) ESRC Non-Familial Relationships Across the Lifecourse Seminar Five: Learning from Non-Familial Relationships. University of Edinburgh, 6 June 2005.

- Allan, G., Crow, G., Jamieson, L., Morgan, D. and Roseneil, S. (2005) Round Table Discussion. ESRC Non-Familial Relationships Across the Lifecourse Seminar Five: Learning from Non-Familial Relationships, University of Edinburgh, 6 June 2005.

- Milne, S. (2005) ‘Children’s relationships with non-familial adults’. ESRC Non-Familial Relationships Across the Lifecourse Seminar Five: Learning from Non-Familial Relationships, University of Edinburgh, 6 June 2005.

- Reynolds, J. (2005) 'Patterns in the telling: single women’s intimate relationships with men' across the life-course’. ESRC Non-Familial Relationships Across the Lifecourse Seminar Five: Learning from Non-Familial Relationships, University of Edinburgh, 6 June 2005.

- Simpson, R. (2005) ‘The Intimate Relationships of Contemporary Spinsters’. ESRC Non-Familial Relationships Across the Lifecourse Seminar Five: Learning from Non-Familial Relationships, University of Edinburgh, 6 June 2005.

2. Visiting Fellows received by CAVA Research Group Members

(1999-2000) Professor Selma Sevenhuijsen, University of Utrecht, for ESRC Seminars, 8 October 1999, 10 December 1999 and 3 March 2000.

(2000) Professor Kimiko Kimoto, Social Sciences, University of Hitotsubashi, Tokyo, Japan, 11-12 May 2000.

(2000) Dr Deborah Diniz, University of Brasilia. Visiting Fellow in the Centre for Interdisciplinary Gender Studies, funded by Ford Foundation and British Council, June-September 2000.

(2000) Professor Anna Yeatman, Professor of Sociology, Macquarie University, Sydney, Australia, 21-22 September 2000.

(2000) Sue Howard, Research Manager, The Children’s Commission of Queensland, Visiting Fellow in the Centre for Research on Family, Kinship & Childhood, September 2000.

(2000) Dr Jean Duruz, Dept of Cultural Studies, University of South Australia, Visiting Fellow in the Centre for Interdisciplinary Gender Studies, December 2000

(2000) Professor Judith Halberstam, Dept of English, University of California, San Diego, December 2000

- (2000) Dr Carol Johnson, Dept of Politics, University of Adelaide, Visiting Fellow in the Centre for Interdisciplinary Gender Studies, December 2000

(2001) Professor Ulla Bjornberg, Sociologistia Inst, Goteborgs Universitet, Sweden, Contributor to International Seminar, 19-21 January 2001.

(2001) Professor Linda Hancock, University of Melbourne, Contributor to International Seminar, 19-21 January 2001.

- (2001) Professor Hilary Land, University of Bristol, Contributor to International Seminar, 19-21 January 2001.

- (2001) Professor Anita Nyberg, University of Stockholm, Sweden, Contributor to International Seminar, 19-21 January 2001.

- (2001) Professor Ann Orloff, Dept of Sociology, Northwestern University, USA, Contributor to International Seminar, 19-21 January 2001.

- (2001) Professor Janneke Plantenga, Institute of Economics, Utrecht, The Netherlands, Contributor to International Seminar, 19-21 January 2001.

- (2001) Dr Alexandra Dobrowsky, Asst professor, Dept of Political Science, St Mary’s University, Halifax, Nova Scotia, Canada. On behalf of groupe de recherche sur les aspects sociaux  de la santé et de la prévention (GRASP), Université de Montréal, 16 May 2001.

(2001) Dr Brinda Bose, Dept of English, University of Delhi, Visiting Fellow in the Centre for Interdisciplinary Gender Studies, funded by Leverhulme Interchange, June 2001.

- (2001) Dr Radhika Singha, Dept of History, University of Delhi, Visiting Fellow in the Centre for Interdisciplinary Gender Studies, funded by Leverhulme Interchange, June 2001.

- (2001) Professor Gina Yu, Dept of Cultural Studies, Dongguk University, Seoul, July 2001

- (2001) Professor Christine Brinkgreve, University of Utrecht, The Netherlands, Contributor to International Seminar, 21-23 September 2001

- (2001) Dr Diane Hogan, Trinity College, Dublin, Contributor to International Seminar, 21-23 September 2001

- (2001) Professor Mavis MacLean, University of Oxford, Contributor to International Seminar, 21-23 September 2001

- (2001) Professor Kari Moxnes, University of Trondheim, Norway, Contributor to International Seminar, 21-23 September 2001

- (2001) Dr Maria Nemenyi, Hungarian Academy of Sciences, Contributor to International Seminar, 21-23 September 2001

- (2001) Dr Lis Pike, Edith Cowan University, Perth, Contributor to International Seminar, 21-23 September 2001

- (2001) Professor Anne Smith, University of Otago, New Zealand, Contributor to International Seminar, 21-23 September 2001

(2001-2) Dr Vanessa May, Åbo Akademi University, Åbo, Finland, Funded by the Academy of Finland and Åbo Akademi University Foundation’s Research Institute, Visiting Fellow in the Centre for Research on Family, Kinship & Childhood, 21 September 2001 – 30 March 2002.

- (2001) Sara Elden, Department of Sociology, University of Lund, Sweden, November 2001.

(2001) Professor Sharzad Mojab, Ontario Institute for Studies in Education. November 2001.

(2001) Rachel Gorman, Ontario Institute for Studies in Education, November 2001.

(2001) Dr. Linda Hogan, Department of Philosophy, University College Dublin, Contributor to CAVA Values and Ethics Workshop, 2 November 2001.

(2001) Professor Don Kulick, Department of Anthropology, New York University, December 2001.

- (2002) Professor Barry Adam, University of Windsor, Canada, Contributor to International Seminar, 25-27 January 2002.

- (2002) Professor Bernadette Bawin-Legros, University of Liege, Contributor to International Seminar, 25-27 January 2002.

(2002) Professor Irene Levin, Oslo University, Contributor to International Seminar, 25-27 January 2002.

(2002) Professor Ray Pahl, University of Essex, Contributor to International Seminar, 25-27 January 2002.

(2002) Dr Judith Stacey, University of Southern California, Contributor to International Seminar, 25-27 January 2002.

(2002) Professor Selma Sevenhuisjen, University of Utrecht, contributor to CAVA ‘Care’ Workshop, 15 February 2002.

- (2002) Professor Lauren Berlant, Centre for Gender Studies, University of Chicago, May 2002.

- (2002) Roshni Basu, Centre for Feminist Legal Research, New Delhi, Visiting Fellow in the Centre for Interdisciplinary Gender Studies, funded by Leverhulme Interchange, May-June 2002.

(2002) Mallarika Sinha Roy, Centre for Feminist Legal Research, New Delhi, Visiting Fellow in the Centre for Interdisciplinary Gender Studies, funded by Leverhulme Interchange, May-June 2002.

(2002-3) Dr. Helen O’Grady, American Association of University Women Postdoctoral Fellow in the Centre for Interdisciplinary Gender Studies, funded by an American Association of University Women Post-doctoral Fellowship, working on a project on the ‘The Ethics of Care for the Self’, 1 June 2002 to 30 August 2003.

(2002-3) Dr Jacqui Gabb, Open University, Visiting Fellow in the Centre for Interdisciplinary Gender Studies, Leeds, July 2002 – June 2003.

- (2002) Professor Solveig Bergman, Abo Akademi, Contributor to International Seminar, 1-2 November 2002.

- (2002) Dr. Alexandra Dobrolowsky, St Mary’s University, Canada, Contributor to International Seminar, 1-2 November 2002.

(2002) Dr Anna Gavanas, Stockholm University, SUNY Stony Brook, Contributor to International Seminar, 1-2 November 2002.

(2002) Professor Jane Jenson, University of Montreal, Contributor to International Seminar, 1-2 November 2002.

(2002) Professor John Gillis, Department of History, Rutgers University, USA, November 2002.

- (2002) Professor Anneli Antonnen, University of Tampere, Finland, 5-27 November 2002.

(2002) Elena Galinova, Education Policy Studies, Penn State University, USA, December 2002.

- (2002) Professor Karen Blaisure, Department of Family and Consumer Sciences, Western Michigan University, USA, December 2002.

- (2003) Ms Helen Rhoades, Law School, University of Melbourne.

(2003) Antu Sorainen, University of Helsinki, Visiting Fellow in the Centre for Interdisciplinary Gender Studies, February 2003.

(2003-5) Dr Natalia Gerodetti, University of Lausanne, Visiting Fellow in the Centre for Interdisciplinary Gender Studies, March 2003 - March 2005.

(2003) Dr. Nirmal Kumar, Department of History, University of Delhi, Visiting Fellow in the Centre for Interdisciplinary Gender Studies, April to June 2003.

(2003) Dr. Mona Albahar, Department of Social Work, University of United Arab Emirates, Visiting Fellow in the Centre for Interdisciplinary Gender Studies, June to July 2003.

(2003-4) Professor Cristina Stevens, Department of English, University of Brasilia, Visiting Fellow in the Centre for Interdisciplinary Gender Studies, 1 August 2003 to 31 January 2004.

(2003) Professor Loretta Baldassar, University of Western Australia, Contributor to International Seminar, 19 September 2003.

(2003) Professor Cora Baldock, Murdoch University, Contributor to International Seminar, 19 September 2003.

(2003) Dr Roger Ballard, University of Manchester, Contributor to International Seminar, 19 September 2003.

(2003) Professor Mary Chamberlain, Oxford Brookes University, Contributor to International Seminar, 19 September 2003.

(2003) Professor Eleonore Kofman, Nottingham Trent University, Contributor to International Seminar, 19 September 2003.

(2003) Dr Parvati Raghuram, Nottingham Trent University, Contributor to International Seminar, 19 September 2003.

(2003) Professor Tony Warnes, University of Sheffield, Contributor to International Seminar, 19 September 2003.

(2003) Dr. John Murphy, Associate Professor, Politics and History, RMIT University, Melbourne, October 2003.

- (2003-4) T Sengedorj. Mongolian Pedagogical State University, Ulaan Baator, Mongolia, December 2003 to February 2004.

(2004) Dr Carol Johnson, School of History & Politics, University of Adelaide, Visiting Fellow in the Centre for Interdisciplinary Gender Studies, May 2004.

(2004) Dr Brinda Bose, Department of English, Hindu College, Delhi University, Visiting Fellow in the Centre for Interdisciplinary Gender Studies, September 2004.

(2005) Dr. Pauline Stoltz, Political Science, School of Technology and Society,Malmö University, Sweden. March–May 2005.

3. Membership of external committees and working parties

Ackers, H. L. (1998-2000) ‘Expert’ advisor to EURONET (the European Children’s network) in its development of a ‘Children’s Policy for European Union’ and also to the European Commission’s Research Directorate in the development of the European Research Area [Contract HPMA-CT-2000-02217]

Churchill, H. (2002 -) Postgraduate Coordinator, Women’s Workshop for Qualitative Research on Family and Household Research.

Deacon, A. (2001) Member Pensions Reform Group. January 2000-December 2001. Report Universal Protected Pension: Modernising Pensions for the Millenium, published by Institute of Community Studies, London, 18 October 2001.

Deacon, A. (2001-4) Chair, Social Policy Association, July 2001- August 2004.

- Deacon, A. (2001-5) Chair, Editorial Board, Social Policy and Society, July 2001 - January 2005.

Deacon, A. (2001-5) Member, Editorial Board, Journal of Social Policy, July 2001 - January 2005.

Deacon, A. (2000-3) Member of Advisory Group to ESRC research project Welfare to Work: A case for Evidence-Based Policy-Making. Loughborough and Nottingham Universities, Grant Holder: Professor Robert Walker. Part of ESRC Research Programme on Future Government.

Duncan, S. (1999-2001) Member, Editorial Board, Policy and Politics.

Duncan, S. (2000) Committee Membership Health Action Zone evaluation board, Bradford City Health Authority, 2000.

Duncan, S. (2003-5) Mentor for Central Asian Research Initiative, for PhD research at the Mongolian State University of Education on ‘Gender and the labour market’ 2003-5

Duncan, S. (2004) Expert rapporteur for end of research programme conference ‘Changing gender roles’ Karlstad University, Sweden, 10-13 May 2004.

Duncan, S. (2005) Member of HMG Dept Work and Pensions discussion panel on the constraints to lone parents' labour market participation 2005

- Hollway, W. (2003) Executive committee member of the International Research Group for Psycho-Societal Analysis.

Hollway, W. (2004) ESRC selection panel for commissioning of Research Methods nodes.

Martin, G. (2001-5) Convenor, BSA Study Group for Protest and Social Movements.

Martin, G. (2001-) Member, Editorial Advisory Board, Social Movement Studies.

Mason, J. (2000-2) Research Advisory Group member: Intergenerational Obligations among Young Pakistani People and their families, National Lotteries Board, University of Leeds.

Mason, J. (2001-3) Research Advisory Group member: Enduring Families, ESRC, University of Leeds.

Mason, J. (2001-3) Research Advisory Group Member: ‘Continuity and Change in Parent-Child Relations over 3 Generations’ ESRC, University of Leeds.

Mason, J. (2001-5) ESRC Research Resources Board Member, from September 2001.

Mason, J. (2002) Genomics Survey, Member of Commissioning Panel.

Mason, J. (2002), ESRC Research Methods Programme Phase One. Member and Vice Chair of Commissioning Panel

Mason, J. (2002-3) Editorial Board Member for two different Research Methodology 'boxed' set/handbook publications (Sage), and contributor to Sage Research Methods Encyclopaedia.

Mason, J. (2003) ESRC Research Methods Programme Phase Two Chair of Commissioning Panel.

- Mason, J. (2003) ESRC Postgraduate Research Training Interim Recognition Exercise, Member of Sociology Panel.

Mason, J. (2003) Interviewed as an expert respondent in Cabinet Office funded National Centre for Social Research study ‘Quality in Qualitative Evaluation’, Liz Spencer, Jane Ritchie, Jane Lewis, Lucy Dillon.

- Mason, J. (2003) ESRC Review of Qualitative Resources, Chair of Advisory Panel,

Mason, J. (2003) ESRC National Centre for Research Methods, member of team devising the specification.

Mason, J. (2003-4) ESRC Qualitative Longitudinal Feasibility Study, Chair of Advisory Panel.

Mason, J. (2004) ESRC Qualitative Data Sharing and Research Archiving, Chair of Commissioning Panel

Mason, J. (2004) Interviewed as an expert respondent in Prof. Alan Bryman’s ESRC Fellowship study of Mixing Qualitative and Quantitative Methods.

Mason, J. (2004) Interviewed as an expert respondent in ESRC funded Research Methods Programme study of ‘Informed Consent and the Research Process’, Rose Wiles, Sue Heath and Graham Crow.

- Neale, B. (1999 -2001) Research Advisory Group Member: Children and Family Change, National Lottery Funded, Parentline Plus, London.

Neale, B. (2000 -2002) Research Advisory Group Member: Child Contact After Divorce, Joseph Rowntree Foundation, University of Cambridge.

- Neale, B. (2001 -3) Research Advisory Group Member: Disabled Childhoods (ESRC Childhood 5-16 Programme), University of Leeds.

Neale, B. ((2001-3) Research Advisory Group Member: ‘Continuity and Change in Parent-Child Relations over 3 Generations’ ESRC, University of Leeds.

Neale, B. (2002-4) Research Advisory Group Member: Ethnic Minority Parenting, Joseph Rowntree Foundation, University of Leeds.

Neale, B. (2002-4) Research Advisory Group Member: Father’s Engagement with their Children, Joseph Rowntree Foundation, University of Oxford.

- Neale, B. (2003 -5) Research Advisory Group Member: Siblings in Middle Childhood, Joseph Rowntree Foundation, London South Bank University.

- Neale, B. (2004 -6) Research Advisory Group Member, Children Creating Kinship, ESRC, University of Leeds.

Neale, B. (2004-5) CAFCASS Yorkshire and Humberside Regional Strategy for Children’s Participation. Member of Steering Group.

- Neale, B. (2003-6) Member, ESRC Virtual College.

Neale, B. (2004 -)  Co- Convenor, BSA Family Studies Group,

Neale, B. (2004- ) European Sociological Association Childhood Network, member

Neale, B. (2004-) International Sociological Association, Research Committee 53 (Sociology of Childhood), Member and conference stream organiser

Roseneil, S. (1998-2000) Member, Local Research Ethics Committee, United Leeds Teaching Hospitals.

Roseneil, S. (1998-2002) International Sociological Association, Research Committee 47 (Social Movements and Social Classes), Secretary/Treasurer

Roseneil, S. (1999-2003) Member of Women’s Movements and Internationalisation Research Network, funded by Nordic Council of Ministers.

Roseneil, S. (2000-) Editorial Board Member, Social Movement Studies.

Roseneil, S. (2000-) Founding Editor, Feminist Theory.

Roseneil, S. (2002-) Virtual Advisory Board Member, International Bibliography of the Social Sciences (IBSS).

Roseneil, S. (2002-) Management Board Member, AHRB Centre for Cultural Analysis, Theory and History (CentreCATH), University of Leeds.

Roseneil, S. (2002) Consultant to University College Cork on PhD Programme in Women’s Studies

Roseneil, S. (2002) International Advisor, Swiss National Science Foundation.

Roseneil, S. (2003) Advisor to the Vice Chancellor of University of Copenhagen on establishment of Gender Studies programmes.

Roseneil, S. (2003) International Referee, Nordic Research Council.

Roseneil, S. (2004) International Referee, European Science Foundation.

Roseneil, S. (2004-7) International Expert Advisor, Research Council of Norway.

Roseneil, S. (2005) Canada Research Chairs, College of Reviewers.

Smart, C. (1999-2003) Committee Member, Children, Young People and Families, Joseph Rowntree Foundation.

Smart, C. (1999-2005) Research Advisory Group member: Family Restructuring, the Common Law Marriage Myth and the Need for Legal Realism Project.  Nuffield Foundation,  University of Aberystwyth

Smart, C. (1999) Chair of the Review Panel of the Women’s Studies Dept, University of Manchester

Smart, C. (2000) External Assessor for the Director of the Gender Institute, LSE

Smart, C. (2000) External Assessor for the Chair in Sociology, University of Lancaster

Smart, C. (2001) Member of the Review Panel of the Dept of Sociology, National University of Singapore

Smart, C. (2001) Consultant to the University of Cardiff, School of Social Science RAE return

Smart, C. (2001) External Assessor for the Chair in Sociology, University of Southampton

Smart, C. (2001) External Assessor for the Chair in Women’s Studies, University of Hull

Smart, C. (2002-7) Advisory Board to the Thomas Coram Research Centre

Smart, C. (2002) External Assessor for Chair in Sociology at LSE

Smart, C. (2002) External Assessor for Chair in Socio-Legal Studies, University of Bristol

Smart, C. (2002-) External Assessor to the Department of Sociology, LSE

Smart, C. (2003) External Assessor for the Chair in Sociology, University of Essex

Smart, C. (2003) ESRC Task Group on Peer Review

Smart, C. (2004) External Assessor for the Chair in Women’s Studies, University of Lancaster.

Smart, C. (2004) External Assessor for the Chair in Sociology, University of Manchester.

- Smart, C. (2004-6) Associate, National Family and Parenting Institute (NFPI).

Terry-Schuhmann, J. (2001-) Member, Voluntary Sector Studies Network.

Williams, F. (1984-2003) Editorial Board Member, Critical Social Policy.

Williams, F. (1996 – 2003) International Editor, Critical Social Policy

Williams, F. (1996- ) Member, Network on ‘Gender, Welfare and Citizenship in Europe’

Williams, F. (1997–2002) Member, International Network on Recognition Struggles, funded by the Central Bank of Sweden.

Williams, F. (1998 – 1999) ESRC Growing Older: Extending the Quality of Life Research Programme, Member of Commissioning Panel

Williams, F. (1999 -) Research Advisory Group Member, ‘Politics, Power and Political Renewal’, ESRC,  University of Birmingham.

Williams, F. (2000) Assessor, Academic Review of Dept of Applied Social Sciences, University of Stirling.

Williams, F. (2000-1) Member, ESRC Selection Panel “Changing Families”, Research Centres Competition, 2000.

Williams, F. (2000-3) Member, ESRC’s Sociology, History Anthropology and Resources (SHAR) Research College.

Williams, F. (2000 -) Fellow, The Royal Society for the Arts.

Williams, F. (2001) Editorial Board Member, National Council Member, Catalyst, independent think-tank.

Williams, F. (2001 -) Research Advisory Group Member, ‘Families and Social Capital’, ESRC Research Group, South Bank University.

Williams, F. (2001-2) Member, ESRC Review Panel, Centre for Social Exclusion (CASE), London School of Economics.

Williams, F. (2001 -) Member, Regional Committee of WITNE, (Women in the New Economy), policy making forum organised by Yorkshire and Humberside Government Office.

Williams, F. (2002) Scientific Committee Member, International Congress on Child Migration, Child Migrants’ Trust.

Williams, F. (2002-3) Member, Advisory Board, Ethics, Rights and Trust, New ESRC Research Programme Proposal.

Williams, F. (2002 -) Academician, Learned Societies in the Social Sciences.

Williams, F. (2002 -) Associate, National Family and Parenting Institute (NFPI).

Williams, F. (2003 -) Co-Editor, Social Politics: International Studies in Gender, State and Society

Williams, F. (2003 -) Member, Advisory Board, Social Contexts and Responses to Risk, ESRC Research Network.

Williams, F. (2003-5) Member, National Commission on the Future of the Family and the Well-being of Children, National Family and Parenting Institute.

Williams, F. (2004) Advisory Board, Critical Social Policy

Williams, F. (2005 -) Research Advisory Group member: Identities in Process: Becoming African Caribbean, Bangladeshi and White mothers, ESRC (identities and Social Action programme), Open University.

Williams, F. (2005-8) RAE2008, subpanel member, UoA 40, Social Policy.

Annex E - Research Group Staff’s CVs

1. Funded Staff Members

------------------------------------------------------------------------------------------------------------------------------------------------

Title and name:	Professor Louise Ackers

Qualifications:	BSc (Econ), 1981, LSE; PhD, 1985, LSE; MA, 1986, London University; CPE, 1992, Nottingham Trent; PGCEL, 1993, Bristol; LLM, 1999, Bristol.

Current position:	Jean Monnet Chair in European Law, University of Leeds

Recent research/employment biography:

My work is concerned with the social dimension of European Union law and especially the social and legal issues around mobility within the European Union. My current work focuses on the gender dynamics of these forms of movement and the specific issue of highly skilled mobility. I am also Director of the Centre for the Study of Law and Policy in Europe (CSLPE) based in the School of Law at Leeds.

------------------------------------------------------------------------------------------------------------------------------------------------

Title and name:	Dr. Shelley Budgeon

Qualifications:	B.A. 1990 (University of Calgary); MA 1993 (University of British Columbia); PhD 2000, University of Leeds

Current position:	Senior Lecturer in Sociology, University of Birmingham.

Recent research/employment biography:

My broad research interests are in the sociology of gender and feminist theory. I have researched in the areas of feminist theory and epistemology, gender relations, cultural and social theory, ethics, the body and embodiment, theorising subjectivity and identity, sexuality, and intimacy and personal relationships. From 2000 to 2002, I was employed as a CAVA research fellow on the non conventional partnerships study.

------------------------------------------------------------------------------------------------------------------------------------------------

Title and name:	Professor Alan Deacon,

Qualifications:		BSc (Soc) 1969, LSE; PhD 1979, LSE

Current position:	Professor of Social Policy, University of Leeds.

Recent research/employment biography:

My primary research interests are in the current debates about the future direction of welfare reform in Britain and the United States, and the competing understandings of human nature and of the self that underpin those debates. I am currently working on three inter-related issues: the assumptions about human nature and motivation that underpin recent writings on the ‘ethic of care’; the commonalities between arguments for an ethic of care and communitarian justifications for ‘conditionality in welfare’; contrasting analyses of inter-generational continuities in social deprivation.

------------------------------------------------------------------------------------------------------------------------------------------------

Title and name:	Professor Simon Duncan

Qualifications:		BA; PhD; Svenska 3

Current position:	Professor in Comparative Social Policy, University of Bradford

Recent research/employment biography:

Current research interests lie in the area of family lives and social policy, especially in parenting, partnering and the work-life balance; marriage, cohabitation, and the law, and in the comparative gender inequality in European welfare states. Previously I have worked on the relative success and failure of different European housing systems, and on local–central government relations.

------------------------------------------------------------------------------------------------------------------------------------------------

Title and name:	Dr. Jacqui Gabb

Qualifications:	BA (Hons) Film & Television Studies; MA Women's Studies; PhD Women's Studies (York)

Current position:	Staff Tutor, Open University (Yorkshire Region); Research Associate, ESRC Centre for Socio-Cultural Change, Manchester/Open University

Recent research/employment biography:

I am part of a course team developing a new, third level, sociological unit around the theme of ‘defining the social' – exploring areas such as trust, care, security and loyalty. I am currently working on a research project – Behind Closed Doors: Researching Intimacy and Sexuality in Families. This project aims to problematize the concept of ‘intimacy’, and to develop understandings of how family members demonstrate love and affection, non-abusively, across generations – emotionally and physically. It will explore the effects of cultural debates, social policy and government legislation on families’ ‘intimate practices’ and how these cultural changes and social discourses structure the emotional currency of families. In the first instance the ESRC have funded a small scale, methodological pilot project (Mar 2005- Feb 2006) that will interrogate the potential of different methods of researching intimacy and emotion.

------------------------------------------------------------------------------------------------------------------------------------------------

Title and name:	Dr. Keleigh Groves

Qualifications:	BA (Hons.), 1998, Leeds; PhD, 2002, Leeds

Current position:	Research Manager, Centre for the Study of Law and Policy in Europe, University of Leeds

Recent research/employment biography:

Before March 2005, I worked for CAVA as communications co-ordinator, with responsibility for designing, implementing and monitoring the group’s dissemination strategy. I worked very closely with CAVA’s Director on the influential book ‘Rethinking Families’. My new role in CSLPE is also concerned with external relations, as well as writing research grant applications, supporting Centre projects and preparing publications. My research interests continue to be centred on welfare policies, social security and benefits fraud.

------------------------------------------------------------------------------------------------------------------------------------------------

Title and name:	Dr Sally Hines

Qualifications:	BA, MA, PhD

Current position:	Associate Lecturer

Recent research/employment biography:

I was a CAVA PhD Student and received my PhD in 2004 on ‘Care and Intimacy in Transgender Communities’. I am currently employed as a teaching assistant in the Department of Sociology and Social Policy at the University of Leeds, as an associate lecturer for the Open University and as associate lecturer and module leader in the Department of Cultural Studies at Sheffield Hallam University. I start an ESRC postdoctoral fellowship in October 2005.

------------------------------------------------------------------------------------------------------------------------------------------------

Title and name:	Professor Wendy Hollway

Qualifications:	BA (econ) Psychology, 2.1 (Sheffield, 1971); PhD in Social Psychology, (University of London 1982)

Current position:	Professor of Psychology, Faculty of Social Sciences, Open University and Director of Research Centre for Citizenship, Identities and Governance (CIG) (2004 to date)

Recent research/employment biography:

After leaving the University of Leeds, department of psychology (where I was made a professor in 2000) and my first three years at the Open University as Head of Psychology, I refocused on research. I was central to the development and institutionalisation of the Centre for Citizenship, Identities and Governance, which is one of five flagship research centres at the Open University. With Ann Phoenix I was successful in getting funding (£189K) under the ESRC programme ‘Identities and Social Action programme. The three-year project – on the identity transition to being a mother – started in April 2005. Using my final year buyout in CAVA, I have almost finished writing a book on the capacity to care, which will be published by Routledge in 2006.

------------------------------------------------------------------------------------------------------------------------------------------------

Title and name:	Dr. Yasmin Hussain

Qualifications:	BA; PhD

Current position:	Research Fellow, School of Sociology and Social Policy, University of Leeds

Recent research/employment biography:

My main interests are in the areas of the Ethnicity, Gender, Disability and Identity. I have carried out extensive research on the urban 'riots' in 2001, funded by the British Academy. I am also working on a Joseph Rowntree funded project on the role of higher education in providing opportunities for Young South Asian Women.  For CAVA I was employed as a research fellow on the strand three Transnational Kinship study.

------------------------------------------------------------------------------------------------------------------------------------------------

Title and name: 	Dr Sarah Irwin

Qualifications: 	BA (Leeds), PhD (Edinburgh)

Current position: 	Senior Lecturer, School of Sociology and Social Policy, University of Leeds

Recent research/employment biography:

Recently I have completed my book Reshaping Social Life to be published with Routledge, which develops a new set of conceptual arguments developed through grounded empirical analyses. I have completed research with CAVA, and intend further publication, specifically on the integrative analysis. I am a co-applicant on, and Deputy Director of, the Real Life Methods Node of the ESRC National Centre for Research Methods.

------------------------------------------------------------------------------------------------------------------------------------------------

Title and name:	Dr Hazel May

Qualifications:	PhD

Current position:	No longer working in academia

Recent research/employment biography:

Dr. May was employed as CAVA communications officer.  In 2002, she took up a post as lecturer in Criminology at the University of Sheffield. She subsequently changed career direction and emigrated to America in 2003.

------------------------------------------------------------------------------------------------------------------------------------------------

Title and name:	Dr. Greg Martin

Qualifications:	BA. PhD

Current position:	No longer working in academia

Recent research/employment biography:

Dr Martin was employed as a CAVA research fellow on strand five of the study. He left in 2003 to travel abroad.

------------------------------------------------------------------------------------------------------------------------------------------------

Title and name:	Dr. Jennifer Mason

Qualifications:		Bsc Hons (Soc. Sci) Sociology, Southampton.

PhD Sociology, Kent.

Current position:	Director, Leeds Social Sciences Institute, University of Leeds; Deputy Director of the Centre for Research on Family, Kinship and Childhood; Director of the Real Life Methods Node of the National Centre for Research Methods

Recent research/employment biography:

My research focuses on kinship and family relationships, and I have a strong interest in research methodology, particularly qualitative and mixed method approaches.

------------------------------------------------------------------------------------------------------------------------------------------------

Title and name:             Dr. Bren Neale

Qualifications:		BA; (CNAA 1974); PhD (Leeds 1985)

Current position	ESRC Principal Research Fellow; Executive member of the Real Life Methods node of the National Centre for Research Methods

Recent research/employment biography:

My research interests are in the sociology of young lives, family processes, personal and intergenerational relationships across the life course, and qualitative research methods. My remit under my ESRC fellowship (2005-7) and under the new Real Life Methods node of the NCRM is to advance qualitative longitudinal and mixed methods in the context of research with young people.  I am currently consolidating my previous longitudinal research on childhood and divorce, and establishing a prospective study of young lives and personal relationships that is designed to run over a decade.

------------------------------------------------------------------------------------------------------------------------------------------------

Title and name: 	Professor Sasha Roseneil

Qualifications:	 	B.Sc. (Econ) Special Subject Sociology 1st (LSE 1988)

Ph.D. (LSE 1995)

Current position: 	Professor of Sociology and Gender Studies, School of Sociology and Social Policy, University of Leeds

Recent research/employment biography:

From 1997 to 2004 I was founding Director of the Centre for Interdisicplinary gender Studies at Leeds. There are two main substantive strands to my recent research i) personal life and social change, and ii) social movements, collective experience and political process. This work contributes to social theory and methodology more generally, most particularly through the theorization of individualization and the transformation of gender and sexuality, in developing psycho-social theory and queer theory, and in the theorization of the realm of the political within postmodernity.

------------------------------------------------------------------------------------------------------------------------------------------------

Title and name:	Dr. Lise Saugeres

Qualifications:	MA (Canadian Studies) Bordeaux; MA (Folklore Studies) Memorial University of Newfoundland; PhD (Human Geography) Manchester Metropolitan University.

Current position:	Post Doctoral Research Fellow

(Women’s Studies and Sociology, Monash University).

Recent research/employment biography:

Lise’s research interests include gender relations, cultural constructions of masculinities and femininities, the family, organisations and employment, discourses of social change, feminist theory and epistemology, and qualitative research methods. She was employed as a CAVA research fellow on the mothers and employment strand three project, and is currently working with Dr Maryanne Dever and Dr Jane Maree Maher in the Centre for Women's Studies and Gender Research at Monash University on a project on Family and Fertility Decisions in Victoria.

------------------------------------------------------------------------------------------------------------------------------------------------

Title and name:	Beccy Shipman

Qualifications		MA (Glasgow, 1998); MA (Warwick, 2001)

Current position:	Research Officer, Centre for Research on Family, Kinship & Childhood, University of Leeds

Recent research/employment biography:

I am currently working on an ESRC funded project entitled “Gay and Lesbian Marriage: An exploration of the meanings and significance of legitimating same sex relationships”. I previously worked as a research assistant on the CAVA Transnational Kinship study. My research interests include relationships, sexualities, families, and rituals. I am also interested in visual and narrative methods in qualitative research. I was employed in CAVA on the Transnational Kinship project.

------------------------------------------------------------------------------------------------------------------------------------------------

Title and name:	Jessica Shipman

Qualifications:	BA Hons (Liverpool John Moores, 2001); MA (Leeds, 2002)

Current position:	PhD Candidate, University of Adelaide, Australia.

Recent research/employment biography:

My general research interests are in the sociology of health and medicine, gender, sexualities and feminist methodologies. I worked as a research assistant on the Transnational Kinship Project in 2002. My current research is looking at the politics of ‘choice’ and ‘medicalisation’ in relation to the suppression of menstruation.

------------------------------------------------------------------------------------------------------------------------------------------------

Title and name:	Professor Carol Smart

Qualifications:		PhD, MA, BSc

Current position:	Professor of Sociology

Recent research/employment biography:

Since 1999 I have been Deputy Director of CAVA and (since 1997) Director of the Centre for Research on Family, Kinship & Childhood at the University of Leeds.  In addition to my role in the ESRC Research Group on Care, Values and the Future of Welfare I have held a number of ESRC grants on issues related to families and divorce and a grant from the Department for Constitutional Affairs for a project on conflict over contact and residence on divorce.

------------------------------------------------------------------------------------------------------------------------------------------------

Title and name:	Dr. Helen Stalford

Qualifications:		LLB (English and French Laws with French) University of Liverpool;

PhD, University of Leeds.

Current position:	Senior Lecturer, Liverpool Law School, University of Liverpool

Recent research/employment biography:

My research focuses on the impact of EU law on family and children's rights, with a focus on the experiences of children under the EU free movement of persons provisions. I am currently researching the nature, scope and effectiveness of the emerging EU family law governing cross-national family disputes within the EU. Of particular interest is how families negotiate child contact, residence and maintenance arrangements across geographical and legal spaces and the extent to which children are involved in these processes. All of this research has applied a qualitative approach, involving in-depth semi-structured interviews with children, parents and practitioners. I provided research support to CAVA in 1999-2000.

------------------------------------------------------------------------------------------------------------------------------------------------

Title and name:	Jackie Terry-Schuhmann

Qualifications:		MA, Disability Studies, University of Leeds

Current position:	PhD student, Year 4

Recent research/employment biography:

I am a CAVA PhD student. The aim of my research is to look at how notions about care, rights and charity get ‘worked out’ in the perceptions and practices of, and interactions between, volunteers and service users in local community volunteer services for disabled older people. Previous employment – 14 years in personnel management in the electricity supply industry; 9 years in the voluntary sector – working with volunteers and promoting volunteering.

------------------------------------------------------------------------------------------------------------------------------------------------

Title and name:	Professor Fiona Williams

Qualifications:		B.Sc Soc.Hons, PhD

Current position:	Professor of Social Policy and Director of the CAVA Research Centre,

University of Leeds

Recent research/employment biography:

My current research focuses on the place of care in contemporary society and it covers the ethical, social, political and international dimensions of care. I have also researched and written about gender, 'race', ethnicity, and disability. Central to my work is a concern to find ways in which people, especially those who have been marginalized, can themselves define the nature of the problems they face.

2. Co-Funded Staff Members

------------------------------------------------------------------------------------------------------------------------------------------------

Title and name:	Dr. Harriet Churchill

Qualifications:		BA (Hons) 1994; PhD 2004.

Current position:	Research Fellow, ESRC CAVA Group, University of Leeds.

Recent research/employment biography:

My research interests bridge sociological and social policy debates about family lives, theories on inequality, subjectivity and identities, and research methods.  My current research, undertaken with Professor Fiona Williams, considers parental empowerment and forms of individual / collective agency facilitated by local Sure Start programmes.  This study is funded by the National Evaluation of Sure Start, and explores the Impact of six Sure Start local programmes, employing a multi media case study approach.

------------------------------------------------------------------------------------------------------------------------------------------------

Title and name: 	Dr. Anna Gavanas

Qualifications: 	PhD

Current position: 	Marie Curie Research Fellow, CAVA Centre, University of Leeds

Recent research/employment biography:

For CAVA I am currently working on a project on  "Migrant Domestic Workers in European Care Regimes"

This investigates parental strategies to reconcile new demands in work and care in conjunction with the increasing European demand for migrant domestic workers in three contrasting welfare states: the U.K., Sweden and Spain. It explores the diversity of relations between employers and employees in domestic work with a focus on child care. The project highlights localised concepts of appropriate care in relation to welfare policies, migration policies and the global division of domestic and care work.

------------------------------------------------------------------------------------------------------------------------------------------------