ESRC Research: ‘Gender Diversity, Recognition and Citizenship’

Timetable: 24 months

Phase One (months 1-3) April-June

1. An advisory group will be established at the start of the project.

2. The advisory group will hold its first face-to-face meeting. It is anticipated that the advisory group will hold two face-to-face meetings- the first of which will be in month 3 and the second in month 23 - and one mid-point (month 12) virtual meting in which emerging findings will be disseminated.

3. The literature review will be brought up to date.

During Phase 1, the PI will work on the above tasks

Phase Two (months 4-6) July-September

1. The research will be publicized through relevant regional transgender community groups and on transgender internet sites.

2. All the individuals that express an interest will be asked to complete a biographic profile form either on the phone or to be returned by post.

3. 25 people will be selected for interview in line with the sampling strategy.

4. A pilot interview will be held.

5. Focus group members will be selected.

6. Interview schedules will be formulated and focus group questions developed.

During Months 4-5 in Phase 2, the PI will work on: publicizing the research, formulating the interview schedules, selecting the interviewees, setting up the focus groups. The RA will begin work in Month 6 of Phase 2 (Sep 08) and will carry out the pilot interview and work on formulating the interview schedules with the PI.

Phase Three (months 7-12) October - March

1. 25 interviews will be conducted.

2. Interviews will be transcribed.

3. Virtual research methods will be employed to analyse web-based materials, such as individual BLOGS and on-line collective responses to the GRA from transgender campaigning organisations and support groups.

4. Textual analysis of policy documents will take place (the GRA)

5. The two focus groups will take place.

6. The advisory group will have a virtual meeting.

During all the months of Phase 3, the PI and RA will work on the project.

Phase Four (months 13-18) April – September

1. Coding of data will be structured around the core theoretical concerns: the meaning, significance, and experiences of gender recognition.

2. Themes will be extrapolated from across the data and analyzed.

3. Initial findings will be presented at the British Sociological Association (BSA) and the Social Policy Association (SPA) 2009 conferences.

4. Writing up will begin.

During months 13-17 of Phase 4, the PI and RA will work on the project.  The RA will code data, managed by the PI, and will begin data analysis. Initial findings will be co-presented at BSA and SPA conferences (this will meet staff development plans for the RA set out in the proposal).  The RA will stop working on the project at the end of Month 17 (Aug 08).  The PI will continue with writing up.

Phase Five (months 19-24) October - March

1. The advisory group will have its second face-to-face meeting.

2. Writing up will continue.

3. User-group and media dissemination will take place and academic publications will be written.

4. Research outcomes and future research developments will be discussed with the advisory group and funding proposals will be developed as appropriate.

5. A final report will be written for the ESRC and data sets will be built for ESRC archiving.

During Phase 5, the PI will work on the above tasks

The timetable indicates the approximate time allocation for each area of research and related activities. There will, however, be flexibility across the five phases.